## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | PROJECT Production Line Change | 1 |  |  | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 | 669.375
1 | Design | 1.1 |  | FS23 | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 406.375
26 | Refueling Test P8X | 1.2 |  |  | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 | 28.375
2 | Definition of 2D and 3D for prototypes for P8X | 1.2.1 |  | FS3 | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 0.375
3 | Prototype components assembly &amp; refueling test for P8X | 1.2.2 | 2FS | FS4;FS6;FS7 | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 28.375
27 | Refueling Test P1UO | 1.3 |  |  | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 | 28.375
4 | Definition of 2D and 3D for prototypes for P1UO | 1.3.1 | 3FS | FS5;FS10 | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 0.375
5 | Prototype components assembly &amp; refueling test for P1UO | 1.3.2 | 4FS | FS8;FS9;FS15;FS16;FS17;FS18;FS19 | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 28.375
6 | Produce Filler Pipe Blow molds P8x | 1.4 | 3FS | FS11;FS12;FS20 | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 210.375
7 | Produce Filler Pipe Calibrations P8x | 1.5 | 3FS | FS20 | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 217.375
8 | Produce Filler Pipe Blow mold P1UO | 1.6 | 5FS | FS21 | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 162.375
9 | Produce Filler Pipe Calibration P1UO | 1.7 | 5FS | FS21 | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 169.375
10 | Filler pipe Welding/assembly machine Liberec | 1.8 | 4FS | FS13;FS14 | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 388.375
11 | Modification Welding lines Lokeren ‚6D | 1.9 | 6FS | FS23 | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 | 137.375
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 1.10 | 6FS | FS23 | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 | 137.375
13 | Mariage welder Rennes | 1.11 | 10FS | FS23 | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 214.375
14 | Modification assembly line Rennes | 1.12 | 10FS | FS23 | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 211.375
15 | Modification Leak Tester Rennes | 1.13 | 5FS | FS23 | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 176.375
16 | Mariage welder Sochaux ‚6D | 1.14 | 5FS | FS23 | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 | 294.375
17 | Modification assembly line Sochaux ‚6D | 1.15 | 5FS | FS23 | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 | 144.375
18 | Modification Leak Tester Sochaux ‚6D | 1.16 | 5FS | FS23 | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 | 144.375
19 | Modification Sequencer and conveyors Sochaux ‚6D | 1.17 | 5FS | FS23 | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 | 179.375
20 | Production for VRS P8x | 1.18 | 6FS;7FS | FS22 | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 | 25.375
21 | Production for VRS P1UO | 1.19 | 8FS;9FS | FS23 | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 | 88.375
22 | Production for homologation P8x | 1.20 | 20FS | FS23 | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 | 28.375
23 | Finalization of all test runs, design systems and go life | 1.21 | 1FS;11FS;12FS;13FS;14FS;15FS;16FS;17FS;18FS;19FS;21FS;22FS |  | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 | 11.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT Production Line Change | 3840h
1 | Design | 2328h | standard - no risk | 99 | 100 | 101
26 | Refueling Test P8X | 168h
2 | Definition of 2D and 3D for prototypes for P8X | 8h | standard - no risk | 99 | 100 | 101
3 | Prototype components assembly &amp; refueling test for P8X | 168h | standard - no risk | 99 | 100 | 101
27 | Refueling Test P1UO | 168h
4 | Definition of 2D and 3D for prototypes for P1UO | 8h | standard - no risk | 99 | 100 | 101
5 | Prototype components assembly &amp; refueling test for P1UO | 168h | standard - no risk | 99 | 100 | 101
6 | Produce Filler Pipe Blow molds P8x | 1208h | standard - no risk | 99 | 100 | 101
7 | Produce Filler Pipe Calibrations P8x | 1248h | standard - no risk | 99 | 100 | 101
8 | Produce Filler Pipe Blow mold P1UO | 936h | standard - no risk | 99 | 100 | 101
9 | Produce Filler Pipe Calibration P1UO | 976h | standard - no risk | 99 | 100 | 101
10 | Filler pipe Welding/assembly machine Liberec | 2216h | standard - no risk | 99 | 100 | 101
11 | Modification Welding lines Lokeren ‚6D | 800h | standard - no risk | 99 | 100 | 101
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 800h | standard - no risk | 99 | 100 | 101
13 | Mariage welder Rennes | 1240h | standard - no risk | 99 | 100 | 101
14 | Modification assembly line Rennes | 1216h | standard - no risk | 99 | 100 | 101
15 | Modification Leak Tester Rennes | 1016h | standard - no risk | 99 | 100 | 101
16 | Mariage welder Sochaux ‚6D | 1688h | standard - no risk | 99 | 100 | 101
17 | Modification assembly line Sochaux ‚6D | 840h | standard - no risk | 99 | 100 | 101
18 | Modification Leak Tester Sochaux ‚6D | 840h | standard - no risk | 99 | 100 | 101
19 | Modification Sequencer and conveyors Sochaux ‚6D | 1040h | standard - no risk | 99 | 100 | 101
20 | Production for VRS P8x | 160h | standard - no risk | 99 | 100 | 101
21 | Production for VRS P1UO | 504h | standard - no risk | 99 | 100 | 101
22 | Production for homologation P8x | 168h | standard - no risk | 99 | 100 | 101
23 | Finalization of all test runs, design systems and go life | 80h | standard - no risk | 99 | 100 | 101

## TP1
| TP Status Date | 2016-11-20 17:00 |  | TP Name | TP1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 15d | [5 empty] | 7116.9173 |  | 0.4294% |  | 6492.4812 | 8092.7835
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 15d | 8092.7835 | 187617.6976 | 347d 6h | -975.8662 | 0 | 7116.9173 | 187617.6976 | 4.135% | Started | 6492.4812 | 8092.7835
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 |  | 0 | 0 | 15000 | 1d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 |  | 0 | 0 | 56000 | 21d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 |  | 0 | 0 | 15000 | 1d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 |  | 0 | 0 | 45000 | 21d | 0 | 0 | 0 | 45000 | 0% | Not Started | 0 | 0
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 |  | 0 | 0 | 58000 | 151d | 0 | 0 | 0 | 58000 | 0% | Not Started | 0 | 0
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 |  | 0 | 0 | 22000 | 156d | 0 | 0 | 0 | 22000 | 0% | Not Started | 0 | 0
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 |  | 0 | 0 | 55000 | 117d | 0 | 0 | 0 | 55000 | 0% | Not Started | 0 | 0
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 |  | 0 | 0 | 20000 | 122d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 0
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 |  | 0 | 0 | 225000 | 277d | 0 | 0 | 0 | 225000 | 0% | Not Started | 0 | 0
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 |  | 0 | 0 | 8000 | 100d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 |  | 0 | 0 | 35000 | 100d | 0 | 0 | 0 | 35000 | 0% | Not Started | 0 | 0
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 |  | 0 | 0 | 345000 | 155d | 0 | 0 | 0 | 345000 | 0% | Not Started | 0 | 0
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 |  | 0 | 0 | 45000 | 152d | 0 | 0 | 0 | 45000 | 0% | Not Started | 0 | 0
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 |  | 0 | 0 | 9000 | 127d | 0 | 0 | 0 | 9000 | 0% | Not Started | 0 | 0
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 |  | 0 | 0 | 89000 | 211d | 0 | 0 | 0 | 89000 | 0% | Not Started | 0 | 0
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 |  | 0 | 0 | 50000 | 105d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 |  | 0 | 0 | 30000 | 105d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 |  | 0 | 0 | 40000 | 130d | 0 | 0 | 0 | 40000 | 0% | Not Started | 0 | 0
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 |  | 0 | 0 | 25000 | 20d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 |  | 0 | 0 | 25000 | 63d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 |  | 0 | 0 | 18000 | 21d | 0 | 0 | 0 | 18000 | 0% | Not Started | 0 | 0
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2017-01-10 17:00 |  | TP Name | TP2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 52d | [5 empty] | 17210 |  | 1.038% |  | 15700 | 28054.9828
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 52d | 28054.9828 | 252494.8454 | 468d | -10844.9828 | 0 | 17210 | 252494.8454 | 10% | Started | 15700 | 28054.9828
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 |  | 0 | 0 | 15000 | 1d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 |  | 0 | 0 | 56000 | 21d | 0 | 0 | 0 | 56000 | 0% | Not Started | 0 | 0
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 |  | 0 | 0 | 15000 | 1d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 |  | 0 | 0 | 45000 | 21d | 0 | 0 | 0 | 45000 | 0% | Not Started | 0 | 0
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 |  | 0 | 0 | 58000 | 151d | 0 | 0 | 0 | 58000 | 0% | Not Started | 0 | 0
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 |  | 0 | 0 | 22000 | 156d | 0 | 0 | 0 | 22000 | 0% | Not Started | 0 | 0
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 |  | 0 | 0 | 55000 | 117d | 0 | 0 | 0 | 55000 | 0% | Not Started | 0 | 0
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 |  | 0 | 0 | 20000 | 122d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 0
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 |  | 0 | 0 | 225000 | 277d | 0 | 0 | 0 | 225000 | 0% | Not Started | 0 | 0
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 |  | 0 | 0 | 8000 | 100d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 |  | 0 | 0 | 35000 | 100d | 0 | 0 | 0 | 35000 | 0% | Not Started | 0 | 0
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 |  | 0 | 0 | 345000 | 155d | 0 | 0 | 0 | 345000 | 0% | Not Started | 0 | 0
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 |  | 0 | 0 | 45000 | 152d | 0 | 0 | 0 | 45000 | 0% | Not Started | 0 | 0
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 |  | 0 | 0 | 9000 | 127d | 0 | 0 | 0 | 9000 | 0% | Not Started | 0 | 0
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 |  | 0 | 0 | 89000 | 211d | 0 | 0 | 0 | 89000 | 0% | Not Started | 0 | 0
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 |  | 0 | 0 | 50000 | 105d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 |  | 0 | 0 | 30000 | 105d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 |  | 0 | 0 | 40000 | 130d | 0 | 0 | 0 | 40000 | 0% | Not Started | 0 | 0
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 |  | 0 | 0 | 25000 | 20d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 |  | 0 | 0 | 25000 | 63d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 |  | 0 | 0 | 18000 | 21d | 0 | 0 | 0 | 18000 | 0% | Not Started | 0 | 0
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2017-04-19 17:00 |  | TP Name | TP3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 123d | [5 empty] | 119086.966 |  | 7.807% |  | 118037.415 | 146813.1936
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 123d | 66360.8247 | 235297.6804 | 436d 1h | -28498.8247 | 0 | 37862 | 235297.6804 | 22% | Started | 34540 | 66360.8247
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 |  | 0 | 0 | 15000 | 1d | 0 | 0 | 0 | 15000 | 0% | Not Started | 0 | 0
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 |  | 0 | 0 | 45000 | 21d | 0 | 0 | 0 | 45000 | 0% | Not Started | 0 | 0
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 18d | 6913.9073 | 50701.9868 | 132d | -673.9073 | 0 | 6240 | 50701.9868 | 12% | Started | 6960 | 6913.9073
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 18d | 2538.4615 | 7544.8718 | 53d 4h | 3376.5044 | 0 | 5914.966 | 7544.8718 | 25.17% | Started | 5537.415 | 2538.4615
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 |  | 0 | 0 | 55000 | 117d | 0 | 0 | 0 | 55000 | 0% | Not Started | 0 | 0
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 |  | 0 | 0 | 20000 | 122d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 0
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 |  | 0 | 0 | 225000 | 277d | 0 | 0 | 0 | 225000 | 0% | Not Started | 0 | 0
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 |  | 0 | 0 | 8000 | 100d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 |  | 0 | 0 | 35000 | 100d | 0 | 0 | 0 | 35000 | 0% | Not Started | 0 | 0
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 |  | 0 | 0 | 345000 | 155d | 0 | 0 | 0 | 345000 | 0% | Not Started | 0 | 0
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 |  | 0 | 0 | 45000 | 152d | 0 | 0 | 0 | 45000 | 0% | Not Started | 0 | 0
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 |  | 0 | 0 | 9000 | 127d | 0 | 0 | 0 | 9000 | 0% | Not Started | 0 | 0
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 |  | 0 | 0 | 89000 | 211d | 0 | 0 | 0 | 89000 | 0% | Not Started | 0 | 0
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 |  | 0 | 0 | 50000 | 105d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 |  | 0 | 0 | 30000 | 105d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 |  | 0 | 0 | 40000 | 130d | 0 | 0 | 0 | 40000 | 0% | Not Started | 0 | 0
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 |  | 0 | 0 | 25000 | 20d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 |  | 0 | 0 | 25000 | 63d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 |  | 0 | 0 | 18000 | 21d | 0 | 0 | 0 | 18000 | 0% | Not Started | 0 | 0
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2017-08-04 17:00 |  | TP Name | TP4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 200d | [5 empty] | 236467.0693 |  | 15.44% |  | 233457.6406 | 294932.9682
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 200d | 107903.7801 | 66023.6254 | 122d 3h | -1150.0207 | 0 | 106753.7594 | 66023.6254 | 62.03% | Started | 97387.218 | 107903.7801
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 22d | [5 empty] | 43050 |  | 77.5% |  | 46500 | 60000
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 100% | Finished | 15000 | 15000
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 22d | 47142.8571 | 20089.2857 | 9d 3h | -18442.8571 | 0 | 28700 | 20089.2857 | 70% | Started | 31500 | 45000
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 95d | 36490.0662 | 125410.596 | 326d 4h | -24771.7564 | 0 | 11718.3099 | 125410.596 | 22.54% | Started | 13070.4225 | 36490.0662
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 95d | 13397.4359 | 40192.3077 | 285d | -7522.4359 | 0 | 5875 | 40192.3077 | 25% | Started | 5500 | 13397.4359
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 |  | 0 | 0 | 55000 | 117d | 0 | 0 | 0 | 55000 | 0% | Not Started | 0 | 940.1709
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 |  | 0 | 0 | 20000 | 122d | 0 | 0 | 0 | 20000 | 0% | Not Started | 0 | 327.8689
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 |  | 0 | 0 | 225000 | 277d | 0 | 0 | 0 | 225000 | 0% | Not Started | 0 | 4873.6462
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 |  | 0 | 0 | 8000 | 100d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 |  | 0 | 0 | 35000 | 100d | 0 | 0 | 0 | 35000 | 0% | Not Started | 0 | 0
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 |  | 0 | 0 | 345000 | 155d | 0 | 0 | 0 | 345000 | 0% | Not Started | 0 | 0
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 |  | 0 | 0 | 45000 | 152d | 0 | 0 | 0 | 45000 | 0% | Not Started | 0 | 0
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 |  | 0 | 0 | 9000 | 127d | 0 | 0 | 0 | 9000 | 0% | Not Started | 0 | 0
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 |  | 0 | 0 | 89000 | 211d | 0 | 0 | 0 | 89000 | 0% | Not Started | 0 | 0
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 |  | 0 | 0 | 50000 | 105d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 |  | 0 | 0 | 30000 | 105d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 |  | 0 | 0 | 40000 | 130d | 0 | 0 | 0 | 40000 | 0% | Not Started | 0 | 0
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 |  | 0 | 0 | 25000 | 20d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 |  | 0 | 0 | 25000 | 63d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 |  | 0 | 0 | 18000 | 21d | 0 | 0 | 0 | 18000 | 0% | Not Started | 0 | 0
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2017-09-21 17:00 |  | TP Name | TP5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 234d | [5 empty] | 516473 |  | 34.17% |  | 516610 | 440829.7082
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 234d | 126247.4227 | 67979.3814 | 126d | -14382.4227 | 0 | 111865 | 67979.3814 | 65% | Started | 102050 | 126247.4227
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 56d | [5 empty] | 55350 |  | 100% |  | 60000 | 60000
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 100% | Finished | 15000 | 15000
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 56d | 120000 | 0 | 0 | -79000 | 0 | 41000 | 0 | 100% | Finished | 45000 | 45000
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 129d | 49549.6689 | 0 | 0 | 2450.3311 | 0 | 52000 | 0 | 100% | Finished | 58000 | 49549.6689
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 129d | 18192.3077 | 0 | 0 | 5307.6923 | 0 | 23500 | 0 | 100% | Finished | 22000 | 18192.3077
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 2017-08-04 | 35d | 16452.9915 | 55058.7607 | 117d 1h | -4837.9915 | 0 | 11615 | 55058.7607 | 23% | Started | 12650 | 16923.0769
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 2017-08-04 | 35d | 5737.7049 | 38401.6393 | 234d 2h | -3007.7049 | 0 | 2730 | 38401.6393 | 13% | Started | 2600 | 5901.6393
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 2017-08-04 | 35d | 28429.6029 | 55234.657 | 68d | 53170.3971 | 0 | 81600 | 55234.657 | 34% | Started | 76500 | 32490.9747
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 |  | 0 | 0 | 8000 | 100d | 0 | 0 | 0 | 8000 | 0% | Not Started | 0 | 0
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 |  | 0 | 0 | 35000 | 100d | 0 | 0 | 0 | 35000 | 0% | Not Started | 0 | 0
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 2017-08-21 | 24d | 53419.3548 | 118802.4194 | 53d 3h | 49500.6452 | 0 | 102920 | 118802.4194 | 31% | Started | 106950 | 53419.3548
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 2017-08-21 | 24d | 7105.2632 | 71829.7697 | 242d 5h | -2092.2632 | 0 | 5013 | 71829.7697 | 9% | Started | 4050 | 7105.2632
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 2017-08-04 | 35d | 2480.315 | 25077.7559 | 353d 7h | -1670.315 | 0 | 810 | 25077.7559 | 9% | Started | 810 | 0
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 |  | 0 | 0 | 89000 | 211d | 0 | 0 | 0 | 89000 | 0% | Not Started | 0 | 0
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 |  | 0 | 0 | 50000 | 105d | 0 | 0 | 0 | 50000 | 0% | Not Started | 0 | 0
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 |  | 0 | 0 | 30000 | 105d | 0 | 0 | 0 | 30000 | 0% | Not Started | 0 | 0
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 |  | 0 | 0 | 40000 | 130d | 0 | 0 | 0 | 40000 | 0% | Not Started | 0 | 0
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 |  | 0 | 0 | 25000 | 20d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 |  | 0 | 0 | 25000 | 63d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 |  | 0 | 0 | 18000 | 21d | 0 | 0 | 0 | 18000 | 0% | Not Started | 0 | 0
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP6
| TP Status Date | 2017-11-14 17:00 |  | TP Name | TP6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 272d | [5 empty] | 790691.5 |  | 52.18% |  | 788950 | 686858.4356
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 272d | 146749.1409 | 0 | 0 | 25350.8591 | 0 | 172100 | 0 | 100% | Finished | 157000 | 146749.1409
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 56d | [5 empty] | 55350 |  | 100% |  | 60000 | 60000
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 100% | Finished | 15000 | 15000
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 56d | 120000 | 0 | 0 | -79000 | 0 | 41000 | 0 | 100% | Finished | 45000 | 45000
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 129d | 49549.6689 | 0 | 0 | 2450.3311 | 0 | 52000 | 0 | 100% | Finished | 58000 | 58000
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 129d | 18192.3077 | 0 | 0 | 5307.6923 | 0 | 23500 | 0 | 100% | Finished | 22000 | 22000
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 2017-08-04 | 73d | 34316.2393 | 4230.7692 | 9d | 10628.7607 | 0 | 44945 | 4230.7692 | 89% | Started | 48950 | 34786.3248
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 2017-08-04 | 73d | 11967.2131 | 1475.4098 | 9d | 6722.7869 | 0 | 18690 | 1475.4098 | 89% | Started | 17800 | 12131.1475
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 2017-08-04 | 73d | 59296.0289 | 78587.5451 | 96d 6h | 43903.9711 | 0 | 103200 | 78587.5451 | 43% | Started | 96750 | 63357.4007
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 | 2017-10-23 | 17d | 1360 | 9100 | 113d 6h | -164 | 0 | 1196 | 9100 | 13% | Started | 1040 | 1360
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 | 2017-10-23 | 17d | 5950 | 25375 | 72d 4h | -288 | 0 | 5662 | 25375 | 19% | Started | 6650 | 5950
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 2017-08-21 | 62d | 138000 | 132713.7097 | 59d 5h | 31320 | 0 | 169320 | 132713.7097 | 51% | Started | 175950 | 138000
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 2017-08-21 | 62d | 18355.2632 | 42816.6118 | 144d 5h | -1645.2632 | 0 | 16710 | 42816.6118 | 30% | Started | 13500 | 18355.2632
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 2017-08-04 | 73d | 5173.2283 | 18345.4724 | 258d 7h | -3193.2283 | 0 | 1980 | 18345.4724 | 22% | Started | 1980 | 2622.0472
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 | 2017-09-25 | 37d | 15606.6351 | 42180.0948 | 100d | 12473.3649 | 0 | 28080 | 42180.0948 | 27% | Started | 24030 | 15606.6351
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 | 2017-09-25 | 37d | 17619.0476 | 35773.8095 | 75d 1h | -3610.5476 | 0 | 14008.5 | 35773.8095 | 33% | Started | 16500 | 17619.0476
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 | 2017-09-25 | 37d | 10571.4286 | 22464.2857 | 78d 5h | -5451.4286 | 0 | 5120 | 22464.2857 | 32% | Started | 9600 | 10571.4286
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 | 2017-09-21 | 39d | 12000 | 138000 | 448d 4h | -7840 | 0 | 4160 | 138000 | 8% | Started | 3200 | 0
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 | 2017-11-06 | 7d | 8750 | 35000 | 28d | -3150 | 0 | 5600 | 35000 | 20% | Started | 5000 | 8750
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 |  | 0 | 0 | 25000 | 63d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 |  | 0 | 0 | 18000 | 21d | 0 | 0 | 0 | 18000 | 0% | Not Started | 0 | 0
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP7
| TP Status Date | 2018-02-20 17:00 |  | TP Name | TP7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 342d | [5 empty] | 1129790 |  | 74.5% |  | 1126430 | 1138969.7528
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 272d | 146749.1409 | 0 | 0 | 25350.8591 | 0 | 172100 | 0 | 100% | Finished | 157000 | 157000
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 56d | [5 empty] | 55350 |  | 100% |  | 60000 | 60000
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 100% | Finished | 15000 | 15000
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 56d | 120000 | 0 | 0 | -79000 | 0 | 41000 | 0 | 100% | Finished | 45000 | 45000
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 129d | 49549.6689 | 0 | 0 | 2450.3311 | 0 | 52000 | 0 | 100% | Finished | 58000 | 58000
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 129d | 18192.3077 | 0 | 0 | 5307.6923 | 0 | 23500 | 0 | 100% | Finished | 22000 | 22000
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 2017-08-04 | 143d | 67222.2222 | 0 | 0 | -16722.2222 | 0 | 50500 | 0 | 100% | Finished | 55000 | 55000
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 2017-08-04 | 143d | 23442.623 | 2889.3443 | 17d 5h | -4752.623 | 0 | 18690 | 2889.3443 | 89% | Started | 17800 | 20000
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 2017-08-04 | 143d | 116155.2347 | 71175.5415 | 87d 5h | 32644.7653 | 0 | 148800 | 71175.5415 | 62% | Started | 139500 | 120216.6065
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 | 2017-10-23 | 87d | 6960 | 0 | 0 | 2240 | 0 | 9200 | 0 | 100% | Finished | 8000 | 6960
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 | 2017-10-23 | 87d | 30450 | 0 | 0 | -650 | 0 | 29800 | 0 | 100% | Finished | 35000 | 30450
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 2017-08-21 | 132d | 293806.4516 | 0 | 0 | 38193.5484 | 0 | 332000 | 0 | 100% | Finished | 345000 | 293806.4516
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 2017-08-21 | 132d | 39078.9474 | 0 | 0 | 16621.0526 | 0 | 55700 | 0 | 100% | Finished | 45000 | 39078.9474
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 2017-08-04 | 143d | 10133.8583 | 0 | 0 | -1133.8583 | 0 | 9000 | 0 | 100% | Finished | 9000 | 7582.6772
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 | 2017-09-25 | 107d | 45132.7014 | 122005.9242 | 289d 2h | -17052.7014 | 0 | 28080 | 122005.9242 | 27% | Started | 24030 | 45132.7014
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 | 2017-09-25 | 107d | 50952.381 | 76428.5714 | 160d 4h | -33972.381 | 0 | 16980 | 76428.5714 | 40% | Started | 20000 | 50000
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 | 2017-09-25 | 107d | 30571.4286 | 64964.2857 | 227d 3h | -25451.4286 | 0 | 5120 | 64964.2857 | 32% | Started | 9600 | 30000
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 | 2017-09-21 | 109d | 33538.4615 | 100615.3846 | 327d | -20538.4615 | 0 | 13000 | 100615.3846 | 25% | Started | 10000 | 20615.3846
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 | 2017-11-06 | 77d | 96250 | 10625 | 8d 4h | -71050 | 0 | 25200 | 10625 | 90% | Started | 22500 | 25000
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 |  | 0 | 0 | 25000 | 63d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 9126.9841
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 | 2017-11-14 | 71d | 60857.1429 | 0 | 0 | -45157.1429 | 0 | 15700 | 0 | 100% | Finished | 18000 | 18000
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP8
| TP Status Date | 2018-04-28 17:00 |  | TP Name | TP8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 390d | [5 empty] | 1262570 |  | 83.15% |  | 1257250 | 1292969.5385
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 272d | 146749.1409 | 0 | 0 | 25350.8591 | 0 | 172100 | 0 | 100% | Finished | 157000 | 157000
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 56d | [5 empty] | 55350 |  | 100% |  | 60000 | 60000
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 100% | Finished | 15000 | 15000
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 56d | 120000 | 0 | 0 | -79000 | 0 | 41000 | 0 | 100% | Finished | 45000 | 45000
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 129d | 49549.6689 | 0 | 0 | 2450.3311 | 0 | 52000 | 0 | 100% | Finished | 58000 | 58000
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 129d | 18192.3077 | 0 | 0 | 5307.6923 | 0 | 23500 | 0 | 100% | Finished | 22000 | 22000
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 2017-08-04 | 143d | 67222.2222 | 0 | 0 | -16722.2222 | 0 | 50500 | 0 | 100% | Finished | 55000 | 55000
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 2017-08-04 | 191d | 31311.4754 | 0 | 0 | -10311.4754 | 0 | 21000 | 0 | 100% | Finished | 20000 | 20000
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 2017-08-04 | 191d | 155144.4043 | 63357.4007 | 78d | 15255.5957 | 0 | 170400 | 63357.4007 | 71% | Started | 159750 | 159205.7762
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 | 2017-10-23 | 87d | 6960 | 0 | 0 | 2240 | 0 | 9200 | 0 | 100% | Finished | 8000 | 8000
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 | 2017-10-23 | 87d | 30450 | 0 | 0 | -650 | 0 | 29800 | 0 | 100% | Finished | 35000 | 35000
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 2017-08-21 | 132d | 293806.4516 | 0 | 0 | 38193.5484 | 0 | 332000 | 0 | 100% | Finished | 345000 | 345000
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 2017-08-21 | 132d | 39078.9474 | 0 | 0 | 16621.0526 | 0 | 55700 | 0 | 100% | Finished | 45000 | 45000
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 2017-08-04 | 143d | 10133.8583 | 0 | 0 | -1133.8583 | 0 | 9000 | 0 | 100% | Finished | 9000 | 9000
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 | 2017-09-25 | 155d | 65379.1469 | 65379.1469 | 155d | -13379.1469 | 0 | 52000 | 65379.1469 | 50% | Started | 44500 | 65379.1469
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 | 2017-09-25 | 155d | 73809.5238 | 0 | 0 | -31359.5238 | 0 | 42450 | 0 | 100% | Finished | 50000 | 50000
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 | 2017-09-25 | 155d | 44285.7143 | 0 | 0 | -28285.7143 | 0 | 16000 | 0 | 100% | Finished | 30000 | 30000
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 | 2017-09-21 | 157d | 48307.6923 | 48307.6923 | 157d | -22307.6923 | 0 | 26000 | 48307.6923 | 50% | Started | 20000 | 35384.6154
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 | 2017-11-06 | 125d | 156250 | 0 | 0 | -128250 | 0 | 28000 | 0 | 100% | Finished | 25000 | 25000
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 | 2018-02-20 | 49d | 19444.4444 | 0 | 0 | 13355.5556 | 0 | 32800 | 0 | 100% | Finished | 25000 | 25000
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 | 2017-11-14 | 71d | 60857.1429 | 0 | 0 | -45157.1429 | 0 | 15700 | 0 | 100% | Finished | 18000 | 18000
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP9
| TP Status Date | 2018-05-22 17:00 |  | TP Name | TP9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 407d | [5 empty] | 1352970 |  | 88.53% |  | 1338500 | 1318564.2035
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 272d | 146749.1409 | 0 | 0 | 25350.8591 | 0 | 172100 | 0 | 100% | Finished | 157000 | 157000
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 56d | [5 empty] | 55350 |  | 100% |  | 60000 | 60000
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 100% | Finished | 15000 | 15000
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 56d | 120000 | 0 | 0 | -79000 | 0 | 41000 | 0 | 100% | Finished | 45000 | 45000
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 129d | 49549.6689 | 0 | 0 | 2450.3311 | 0 | 52000 | 0 | 100% | Finished | 58000 | 58000
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 129d | 18192.3077 | 0 | 0 | 5307.6923 | 0 | 23500 | 0 | 100% | Finished | 22000 | 22000
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 2017-08-04 | 143d | 67222.2222 | 0 | 0 | -16722.2222 | 0 | 50500 | 0 | 100% | Finished | 55000 | 55000
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 2017-08-04 | 191d | 31311.4754 | 0 | 0 | -10311.4754 | 0 | 21000 | 0 | 100% | Finished | 20000 | 20000
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 2017-08-04 | 208d | 168953.0686 | 0 | 0 | 71046.9314 | 0 | 240000 | 0 | 100% | Finished | 225000 | 173014.4404
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 | 2017-10-23 | 87d | 6960 | 0 | 0 | 2240 | 0 | 9200 | 0 | 100% | Finished | 8000 | 8000
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 | 2017-10-23 | 87d | 30450 | 0 | 0 | -650 | 0 | 29800 | 0 | 100% | Finished | 35000 | 35000
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 2017-08-21 | 132d | 293806.4516 | 0 | 0 | 38193.5484 | 0 | 332000 | 0 | 100% | Finished | 345000 | 345000
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 2017-08-21 | 132d | 39078.9474 | 0 | 0 | 16621.0526 | 0 | 55700 | 0 | 100% | Finished | 45000 | 45000
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 2017-08-04 | 143d | 10133.8583 | 0 | 0 | -1133.8583 | 0 | 9000 | 0 | 100% | Finished | 9000 | 9000
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 | 2017-09-25 | 172d | 72549.763 | 72549.763 | 172d | -20549.763 | 0 | 52000 | 72549.763 | 50% | Started | 44500 | 72549.763
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 | 2017-09-25 | 155d | 73809.5238 | 0 | 0 | -31359.5238 | 0 | 42450 | 0 | 100% | Finished | 50000 | 50000
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 | 2017-09-25 | 155d | 44285.7143 | 0 | 0 | -28285.7143 | 0 | 16000 | 0 | 100% | Finished | 30000 | 30000
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 | 2017-09-21 | 174d | 53538.4615 | 5961.5385 | 19d 3h | -6738.4615 | 0 | 46800 | 5961.5385 | 90% | Started | 36000 | 40000
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 | 2017-11-06 | 125d | 156250 | 0 | 0 | -128250 | 0 | 28000 | 0 | 100% | Finished | 25000 | 25000
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 | 2018-02-20 | 49d | 19444.4444 | 0 | 0 | 13355.5556 | 0 | 32800 | 0 | 100% | Finished | 25000 | 25000
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 | 2017-11-14 | 71d | 60857.1429 | 0 | 0 | -45157.1429 | 0 | 15700 | 0 | 100% | Finished | 18000 | 18000
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 0

## TP10
| TP Status Date | 2018-09-01 17:00 |  | TP Name | TP10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 480d | [5 empty] | 1394570 |  | 90.85% |  | 1373650 | 1512000
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 272d | 146749.1409 | 0 | 0 | 25350.8591 | 0 | 172100 | 0 | 100% | Finished | 157000 | 157000
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 56d | [5 empty] | 55350 |  | 100% |  | 60000 | 60000
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 100% | Finished | 15000 | 15000
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 56d | 120000 | 0 | 0 | -79000 | 0 | 41000 | 0 | 100% | Finished | 45000 | 45000
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 129d | 49549.6689 | 0 | 0 | 2450.3311 | 0 | 52000 | 0 | 100% | Finished | 58000 | 58000
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 129d | 18192.3077 | 0 | 0 | 5307.6923 | 0 | 23500 | 0 | 100% | Finished | 22000 | 22000
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 2017-08-04 | 143d | 67222.2222 | 0 | 0 | -16722.2222 | 0 | 50500 | 0 | 100% | Finished | 55000 | 55000
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 2017-08-04 | 191d | 31311.4754 | 0 | 0 | -10311.4754 | 0 | 21000 | 0 | 100% | Finished | 20000 | 20000
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 2017-08-04 | 208d | 168953.0686 | 0 | 0 | 71046.9314 | 0 | 240000 | 0 | 100% | Finished | 225000 | 225000
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 | 2017-10-23 | 87d | 6960 | 0 | 0 | 2240 | 0 | 9200 | 0 | 100% | Finished | 8000 | 8000
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 | 2017-10-23 | 87d | 30450 | 0 | 0 | -650 | 0 | 29800 | 0 | 100% | Finished | 35000 | 35000
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 2017-08-21 | 132d | 293806.4516 | 0 | 0 | 38193.5484 | 0 | 332000 | 0 | 100% | Finished | 345000 | 345000
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 2017-08-21 | 132d | 39078.9474 | 0 | 0 | 16621.0526 | 0 | 55700 | 0 | 100% | Finished | 45000 | 45000
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 2017-08-04 | 143d | 10133.8583 | 0 | 0 | -1133.8583 | 0 | 9000 | 0 | 100% | Finished | 9000 | 9000
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 | 2017-09-25 | 245d | 103341.2322 | 18242.891 | 43d 2h | -14941.2322 | 0 | 88400 | 18242.891 | 85% | Started | 75650 | 89000
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 | 2017-09-25 | 155d | 73809.5238 | 0 | 0 | -31359.5238 | 0 | 42450 | 0 | 100% | Finished | 50000 | 50000
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 | 2017-09-25 | 155d | 44285.7143 | 0 | 0 | -28285.7143 | 0 | 16000 | 0 | 100% | Finished | 30000 | 30000
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 | 2017-09-21 | 247d | 76000 | 0 | 0 | -24000 | 0 | 52000 | 0 | 100% | Finished | 40000 | 40000
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 | 2017-11-06 | 125d | 156250 | 0 | 0 | -128250 | 0 | 28000 | 0 | 100% | Finished | 25000 | 25000
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 | 2018-02-20 | 49d | 19444.4444 | 0 | 0 | 13355.5556 | 0 | 32800 | 0 | 100% | Finished | 25000 | 25000
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 | 2017-11-14 | 71d | 60857.1429 | 0 | 0 | -45157.1429 | 0 | 15700 | 0 | 100% | Finished | 18000 | 18000
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 |  | 0 | 0 | 125000 | 10d | 0 | 0 | 0 | 125000 | 0% | Not Started | 0 | 125000

## TP11
| TP Status Date | 2018-10-01 17:00 |  | TP Name | TP11
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Production Line Change | 2016-10-31 08:00 | 2018-08-31 17:00 | 480d |  |  | 0 |  |  | 1512000 |  | 501d | [5 empty] | 1534060 |  | 100% |  | 1512000 | 1512000
1 | Design | 2016-10-31 08:00 | 2017-12-11 17:00 | 291d |  | 0 | 0 | 67.4399 | 157000 | 157000 | 2016-10-31 | 272d | 146749.1409 | 0 | 0 | 25350.8591 | 0 | 172100 | 0 | 100% | Finished | 157000 | 157000
26 | Refueling Test P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  |  | 0 |  |  | 71000 |  | 38d | [5 empty] | 69070 |  | 100% |  | 71000 | 71000
2 | Definition of 2D and 3D for prototypes for P8X | 2017-02-27 08:00 | 2017-02-27 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-02-27 | 38d | 570000 | 0 | 0 | -553600 | 0 | 16400 | 0 | 100% | Finished | 15000 | 15000
3 | Prototype components assembly &amp; refueling test for P8X | 2017-02-27 08:00 | 2017-03-27 17:00 | 21d |  | 0 | 0 | 333.3333 | 56000 | 56000 | 2017-02-27 | 38d | 101333.3333 | 0 | 0 | -48663.3333 | 0 | 52670 | 0 | 100% | Finished | 56000 | 56000
27 | Refueling Test P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  |  | 0 |  |  | 60000 |  | 56d | [5 empty] | 55350 |  | 100% |  | 60000 | 60000
4 | Definition of 2D and 3D for prototypes for P1UO | 2017-07-06 08:00 | 2017-07-06 17:00 | 1d |  | 0 | 0 | 1875 | 15000 | 15000 | 2017-07-06 | 22d | 330000 | 0 | 0 | -315650 | 0 | 14350 | 0 | 100% | Finished | 15000 | 15000
5 | Prototype components assembly &amp; refueling test for P1UO | 2017-07-06 08:00 | 2017-08-03 17:00 | 21d |  | 0 | 0 | 267.8571 | 45000 | 45000 | 2017-07-06 | 56d | 120000 | 0 | 0 | -79000 | 0 | 41000 | 0 | 100% | Finished | 45000 | 45000
6 | Produce Filler Pipe Blow molds P8x | 2017-03-27 08:00 | 2017-10-23 17:00 | 151d |  | 0 | 0 | 48.0132 | 58000 | 58000 | 2017-03-27 | 129d | 49549.6689 | 0 | 0 | 2450.3311 | 0 | 52000 | 0 | 100% | Finished | 58000 | 58000
7 | Produce Filler Pipe Calibrations P8x | 2017-03-27 08:00 | 2017-10-30 17:00 | 156d |  | 0 | 0 | 17.6282 | 22000 | 22000 | 2017-03-27 | 129d | 18192.3077 | 0 | 0 | 5307.6923 | 0 | 23500 | 0 | 100% | Finished | 22000 | 22000
8 | Produce Filler Pipe Blow mold P1UO | 2017-08-03 08:00 | 2018-01-12 17:00 | 117d |  | 0 | 0 | 58.7607 | 55000 | 55000 | 2017-08-04 | 143d | 67222.2222 | 0 | 0 | -16722.2222 | 0 | 50500 | 0 | 100% | Finished | 55000 | 55000
9 | Produce Filler Pipe Calibration P1UO | 2017-08-03 08:00 | 2018-01-19 17:00 | 122d |  | 0 | 0 | 20.4918 | 20000 | 20000 | 2017-08-04 | 191d | 31311.4754 | 0 | 0 | -10311.4754 | 0 | 21000 | 0 | 100% | Finished | 20000 | 20000
10 | Filler pipe Welding/assembly machine Liberec | 2017-07-28 08:00 | 2018-08-20 17:00 | 277d |  | 0 | 0 | 101.5343 | 225000 | 225000 | 2017-08-04 | 208d | 168953.0686 | 0 | 0 | 71046.9314 | 0 | 240000 | 0 | 100% | Finished | 225000 | 225000
11 | Modification Welding lines Lokeren ‚6D | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 10 | 8000 | 8000 | 2017-10-23 | 87d | 6960 | 0 | 0 | 2240 | 0 | 9200 | 0 | 100% | Finished | 8000 | 8000
12 | Modification ROV web assembly station Lokeren ‚6D (FETE 51) | 2017-10-23 08:00 | 2018-03-09 17:00 | 100d |  | 0 | 0 | 43.75 | 35000 | 35000 | 2017-10-23 | 87d | 30450 | 0 | 0 | -650 | 0 | 29800 | 0 | 100% | Finished | 35000 | 35000
13 | Mariage welder Rennes | 2017-08-21 08:00 | 2018-03-23 17:00 | 155d |  | 0 | 0 | 278.2258 | 345000 | 345000 | 2017-08-21 | 132d | 293806.4516 | 0 | 0 | 38193.5484 | 0 | 332000 | 0 | 100% | Finished | 345000 | 345000
14 | Modification assembly line Rennes | 2017-08-21 08:00 | 2018-03-20 17:00 | 152d |  | 0 | 0 | 37.0066 | 45000 | 45000 | 2017-08-21 | 132d | 39078.9474 | 0 | 0 | 16621.0526 | 0 | 55700 | 0 | 100% | Finished | 45000 | 45000
15 | Modification Leak Tester Rennes | 2017-09-25 08:00 | 2018-03-20 17:00 | 127d |  | 0 | 0 | 8.8583 | 9000 | 9000 | 2017-08-04 | 143d | 10133.8583 | 0 | 0 | -1133.8583 | 0 | 9000 | 0 | 100% | Finished | 9000 | 9000
16 | Mariage welder Sochaux ‚6D | 2017-09-25 08:00 | 2018-07-16 17:00 | 211d |  | 0 | 0 | 52.7251 | 89000 | 89000 | 2017-09-25 | 266d | 112199.0521 | 0 | 0 | -8199.0521 | 0 | 104000 | 0 | 100% | Finished | 89000 | 89000
17 | Modification assembly line Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 59.5238 | 50000 | 50000 | 2017-09-25 | 155d | 73809.5238 | 0 | 0 | -31359.5238 | 0 | 42450 | 0 | 100% | Finished | 50000 | 50000
18 | Modification Leak Tester Sochaux ‚6D | 2017-09-25 08:00 | 2018-02-16 17:00 | 105d |  | 0 | 0 | 35.7143 | 30000 | 30000 | 2017-09-25 | 155d | 44285.7143 | 0 | 0 | -28285.7143 | 0 | 16000 | 0 | 100% | Finished | 30000 | 30000
19 | Modification Sequencer and conveyors Sochaux ‚6D | 2017-11-20 08:00 | 2018-05-18 17:00 | 130d |  | 0 | 0 | 38.4615 | 40000 | 40000 | 2017-09-21 | 247d | 76000 | 0 | 0 | -24000 | 0 | 52000 | 0 | 100% | Finished | 40000 | 40000
20 | Production for VRS P8x | 2017-11-06 08:00 | 2017-12-01 17:00 | 20d |  | 0 | 0 | 156.25 | 25000 | 25000 | 2017-11-06 | 125d | 156250 | 0 | 0 | -128250 | 0 | 28000 | 0 | 100% | Finished | 25000 | 25000
21 | Production for VRS P1UO | 2018-01-19 08:00 | 2018-04-17 17:00 | 63d |  | 0 | 0 | 49.6032 | 25000 | 25000 | 2018-02-20 | 49d | 19444.4444 | 0 | 0 | 13355.5556 | 0 | 32800 | 0 | 100% | Finished | 25000 | 25000
22 | Production for homologation P8x | 2017-12-01 08:00 | 2017-12-29 17:00 | 21d |  | 0 | 0 | 107.1429 | 18000 | 18000 | 2017-11-14 | 71d | 60857.1429 | 0 | 0 | -45157.1429 | 0 | 15700 | 0 | 100% | Finished | 18000 | 18000
23 | Finalization of all test runs, design systems and go life | 2018-08-20 08:00 | 2018-08-31 17:00 | 10d |  | 0 | 0 | 1562.5 | 125000 | 125000 | 2018-09-01 | 21d | 262500 | 0 | 0 | -138610 | 0 | 123890 | 0 | 100% | Finished | 125000 | 125000

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | SPI | p-factor
TP1 | 2016-10-31 08:00 | 2016-11-20 17:00 | 8092.7835 | 6492.4812 | 7116.9173 | 2016-11-15 17:00 | -1600.3023 | 80.23% | -624.4361 | 91.23% | -3d | 80% | 100% | 2018-09-03 12:00 | 2019-02-14 11:00 | 2019-05-06 16:00 | 2018-09-05 17:00 | 2019-02-14 11:00 | 2019-05-03 11:00 | 2018-09-05 17:00 | 2019-02-15 17:00 | 2019-05-07 10:00 | 1512624.4361 | 1657421.6561 | 1883710.1694 | 1889001.3158 | 2064197.8007 | 2069997.8407 | 1698205.5535 | 1699062.926 | 0.8 | 0.80226 | 1
TP2 | 2016-11-20 17:00 | 2017-01-10 17:00 | 28054.9828 | 15700 | 17210 | 2016-12-08 17:00 | -12354.9828 | 55.96% | -1510 | 91.23% | -23d | 55.77% | 100% | 2018-09-06 16:00 | 2020-02-12 15:00 | 2020-06-08 10:00 | 2018-10-03 16:00 | 2020-02-12 15:00 | 2020-06-01 10:00 | 2018-10-03 17:00 | 2020-02-17 15:00 | 2020-06-04 12:00 | 1513510 | 1657421.6561 | 2691010.6873 | 2700230.6897 | 2948172.4094 | 2958279.1764 | 1794855.6101 | 1795668.2476 | 0.55769 | 0.55962 | 1
TP3 | 2017-01-10 17:00 | 2017-04-19 17:00 | 146813.1936 | 118037.415 | 119086.966 | 2017-03-22 15:00 | -28775.7786 | 80.4% | -1049.551 | 99.12% | -20d 2h | 83.54% | 82.26% | 2018-09-14 09:00 | 2019-02-12 17:00 | 2019-02-20 11:00 | 2018-10-05 09:00 | 2019-02-12 17:00 | 2019-02-19 10:00 | 2018-10-01 10:00 | 2019-01-11 14:00 | 2019-01-17 14:00 | 1513049.551 | 1525444.2214 | 1852877.0433 | 1787772.1043 | 1868293.3513 | 1802609.5199 | 1580648.5078 | 1571097.2664 | 0.83537 | 0.804 | 0.82257
TP4 | 2017-04-19 17:00 | 2017-08-04 17:00 | 294932.9682 | 233457.6406 | 236467.0693 | 2017-07-11 17:00 | -61475.3276 | 79.16% | -3009.4287 | 98.73% | -18d | 91% | 90.28% | 2018-09-28 12:00 | 2019-02-26 11:00 | 2019-03-08 10:00 | 2018-10-30 15:00 | 2019-02-26 11:00 | 2019-03-05 14:00 | 2018-09-26 17:00 | 2018-11-07 12:00 | 2018-11-13 15:00 | 1515009.4287 | 1531490.7142 | 1851682.1125 | 1641458.673 | 1872503.3392 | 1659569.9758 | 1584954.0514 | 1552085.264 | 0.91 | 0.79156 | 0.90279
TP5 | 2017-08-04 17:00 | 2017-09-21 17:00 | 440829.7082 | 516610 | 516473 | 2017-10-10 11:00 | 75780.2918 | 117.2% | 137 | 100% | 12d 3h | 105.3% | 87.15% | 2018-07-30 17:00 | 2018-05-25 14:00 | 2018-05-25 12:00 | 2018-07-06 15:00 | 2018-05-25 14:00 | 2018-05-25 12:00 | 2018-08-15 14:00 | 2018-07-30 16:00 | 2018-07-30 16:00 | 1511863 | 1511599.0322 | 1365851.6092 | 1461866.242 | 1365626.3621 | 1461615.5328 | 1478580.8383 | 1501238.2382 | 1.0529 | 1.1719 | 0.87151
TP6 | 2017-09-21 17:00 | 2017-11-14 17:00 | 686858.4356 | 788950 | 790691.5 | 2017-12-04 10:00 | 102091.5644 | 114.9% | -1741.5 | 99.78% | 13d 2h | 104.9% | 93.8% | 2018-07-18 14:00 | 2018-06-06 16:00 | 2018-06-07 15:00 | 2018-07-06 14:00 | 2018-06-06 16:00 | 2018-06-07 10:00 | 2018-08-14 15:00 | 2018-08-01 15:00 | 2018-08-02 09:00 | 1513741.5 | 1515337.5347 | 1420177.5154 | 1480155.479 | 1421567.0203 | 1481677.3771 | 1494071.4084 | 1508016.7815 | 1.0487 | 1.1486 | 0.93801
TP7 | 2017-11-14 17:00 | 2018-02-20 17:00 | 1138969.7528 | 1126430 | 1129790 | 2018-02-16 12:00 | -12539.7528 | 98.9% | -3360 | 99.7% | -2d 4h | 99.27% | 91.76% | 2018-09-06 17:00 | 2018-09-10 11:00 | 2018-09-11 15:00 | 2018-09-06 15:00 | 2018-09-10 11:00 | 2018-09-10 15:00 | 2018-09-05 12:00 | 2018-09-06 12:00 | 2018-09-06 17:00 | 1515360 | 1516510.1072 | 1519652.2796 | 1518199.2489 | 1520815.1901 | 1519357.8252 | 1517134.4831 | 1516846.7591 | 0.99269 | 0.98899 | 0.91764
TP8 | 2018-02-20 17:00 | 2018-04-28 17:00 | 1292969.5385 | 1257250 | 1262570 | 2018-03-30 16:00 | -35719.5385 | 97.24% | -5320 | 99.58% | -20d 1h | 94.84% | 98.28% | 2018-09-18 11:00 | 2018-09-20 14:00 | 2018-09-24 15:00 | 2018-09-17 15:00 | 2018-09-20 14:00 | 2018-09-21 09:00 | 2018-10-01 09:00 | 2018-10-09 09:00 | 2018-10-09 14:00 | 1517320 | 1518397.9638 | 1524557.6635 | 1531181.0172 | 1525666.2532 | 1532317.6334 | 1519606.6226 | 1520856.305 | 0.9484 | 0.97237 | 0.98283
TP9 | 2018-04-28 17:00 | 2018-05-22 17:00 | 1318564.2035 | 1338500 | 1352970 | 2018-06-14 10:00 | 19935.7965 | 101.5% | -14470 | 98.93% | 16d 2h | 104% | 97.09% | 2018-08-23 14:00 | 2018-08-22 16:00 | 2018-08-29 17:00 | 2018-08-23 16:00 | 2018-08-22 16:00 | 2018-08-23 14:00 | 2018-08-09 15:00 | 2018-08-07 14:00 | 2018-08-08 09:00 | 1526470 | 1528345.6406 | 1523885.868 | 1519808.7478 | 1525733.5726 | 1521612.3762 | 1527435.1635 | 1526569.0788 | 1.0399 | 1.0151 | 0.97094
TP10 | 2018-05-22 17:00 | 2018-09-01 17:00 | 1512000 | 1373650 | 1394570 | 2018-07-27 12:00 | -138350 | 90.85% | -20920 | 98.5% | -25d 4h | 94.69% | 99.03% | 2018-11-01 16:00 | 2018-11-08 11:00 | 2018-11-20 11:00 | 2018-11-01 16:00 | 2018-11-08 11:00 | 2018-11-09 09:00 | 2018-10-08 12:00 | 2018-10-09 16:00 | 2018-10-10 11:00 | 1532920 | 1535027.0011 | 1546854.2063 | 1540682.2112 | 1549173.4183 | 1542907.4269 | 1537243.153 | 1536122.7487 | 0.94688 | 0.9085 | 0.99028
TP11 | 2018-09-01 17:00 | 2018-10-01 17:00 | 1512000 | 1512000 | 1534060 | 2018-08-31 17:00 | 0 | 100% | -22060 | 98.56% | -21d | 95.81% | 100% | 2018-08-31 17:00 | 2018-08-31 17:00 | 2018-09-11 17:00 | 2018-10-01 17:00 | 2018-10-01 17:00 | 2018-10-01 17:00 | 2018-10-01 17:00 | 2018-10-01 17:00 | 2018-10-01 17:00 | 1534060 | 1534060 | 1534060 | 1534060 | 1534060 | 1534060 | 1534060 | 1534060 | 0.95808 | 1 | 1

## Corrective actions Overview
General |  |  | Corrective actions
Name | Start Tracking Period | Status date | Category | Description
TP1 | 2016-10-31 08:00 | 2016-11-20 17:00 | - | -
TP2 | 2016-11-20 17:00 | 2017-01-10 17:00 | C5 | Involve higher management
TP3 | 2017-01-10 17:00 | 2017-04-19 17:00 | - | -
TP4 | 2017-04-19 17:00 | 2017-08-04 17:00 | C2 | Status update call subcontractor
TP5 | 2017-08-04 17:00 | 2017-09-21 17:00 | - | -
TP6 | 2017-09-21 17:00 | 2017-11-14 17:00 | - | -
TP7 | 2017-11-14 17:00 | 2018-02-20 17:00 | - | -
TP8 | 2018-02-20 17:00 | 2018-04-28 17:00 | C6 | Overtime work
TP9 | 2018-04-28 17:00 | 2018-05-22 17:00 | - | -
TP10 | 2018-05-22 17:00 | 2018-09-01 17:00 | - | -
TP11 | 2018-09-01 17:00 | 2018-10-01 17:00 | - | -