## Hoja1
ID | Name | WBS | Predecessors | Successors | Total Cost | Duration | Description | Optimistic | Most Probable | Pessimistic | d | o | m | p | Actual Duration | PAC | PRC | Remaining Duration | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV) | ad
1 | START | 1.1 |  | FS2 | 0 | 0 | standard - no risk | 99 | 100 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | Finished | 0 | 0 | 0
2 | Creation of the activities plan and location | 1.2 | 1FS | FS3 | 4000 | 40h | standard - skewed left | 80 | 110 | 120 | 40 | 32 | 44 | 48 | 7d 3h | 5900 | 0 | 0 | 5900 | 0 | 1 | Finished | 4000 | 4000 | 59
3 | Asking City Hall Permission / License - email | 1.3 | 2FS | FS4 | 200 | 240h | standard - skewed left | 80 | 110 | 120 | 240 | 192 | 264 | 288 | 42d 3h | 200 | 0 | 0 | 200 | 0 | 1 | Finished | 200 | 200 | 339
4 | Receiving acceptance | 1.4 | 3FS | FS5;FS6;FS7;FS8;FS21 | 200 | 10h | standard - skewed left | 80 | 110 | 120 | 10 | 8 | 11 | 12 | 1d 4h | 200 | 0 | 0 | 200 | 0 | 1 | Finished | 200 | 200 | 12
5 | Creation of a safety plan | 1.5 | 4FS | FS9 | 640 | 16h | standard - skewed left | 80 | 110 | 120 | 16 | 12.8 | 17.6 | 19.2 | 2d 6h | 880 | 0 | 0 | 880 | 0 | 1 | Finished | 640 | 640 | 22
6 | Contacting vegan restaurants and sponsors | 1.6 | 4FS | SS10;FS27;FS13 | 4800 | 240h | standard - skewed left | 80 | 110 | 120 | 240 | 192 | 264 | 288 | 8d 6h | 1400 | 3440 | 21d 4h | 1400 | 3440 | 0.28926 | Started | 1388.4297 | 3800 | 70 | 0.28926
7 | Contacting the truck/stand company | 1.7 | 4FS | FS14 | 2240 | 112h | standard - skewed left | 80 | 110 | 120 | 112 | 89.6 | 123.2 | 134.4 | 8d 6h | 1400 | 2780 | 17d 3h | 1400 | 2780 | 0.33493 | Started | 750.2393 | 2240 | 70
8 | Contacting / contract Music band/ DJ | 1.8 | 4FS | FS14 | 2240 | 112h | standard - skewed left | 80 | 110 | 120 | 112 | 89.6 | 123.2 | 134.4 | 8d 6h | 1400 | 2400 | 15d | 1400 | 2400 | 0.36842 | Started | 825.2631 | 2240 | 70
9 | Approval of the security plan and coordination with the police | 1.9 | 5FS | FS14;FS24 | 200 | 160h | standard - skewed left | 80 | 110 | 120 | 160 | 128 | 176 | 192 | 6d | 200 | 0 | 25d 1h | 200 | 0 | 0.19277 | Started | 200 | 200 | 48
10 | Design the Marketing Campaign | 1.10 | 6SS | FS11;FS12 | 3360 | 56h | standard - skewed left | 80 | 110 | 120 | 56 | 44.8 | 61.6 | 67.2 | 8d 6h | 4200 | 1920 | 4d | 4200 | 1920 | 0.68627 | Started | 2305.8824 | 3360 | 70
11 | Ordering posters and flyers | 1.11 | 10FS | FS13 | 1200 | 10h | standard - skewed left | 80 | 110 | 120 | 10 | 8 | 11 | 12 | 0 | 0 | 1200 | 1d 2h | 0 | 1200 | 0 | Not Started | 0 | 1200 | 0
12 | Preparing online campaign | 1.12 | 10FS | FS13 | 800 | 40h | standard - skewed left | 80 | 110 | 120 | 40 | 32 | 44 | 48 | 0 | 0 | 800 | 5d | 0 | 800 | 0 | Not Started | 0 | 800 | 0
13 | Start Marketing campaign | 1.13 | 11FS;12FS;6FS | FS27 | 500 | 240h | standard - skewed left | 80 | 110 | 120 | 240 | 192 | 264 | 288 | 0 | 0 | 500 | 30d | 0 | 500 | 0 | Not Started | 0 | 0 | 0
14 | Cut the Circulation | 1.14 | 7FS;8FS;9FS | FS15 | 200 | 10h | standard - skewed left | 80 | 110 | 120 | 10 | 8 | 11 | 12 | 0 | 0 | 200 | 1d 2h | 0 | 200 | 0 | Not Started | 0 | 200 | 0
15 | Installing the tent | 1.15 | 14FS;24FS | FS16;FS18;FS17;FS19;FS20 | 320 | 16h | standard - skewed left | 80 | 110 | 120 | 16 | 12.8 | 17.6 | 19.2 | 0 | 0 | 320 | 2d | 0 | 320 | 0 | Not Started | 0 | 0 | 0
16 | Installation of electricity/cabling | 1.16 | 15FS | FS22 | 1000 | 24h | standard - skewed left | 80 | 110 | 120 | 24 | 19.2 | 26.4 | 28.8 | 0 | 0 | 1000 | 3d | 0 | 1000 | 0 | Not Started | 0 | 0 | 0
17 | Stands Construction | 1.17 | 15FS | FS22 | 1000 | 16h | standard - skewed left | 80 | 110 | 120 | 16 | 12.8 | 17.6 | 19.2 | 0 | 0 | 1000 | 2d | 0 | 1000 | 0 | Not Started | 0 | 0 | 0
18 | Backstage Construction | 1.18 | 15FS | FS22 | 1000 | 16h | standard - skewed left | 80 | 110 | 120 | 16 | 12.8 | 17.6 | 19.2 | 0 | 0 | 1000 | 2d | 0 | 1000 | 0 | Not Started | 0 | 0 | 0
19 | Bathrooms construction/installation | 1.19 | 15FS | FS22 | 500 | 8h | standard - skewed left | 80 | 110 | 120 | 8 | 6.4 | 8.8 | 9.6 | 0 | 0 | 500 | 1d | 0 | 500 | 0 | Not Started | 0 | 0 | 0
20 | Tables installation | 1.20 | 15FS | FS22 | 500 | 8h | standard - skewed left | 80 | 110 | 120 | 8 | 6.4 | 8.8 | 9.6 | 0 | 0 | 500 | 1d | 0 | 500 | 0 | Not Started | 0 | 0 | 0
21 | Designing and Budgeting Christmas decoration | 1.21 | 4FS | FS22 | 4800 | 48h | standard - skewed left | 80 | 110 | 120 | 48 | 38.4 | 52.8 | 57.6 | 8d 6h | 7000 | 800 | 1d | 7000 | 800 | 0.89744 | Started | 4307.6923 | 4800 | 70
22 | Installation of the decoration | 1.22 | 21FS;20FS;19FS;18FS;17FS;16FS | FS23 | 640 | 16h | standard - skewed left | 80 | 110 | 120 | 16 | 12.8 | 17.6 | 19.2 | 0 | 0 | 640 | 2d | 0 | 640 | 0 | Not Started | 0 | 0 | 0
23 | Open circulation | 1.23 | 22FS | FS25 | 200 | 8h | standard - skewed left | 80 | 110 | 120 | 8 | 6.4 | 8.8 | 9.6 | 0 | 0 | 200 | 1d | 0 | 200 | 0 | Not Started | 0 | 0 | 0
24 | Hiring security guards | 1.24 | 9FS | FS15 | 1120 | 56h | standard - skewed left | 80 | 110 | 120 | 56 | 44.8 | 61.6 | 67.2 | 0 | 0 | 1120 | 7d | 0 | 1120 | 0 | Not Started | 0 | 280 | 0
25 | Technical Control | 1.25 | 23FS | FS26 | 1000 | 8h | standard - skewed left | 80 | 110 | 120 | 8 | 6.4 | 8.8 | 9.6 | 0 | 0 | 1000 | 1d | 0 | 1000 | 0 | Not Started | 0 | 0 | 0
26 | Placement of people and food | 1.26 | 25FS | FS27 | 640 | 16h | standard - skewed left | 80 | 110 | 120 | 16 | 12.8 | 17.6 | 19.2 | 0 | 0 | 640 | 2d | 0 | 640 | 0 | Not Started | 0 | 0 | 0
27 | Market opening | 1.27 | 13FS;26FS;6FS | FS28 | 24000 | 240h | standard - no risk | 99 | 100 | 101 | 240 | 237.6 | 240 | 242.4 | 0 | 0 | 24000 | 30d | 0 | 24000 | 0 | Not Started | 0 | 0 | 0
28 | Market closing | 1.28 | 27FS | FS29 | 200 | 10h | standard - no risk | 99 | 100 | 101 | 10 | 9.9 | 10 | 10.1 | 0 | 0 | 200 | 1d 2h | 0 | 200 | 0 | Not Started | 0 | 0 | 0
29 | Cut circulation | 1.29 | 28FS | FS30;FS31 | 200 | 10h | standard - skewed left | 80 | 110 | 120 | 10 | 8 | 11 | 12 | 0 | 0 | 200 | 1d 2h | 0 | 200 | 0 | Not Started | 0 | 0 | 0
30 | Cleaning | 1.30 | 29FS | FS32 | 1000 | 10h | standard - skewed left | 80 | 110 | 120 | 10 | 8 | 11 | 12 | 0 | 0 | 1000 | 1d 2h | 0 | 1000 | 0 | Not Started | 0 | 0 | 0
31 | Uninstallation | 1.31 | 29FS | FS32 | 0 | 16h | standard - skewed left | 80 | 110 | 120 | 16 | 12.8 | 17.6 | 19.2 | 0 | 0 | 0 | 2d | 0 | 0 | 0 | Not Started | 0 | 0 | 0
32 | Opening circulation | 1.32 | 30FS;31FS | FS33 | 200 | 8h | standard - skewed left | 80 | 110 | 120 | 8 | 6.4 | 8.8 | 9.6 | 0 | 0 | 200 | 1d | 0 | 200 | 0 | Not Started | 0 | 0 | 0
33 | END | 1.33 | 32FS |  | 0 | 0 | standard - no risk | 99 | 100 | 101 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Not Started | 0 | 0 | 0