## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | PROJECT Nuclear Healthcare | 1 |  |  | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 | 520.375
1 | Fase 1 Voorontwerp | 1.1 |  | FS2 | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 23.375
2 | Fase 2 opmaak ontwerp &amp; studie | 1.2 | 1FS | FS3;FS4 | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 28.375
3 | schriftelijke goedkeuring opstarten aanbesteding | 1.3 | 2FS | FS7 | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 70.375
4 | Fase 3 opmaak bouwvergunningsdossier | 1.4 | 2FS | FS5 | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 27.375
5 | indienen bouwvergunning en wachten op goedkeuring | 1.5 | 4FS | FS6 | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 77.375
6 | opstellen lastencohier | 1.6 | 5FS | FS7 | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 33.375
7 | opmaak dossier | 1.7 | 3FS;6FS | FS8 | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 6.375
8 | goedkeuring dossier | 1.8 | 7FS | FS9 | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
9 | publicatie | 1.9 | 8FS | FS10 | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 0.375
10 | indieningstermijn | 1.10 | 9FS | FS11 | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 20.375
11 | opening | 1.11 | 10FS | FS12 | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
12 | Fase 4 onderzoek offertes | 1.12 | 11FS | FS13 | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 13.375
13 | opmaak verslag | 1.13 | 12FS | FS14 | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 6.375
14 | goedkeuring RC | 1.14 | 13FS | FS15 | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 6.375
15 | indienen RvB | 1.15 | 14FS | FS16 | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
16 | goedkeuring RvB | 1.16 | 15FS | FS17 | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
17 | standstill | 1.17 | 16FS | FS18 | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 13.375
18 | bestelling | 1.18 | 17FS | FS19;FS20 | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 6.375
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 1.19 |  |  | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 | 18.375
19 | voorafgaand leegmaken locatie + afbraakwerken | 1.19.1 | 18FS | FS21 | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 18.375
39 | Fase 0 : SPECT/CT 3 | 1.20 |  |  | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 | 81.375
20 | inrichtingswerken | 1.20.1 | 18FS | FS21 | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 74.375
21 | opkuis en reserve | 1.20.2 | 19FS;20FS | FS22 | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 4.375
22 | ingebruikname | 1.20.3 | 21FS | FS23;FS24 | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
40 | FASE 1: inrichtingswerken afdeling | 1.21 |  |  | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 | 56.375
23 | uitvoering fase 1 (0P8) | 1.21.1 | 22FS | FS25 | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 42.375
24 | levering en plaatsing PET/CT 2 | 1.21.2 | 22FS | FS25 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 | 13.375
25 | opkuis en reserve | 1.21.3 | 23FS;24FS | FS26 | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 11.375
26 | ingebruikname | 1.21.4 | 25FS | FS27;FS29 | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
41 | FASE 2 : inrichting technische ruimte -1P8 | 1.22 |  |  | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 | 136.375
27 | installatie PETC/CT 1 op 0P8 | 1.22.1 | 26FS | FS28 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 | 17.375
28 | indienststelling PET/CT 1 | 1.22.2 | 27FS | FS30;FS31 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
29 | uitbraakwerken | 1.22.3 | 26FS | FS30;FS31 | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 | 14.375
30 | uitvoering fase 2 ) | 1.22.4 | 28FS;29FS | FS32 | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 | 105.375
31 | aanpassingswerken, regeling en testen 0P8 | 1.22.5 | 28FS;29FS | FS32 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 | 10.375
32 | opkuis en reserve | 1.22.6 | 30FS;31FS | FS33 | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 | 14.375
33 | oplevering | 1.22.7 | 32FS |  | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT Nuclear Healthcare | 2984h
1 | Fase 1 Voorontwerp | 144h | standard - no risk | 99 | 100 | 101
2 | Fase 2 opmaak ontwerp &amp; studie | 168h | standard - no risk | 99 | 100 | 101
3 | schriftelijke goedkeuring opstarten aanbesteding | 408h | standard - no risk | 99 | 100 | 101
4 | Fase 3 opmaak bouwvergunningsdossier | 160h | standard - no risk | 99 | 100 | 101
5 | indienen bouwvergunning en wachten op goedkeuring | 448h | standard - no risk | 99 | 100 | 101
6 | opstellen lastencohier | 192h | standard - no risk | 99 | 100 | 101
7 | opmaak dossier | 40h | standard - no risk | 99 | 100 | 101
8 | goedkeuring dossier | 8h | standard - no risk | 99 | 100 | 101
9 | publicatie | 8h | standard - no risk | 99 | 100 | 101
10 | indieningstermijn | 120h | standard - no risk | 99 | 100 | 101
11 | opening | 8h | standard - no risk | 99 | 100 | 101
12 | Fase 4 onderzoek offertes | 80h | standard - no risk | 99 | 100 | 101
13 | opmaak verslag | 40h | standard - no risk | 99 | 100 | 101
14 | goedkeuring RC | 40h | standard - no risk | 99 | 100 | 101
15 | indienen RvB | 8h | standard - no risk | 99 | 100 | 101
16 | goedkeuring RvB | 8h | standard - no risk | 99 | 100 | 101
17 | standstill | 80h | standard - no risk | 99 | 100 | 101
18 | bestelling | 40h | standard - no risk | 99 | 100 | 101
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 120h
19 | voorafgaand leegmaken locatie + afbraakwerken | 120h | standard - no risk | 99 | 100 | 101
39 | Fase 0 : SPECT/CT 3 | 480h
20 | inrichtingswerken | 440h | standard - no risk | 99 | 100 | 101
21 | opkuis en reserve | 40h | standard - no risk | 99 | 100 | 101
22 | ingebruikname | 8h | standard - no risk | 99 | 100 | 101
40 | FASE 1: inrichtingswerken afdeling | 328h
23 | uitvoering fase 1 (0P8) | 248h | standard - no risk | 99 | 100 | 101
24 | levering en plaatsing PET/CT 2 | 80h | standard - no risk | 99 | 100 | 101
25 | opkuis en reserve | 64h | standard - no risk | 99 | 100 | 101
26 | ingebruikname | 8h | standard - no risk | 99 | 100 | 101
41 | FASE 2 : inrichting technische ruimte -1P8 | 792h
27 | installatie PETC/CT 1 op 0P8 | 112h | standard - no risk | 99 | 100 | 101
28 | indienststelling PET/CT 1 | 8h | standard - no risk | 99 | 100 | 101
29 | uitbraakwerken | 88h | standard - no risk | 99 | 100 | 101
30 | uitvoering fase 2 ) | 608h | standard - no risk | 99 | 100 | 101
31 | aanpassingswerken, regeling en testen 0P8 | 72h | standard - no risk | 99 | 100 | 101
32 | opkuis en reserve | 88h | standard - no risk | 99 | 100 | 101
33 | oplevering | 8h | standard - no risk | 99 | 100 | 101

## Project Control - TP1
| TP Status Date | 2016-02-01 17:00 |  | TP Name | TP1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 19d | [5 empty] | 124492.5 |  | 3.984% |  | 172050 | 36335.7143
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 19d | 271428.5714 | 271428.5714 | 19d | -168986.0714 | 0 | 102442.5 | 271428.5714 | 50% | Started | 150000 | 14285.7143
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 51d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 |  | 0 | 0 | 6400 | 20d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 56d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 |  | 0 | 0 | 12000 | 24d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 |  | 0 | 0 | 30700 | 5d | 0 | 0 | 0 | 30700 | 0% | Not Started | 0 | 0
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 1d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 15d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 |  | 0 | 0 | 3200 | 10d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 |  | 0 | 0 | 1600 | 5d | 0 | 0 | 0 | 1600 | 0% | Not Started | 0 | 0
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 0
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 0
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 |  | 0 | 0 | 193000 | 55d | 0 | 0 | 0 | 193000 | 0% | Not Started | 0 | 0
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 |  | 0 | 0 | 2000 | 5d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 |  | 0 | 0 | 2000 | 8d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2016-03-01 17:00 |  | TP Name | TP2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 40d | [5 empty] | 226935 |  | 7.457% |  | 322050 | 322050
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 |  | 0 | 0 | 6400 | 20d | 0 | 0 | 0 | 6400 | 0% | Not Started | 0 | 0
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 22d | 0 | 0 | 0 | 0 | 50% | Started | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 |  | 0 | 0 | 12000 | 24d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 |  | 0 | 0 | 30700 | 5d | 0 | 0 | 0 | 30700 | 0% | Not Started | 0 | 0
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 1d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 15d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 |  | 0 | 0 | 3200 | 10d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 |  | 0 | 0 | 1600 | 5d | 0 | 0 | 0 | 1600 | 0% | Not Started | 0 | 0
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 0
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 0
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 |  | 0 | 0 | 193000 | 55d | 0 | 0 | 0 | 193000 | 0% | Not Started | 0 | 0
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 |  | 0 | 0 | 2000 | 5d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 |  | 0 | 0 | 2000 | 8d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2016-04-15 17:00 |  | TP Name | TP3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 73d | [5 empty] | 260220 |  | 8.238% |  | 355800 | 332450
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 55d | 0 | 0 | 55d | 0 | 0 | 0 | 0 | 50% | Started | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 4000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 34d | 208760 | 208760 | 34d | -192425 | 0 | 16335 | 208760 | 50% | Started | 15350 | 0
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 1d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 15d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 |  | 0 | 0 | 3200 | 10d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 |  | 0 | 0 | 1600 | 5d | 0 | 0 | 0 | 1600 | 0% | Not Started | 0 | 0
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 0
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 0
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 |  | 0 | 0 | 193000 | 55d | 0 | 0 | 0 | 193000 | 0% | Not Started | 0 | 0
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 |  | 0 | 0 | 2000 | 5d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 |  | 0 | 0 | 2000 | 8d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2016-05-01 17:00 |  | TP Name | TP4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 83d | [5 empty] | 276555 |  | 8.594% |  | 371150 | 337450
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 1d | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 50% | Started | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 9000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 0
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 11d | 0 | 0 | 11d | 0 | 0 | 0 | 0 | 50% | Started | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 |  | 0 | 0 | 2500 | 1d | 0 | 0 | 0 | 2500 | 0% | Not Started | 0 | 0
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 15d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 |  | 0 | 0 | 3200 | 10d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 |  | 0 | 0 | 1600 | 5d | 0 | 0 | 0 | 1600 | 0% | Not Started | 0 | 0
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 0
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 0
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 |  | 0 | 0 | 193000 | 55d | 0 | 0 | 0 | 193000 | 0% | Not Started | 0 | 0
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 |  | 0 | 0 | 2000 | 5d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 |  | 0 | 0 | 2000 | 8d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2016-06-02 17:00 |  | TP Name | TP5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 107d | [5 empty] | 279055 |  | 8.651% |  | 373650 | 373650
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 24d | 0 | 0 | 24d | 0 | 0 | 0 | 0 | 50% | Started | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 12d | 0 | 0 | 12d | 0 | 0 | 0 | 0 | 50% | Started | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 |  | 0 | 0 | 3200 | 10d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 0
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 |  | 0 | 0 | 1600 | 5d | 0 | 0 | 0 | 1600 | 0% | Not Started | 0 | 0
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 0
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 0
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 |  | 0 | 0 | 193000 | 55d | 0 | 0 | 0 | 193000 | 0% | Not Started | 0 | 0
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 |  | 0 | 0 | 2000 | 5d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 |  | 0 | 0 | 2000 | 8d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP6
| TP Status Date | 2016-06-30 17:00 |  | TP Name | TP6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 127d | [5 empty] | 386654.385 |  | 10.89% |  | 470150 | 378450
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 32d | 0 | 0 | 32d | 0 | 0 | 0 | 0 | 50% | Started | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 |  | 0 | 0 | 3200 | 10d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 |  | 0 | 0 | 1600 | 5d | 0 | 0 | 0 | 1600 | 0% | Not Started | 0 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 0
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 0
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 21d | [5 empty] | 107599.385 |  | 49.49% |  | 96500 | 0
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 21d | 73690.9091 | 73690.9091 | 21d | 33908.4759 | 0 | 107599.385 | 73690.9091 | 50% | Started | 96500 | 0
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 |  | 0 | 0 | 2000 | 5d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 |  | 0 | 0 | 2000 | 8d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP7
| TP Status Date | 2016-07-15 17:00 |  | TP Name | TP7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 138d | [5 empty] | 386654.385 |  | 10.89% |  | 470150 | 378450
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 |  | 0 | 0 | 3200 | 10d | 0 | 0 | 0 | 3200 | 0% | Not Started | 0 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 |  | 0 | 0 | 1600 | 5d | 0 | 0 | 0 | 1600 | 0% | Not Started | 0 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 0
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 0
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 32d | [5 empty] | 107599.385 |  | 49.49% |  | 96500 | 0
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 32d | 112290.9091 | 112290.9091 | 32d | -4691.5241 | 0 | 107599.385 | 112290.9091 | 50% | Started | 96500 | 0
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 |  | 0 | 0 | 2000 | 5d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 |  | 0 | 0 | 2000 | 8d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP8
| TP Status Date | 2016-09-07 17:00 |  | TP Name | TP8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 176d | [5 empty] | 497453.77 |  | 13.24% |  | 571850 | 635977.2727
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 |  | 0 | 0 | 1600 | 5d | 0 | 0 | 0 | 1600 | 0% | Not Started | 0 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 5d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 82000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 82000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 10527.2727
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 10527.2727
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 |  | 0 | 0 | 2000 | 8d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP9
| TP Status Date | 2016-10-06 17:00 |  | TP Name | TP9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 197d | [5 empty] | 499053.77 |  | 13.32% |  | 575450 | 1037668.1818
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 10d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 84218.1818
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 84218.1818
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 22d | [5 empty] | 0 |  | 0.1892% |  | 2000 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP10
| TP Status Date | 2016-11-07 17:00 |  | TP Name | TP10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 219d | [5 empty] | 499053.77 |  | 13.32% |  | 575450 | 1114868.1818
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 23d | 0 | 0 | 23d | 0 | 0 | 0 | 0 | 50% | Started | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 |  | 0 | 0 | 165000 | 5d | 0 | 0 | 0 | 165000 | 0% | Not Started | 0 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 |  | 0 | 0 | 410000 | 15d | 0 | 0 | 0 | 410000 | 0% | Not Started | 0 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 161418.1818
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 161418.1818
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 0
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 44d | [5 empty] | 0 |  | 0.1892% |  | 2000 | 0
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 0
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP11
| TP Status Date | 2016-12-05 17:00 |  | TP Name | TP11
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 239d | [5 empty] | 905012.64 |  | 21.89% |  | 945450 | 1350288.7097
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 21d | [5 empty] | 215198.77 |  | 50% |  | 205000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 21d | 574000 | 574000 | 21d | -358801.23 | 0 | 215198.77 | 574000 | 50% | Started | 205000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 64d | [5 empty] | 0 |  | 0.1892% |  | 2000 | 201838.7097
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 |  | 0 | 0 | 1042833.3333 | 31d | 0 | 0 | 0 | 1042833.3333 | 0% | Not Started | 0 | 201838.7097
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP12
| TP Status Date | 2017-01-01 17:00 |  | TP Name | TP12
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 258d | [5 empty] | 1632595.0767 |  | 38.71% |  | 1671866.6667 | 1991844.6237
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 83d | [5 empty] | 512383.6667 |  | 49.53% |  | 523416.6667 | 843394.6237
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 20d | 672795.6989 | 672795.6989 | 20d | -160412.0323 | 0 | 512383.6667 | 672795.6989 | 50% | Started | 521416.6667 | 840994.6237
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 2400
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 0
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 0
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 0
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP13
| TP Status Date | 2017-02-01 17:00 |  | TP Name | TP13
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 281d | [5 empty] | 1632595.0767 |  | 38.71% |  | 1671866.6667 | 2254465.1515
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 106d | [5 empty] | 512383.6667 |  | 49.53% |  | 523416.6667 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 43d | 1446510.7527 | 1446510.7527 | 43d | -934127.086 | 0 | 512383.6667 | 1446510.7527 | 50% | Started | 521416.6667 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 49181.8182
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 6000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 43181.8182
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 0
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP14
| TP Status Date | 2017-03-01 17:00 |  | TP Name | TP14
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 301d | [5 empty] | 1632595.0767 |  | 38.71% |  | 1671866.6667 | 2676958.7719
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 126d | [5 empty] | 512383.6667 |  | 49.53% |  | 523416.6667 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 63d | 2119306.4516 | 2119306.4516 | 63d | -1606922.7849 | 0 | 512383.6667 | 2119306.4516 | 50% | Started | 521416.6667 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 471675.4386
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 364675.4386
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP15
| TP Status Date | 2017-04-01 17:00 |  | TP Name | TP15
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 323d | [5 empty] | 1632595.0767 |  | 38.71% |  | 1671866.6667 | 3250020.1754
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 148d | [5 empty] | 512383.6667 |  | 49.53% |  | 523416.6667 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 85d | 2859381.7204 | 2859381.7204 | 85d | -2346998.0538 | 0 | 512383.6667 | 2859381.7204 | 50% | Started | 521416.6667 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1044736.8421
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 937736.8421
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP16
| TP Status Date | 2017-05-01 17:00 |  | TP Name | TP16
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 344d | [5 empty] | 1632595.0767 |  | 38.71% |  | 1671866.6667 | 3797033.3333
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 169d | [5 empty] | 512383.6667 |  | 49.53% |  | 523416.6667 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 103d | 3464897.8495 | 3464897.8495 | 103d | -2952514.1828 | 0 | 512383.6667 | 3464897.8495 | 50% | Started | 521416.6667 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 1591750
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 1484750
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 0
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 0
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP17
| TP Status Date | 2017-06-01 17:00 |  | TP Name | TP17
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 367d | [5 empty] | 1632595.0767 |  | 38.71% |  | 1671866.6667 | 4317859.0909
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 192d | [5 empty] | 512383.6667 |  | 49.53% |  | 523416.6667 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 129d | 4339532.2581 | 4339532.2581 | 129d | -3827148.5914 | 0 | 512383.6667 | 4339532.2581 | 50% | Started | 521416.6667 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2112575.7576
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 1979666.6667
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 25000
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 909.0909
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP18
| TP Status Date | 2017-07-01 17:00 |  | TP Name | TP18
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 388d | [5 empty] | 1632595.0767 |  | 38.71% |  | 1671866.6667 | 4318950
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 213d | [5 empty] | 512383.6667 |  | 49.53% |  | 523416.6667 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 150d | 5045967.7419 | 5045967.7419 | 150d | -4533584.0753 | 0 | 512383.6667 | 5045967.7419 | 50% | Started | 521416.6667 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2113666.6667
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 1979666.6667
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 25000
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP19
| TP Status Date | 2017-08-01 17:00 |  | TP Name | TP19
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 410d | [5 empty] | 1632595.0767 |  | 38.71% |  | 1671866.6667 | 4318950
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 235d | [5 empty] | 512383.6667 |  | 49.53% |  | 523416.6667 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 172d | 5786043.0108 | 5786043.0108 | 172d | -5273659.3441 | 0 | 512383.6667 | 5786043.0108 | 50% | Started | 521416.6667 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 |  | 0 | 0 | 12000 | 10d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2113666.6667
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 1979666.6667
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 25000
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP20
| TP Status Date | 2017-09-01 17:00 |  | TP Name | TP20
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 433d | [5 empty] | 1638935.0767 |  | 38.85% |  | 1677866.6667 | 4318950
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 258d | [5 empty] | 518723.6667 |  | 50.09% |  | 529416.6667 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 195d | 6559758.0645 | 6559758.0645 | 195d | -6047374.3978 | 0 | 512383.6667 | 6559758.0645 | 50% | Started | 521416.6667 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 | 2017-08-01 08:00 | 2d | 2400 | 2400 | 2d | 3940 | 0 | 6340 | 2400 | 50% | Started | 6000 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2113666.6667
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 1979666.6667
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 25000
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP21
| TP Status Date | 2017-10-01 17:00 |  | TP Name | TP21
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 453d | [5 empty] | 2157658.7433 |  | 51.06% |  | 2205283.3333 | 4318950
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 278d | [5 empty] | 1037447.3333 |  | 100% |  | 1056833.3333 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 215d | 7232553.7634 | 0 | 0 | -6207786.4301 | 0 | 1024767.3333 | 0 | 100% | Finished | 1042833.3333 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 | 2017-08-01 08:00 | 44d | 52800 | 0 | 0 | -40120 | 0 | 12680 | 0 | 100% | Finished | 12000 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 2113666.6667
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 |  | 0 | 0 | 12000 | 14d | 0 | 0 | 0 | 12000 | 0% | Not Started | 0 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 |  | 0 | 0 | 95000 | 11d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 |  | 0 | 0 | 1979666.6667 | 76d | 0 | 0 | 0 | 1979666.6667 | 0% | Not Started | 0 | 1979666.6667
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 25000
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP22
| TP Status Date | 2017-11-01 17:00 |  | TP Name | TP22
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 476d | [5 empty] | 3230856.0767 |  | 76.32% |  | 3296116.6667 | 4318950
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 278d | [5 empty] | 1037447.3333 |  | 100% |  | 1056833.3333 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 215d | 7232553.7634 | 0 | 0 | -6207786.4301 | 0 | 1024767.3333 | 0 | 100% | Finished | 1042833.3333 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 | 2017-08-01 08:00 | 44d | 52800 | 0 | 0 | -40120 | 0 | 12680 | 0 | 100% | Finished | 12000 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 23d | [5 empty] | 1073197.3333 |  | 51.61% |  | 1090833.3333 | 2113666.6667
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 | 2017-10-01 08:00 | 23d | 19714.2857 | 19714.2857 | 23d | -14220.7857 | 0 | 5493.5 | 19714.2857 | 50% | Started | 6000 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 | 2017-10-01 08:00 | 23d | 198636.3636 | 0 | 0 | -108636.3636 | 0 | 90000 | 0 | 100% | Finished | 95000 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 | 2017-10-01 08:00 | 23d | 599109.6491 | 599109.6491 | 23d | 378594.1842 | 0 | 977703.8333 | 599109.6491 | 50% | Started | 989833.3333 | 1979666.6667
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 25000
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP23
| TP Status Date | 2017-12-01 17:00 |  | TP Name | TP23
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 520d | [5 empty] | 3236349.5767 |  | 76.46% |  | 3302116.6667 | 4318950
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 278d | [5 empty] | 1037447.3333 |  | 100% |  | 1056833.3333 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 215d | 7232553.7634 | 0 | 0 | -6207786.4301 | 0 | 1024767.3333 | 0 | 100% | Finished | 1042833.3333 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 | 2017-08-01 08:00 | 44d | 52800 | 0 | 0 | -40120 | 0 | 12680 | 0 | 100% | Finished | 12000 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 67d | [5 empty] | 1078690.8333 |  | 51.89% |  | 1096833.3333 | 2113666.6667
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 | 2017-10-01 08:00 | 45d | 38571.4286 | 0 | 0 | -27584.4286 | 0 | 10987 | 0 | 100% | Finished | 12000 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-01 08:00 | 45d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 | 2017-10-01 08:00 | 23d | 198636.3636 | 0 | 0 | -108636.3636 | 0 | 90000 | 0 | 100% | Finished | 95000 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 | 2017-10-01 08:00 | 45d | 1172171.0526 | 1172171.0526 | 45d | -194467.2193 | 0 | 977703.8333 | 1172171.0526 | 50% | Started | 989833.3333 | 1979666.6667
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 |  | 0 | 0 | 25000 | 9d | 0 | 0 | 0 | 25000 | 0% | Not Started | 0 | 25000
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 |  | 0 | 0 | 2000 | 11d | 0 | 0 | 0 | 2000 | 0% | Not Started | 0 | 2000
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP24
| TP Status Date | 2018-01-01 17:00 |  | TP Name | TP24
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT Nuclear Healthcare | 2016-01-06 08:00 | 2017-06-09 17:00 | 373d |  |  | 0 |  |  | 4318950 |  | 520d | [5 empty] | 4232553.41 |  | 100% |  | 4318950 | 4318950
1 | Fase 1 Voorontwerp | 2016-01-06 08:00 | 2016-01-29 17:00 | 18d |  | 0 | 0 | 153.125 | 22050 | 22050 | 2016-01-06 08:00 | 19d | 23275 | 0 | 0 | -1225 | 0 | 22050 | 0 | 100% | Finished | 22050 | 22050
2 | Fase 2 opmaak ontwerp &amp; studie | 2016-02-01 08:00 | 2016-02-29 17:00 | 21d |  | 0 | 0 | 1785.7143 | 300000 | 300000 | 2016-01-06 08:00 | 40d | 571428.5714 | 0 | 0 | -366543.5714 | 0 | 204885 | 0 | 100% | Finished | 300000 | 300000
3 | schriftelijke goedkeuring opstarten aanbesteding | 2016-02-29 08:00 | 2016-05-09 17:00 | 51d |  | 0 | 0 | 0 | 0 | 0 | 2016-02-01 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
4 | Fase 3 opmaak bouwvergunningsdossier | 2016-03-15 08:00 | 2016-04-11 17:00 | 20d |  | 0 | 0 | 40 | 6400 | 6400 | 2016-03-15 08:00 | 24d | 7680 | 0 | 0 | -1280 | 0 | 6400 | 0 | 100% | Finished | 6400 | 6400
5 | indienen bouwvergunning en wachten op goedkeuring | 2016-04-11 08:00 | 2016-06-27 17:00 | 56d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-01 08:00 | 44d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
6 | opstellen lastencohier | 2016-04-06 08:00 | 2016-05-09 17:00 | 24d |  | 0 | 0 | 62.5 | 12000 | 12000 | 2016-04-06 08:00 | 8d | 4000 | 0 | 0 | 6550 | 0 | 10550 | 0 | 100% | Finished | 12000 | 12000
7 | opmaak dossier | 2016-05-10 08:00 | 2016-05-16 17:00 | 5d |  | 0 | 0 | 767.5 | 30700 | 30700 | 2016-03-01 08:00 | 44d | 270160 | 0 | 0 | -237490 | 0 | 32670 | 0 | 100% | Finished | 30700 | 30700
8 | goedkeuring dossier | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-04-15 08:00 | 35d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
9 | publicatie | 2016-05-17 08:00 | 2016-05-17 17:00 | 1d |  | 0 | 0 | 312.5 | 2500 | 2500 | 2016-06-02 08:00 | 1d | 2500 | 0 | 0 | 0 | 0 | 2500 | 0 | 100% | Finished | 2500 | 2500
10 | indieningstermijn | 2016-05-18 08:00 | 2016-06-07 17:00 | 15d |  | 0 | 0 | 0 | 0 | 0 | 2016-05-18 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
11 | opening | 2016-06-07 08:00 | 2016-06-07 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
12 | Fase 4 onderzoek offertes | 2016-06-08 08:00 | 2016-06-21 17:00 | 10d |  | 0 | 0 | 40 | 3200 | 3200 | 2016-07-15 08:00 | 39d | 12480 | 0 | 0 | -9280 | 0 | 3200 | 0 | 100% | Finished | 3200 | 3200
13 | opmaak verslag | 2016-06-22 08:00 | 2016-06-28 17:00 | 5d |  | 0 | 0 | 40 | 1600 | 1600 | 2016-09-07 08:00 | 22d | 7040 | 0 | 0 | -5440 | 0 | 1600 | 0 | 100% | Finished | 1600 | 1600
14 | goedkeuring RC | 2016-06-29 08:00 | 2016-07-05 17:00 | 5d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
15 | indienen RvB | 2016-07-15 08:00 | 2016-07-15 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
16 | goedkeuring RvB | 2016-07-26 08:00 | 2016-07-26 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-11-07 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
17 | standstill | 2016-07-26 08:00 | 2016-08-08 17:00 | 10d |  | 0 | 0 | 0 | 0 | 0 | 2016-10-06 08:00 | 43d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
18 | bestelling | 2016-08-09 08:00 | 2016-08-15 17:00 | 5d |  | 0 | 0 | 4125 | 165000 | 165000 | 2016-11-07 08:00 | 21d | 693000 | 0 | 0 | -502239.9 | 0 | 190760.1 | 0 | 100% | Finished | 165000 | 165000
38 | pre-FASE: afbraakwerken/leegmaken lokalen | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  |  | 0 |  |  | 410000 |  | 40d | [5 empty] | 430397.54 |  | 100% |  | 410000 | 410000
19 | voorafgaand leegmaken locatie + afbraakwerken | 2016-09-05 08:00 | 2016-09-23 17:00 | 15d |  | 0 | 0 | 3416.6667 | 410000 | 410000 | 2016-11-07 08:00 | 40d | 1093333.3333 | 0 | 0 | -662935.7933 | 0 | 430397.54 | 0 | 100% | Finished | 410000 | 410000
39 | Fase 0 : SPECT/CT 3 | 2016-09-05 08:00 | 2016-11-25 17:00 | 60d |  |  | 0 |  |  | 195000 |  | 70d | [5 empty] | 215198.77 |  | 100% |  | 195000 | 195000
20 | inrichtingswerken | 2016-09-05 08:00 | 2016-11-18 17:00 | 55d |  | 0 | 0 | 438.6364 | 193000 | 193000 | 2016-06-02 08:00 | 70d | 245636.3636 | 0 | 0 | -30437.5936 | 0 | 215198.77 | 0 | 100% | Finished | 193000 | 193000
21 | opkuis en reserve | 2016-11-21 08:00 | 2016-11-25 17:00 | 5d |  | 0 | 0 | 50 | 2000 | 2000 | 2016-07-15 08:00 | 39d | 15600 | 0 | 0 | -15600 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
22 | ingebruikname | 2016-11-25 08:00 | 2016-11-25 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-07-15 08:00 | 39d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
40 | FASE 1: inrichtingswerken afdeling | 2016-11-28 08:00 | 2017-01-23 17:00 | 41d |  |  | 0 |  |  | 1056833.3333 |  | 278d | [5 empty] | 1037447.3333 |  | 100% |  | 1056833.3333 | 1056833.3333
23 | uitvoering fase 1 (0P8) | 2016-11-28 08:00 | 2017-01-09 17:00 | 31d |  | 0 | 0 | 4204.9731 | 1042833.3333 | 1042833.3333 | 2016-12-05 08:00 | 215d | 7232553.7634 | 0 | 0 | -6207786.4301 | 0 | 1024767.3333 | 0 | 100% | Finished | 1042833.3333 | 1042833.3333
24 | levering en plaatsing PET/CT 2 | 2016-12-29 08:00 | 2017-01-11 17:00 | 10d |  | 0 | 0 | 150 | 12000 | 12000 | 2017-08-01 08:00 | 44d | 52800 | 0 | 0 | -40120 | 0 | 12680 | 0 | 100% | Finished | 12000 | 12000
25 | opkuis en reserve | 2017-01-12 08:00 | 2017-01-23 17:00 | 8d |  | 0 | 0 | 31.25 | 2000 | 2000 | 2016-09-07 08:00 | 22d | 5500 | 0 | 0 | -5500 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
26 | ingebruikname | 2017-01-23 08:00 | 2017-01-23 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2016-09-07 08:00 | 22d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
41 | FASE 2 : inrichting technische ruimte -1P8 | 2017-01-24 08:00 | 2017-06-09 17:00 | 99d |  |  | 0 |  |  | 2113666.6667 |  | 67d | [5 empty] | 2074894.6667 |  | 100% |  | 2113666.6667 | 2113666.6667
27 | installatie PETC/CT 1 op 0P8 | 2017-01-24 08:00 | 2017-02-10 17:00 | 14d |  | 0 | 0 | 107.1429 | 12000 | 12000 | 2017-10-01 08:00 | 45d | 38571.4286 | 0 | 0 | -27584.4286 | 0 | 10987 | 0 | 100% | Finished | 12000 | 12000
28 | indienststelling PET/CT 1 | 2017-02-10 08:00 | 2017-02-10 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2017-11-01 08:00 | 45d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
29 | uitbraakwerken | 2017-01-26 08:00 | 2017-02-09 17:00 | 11d |  | 0 | 0 | 1079.5455 | 95000 | 95000 | 2017-10-01 08:00 | 23d | 198636.3636 | 0 | 0 | -108636.3636 | 0 | 90000 | 0 | 100% | Finished | 95000 | 95000
30 | uitvoering fase 2 ) | 2017-02-10 08:00 | 2017-05-26 17:00 | 76d |  | 0 | 0 | 3256.0307 | 1979666.6667 | 1979666.6667 | 2017-10-01 08:00 | 66d | 1719184.2105 | 0 | 0 | 236223.4561 | 0 | 1955407.6667 | 0 | 100% | Finished | 1979666.6667 | 1979666.6667
31 | aanpassingswerken, regeling en testen 0P8 | 2017-05-16 08:00 | 2017-05-26 17:00 | 9d |  | 0 | 0 | 347.2222 | 25000 | 25000 | 2017-12-01 08:00 | 22d | 61111.1111 | 0 | 0 | -42611.1111 | 0 | 18500 | 0 | 100% | Finished | 25000 | 25000
32 | opkuis en reserve | 2017-05-26 08:00 | 2017-06-09 17:00 | 11d |  | 0 | 0 | 22.7273 | 2000 | 2000 | 2017-12-01 08:00 | 22d | 4000 | 0 | 0 | -4000 | 0 | 0 | 0 | 100% | Finished | 2000 | 2000
33 | oplevering | 2017-06-09 08:00 | 2017-06-09 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-01-01 08:00 | 1d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | SPI | p-factor
TP1 | 2016-01-06 08:00 | 2016-02-01 17:00 | 36335.7143 | 172050 | 124492.5 | 2016-02-15 12:00 | 135714.2857 | 473.5% | 47557.5 | 138.2% | 9d 4h | 150% | 100% | 2017-05-25 10:00 | 2016-04-25 15:00 | 2016-03-24 17:00 | 2017-03-02 17:00 | 2016-04-25 15:00 | 2016-04-01 10:00 | 2017-05-29 12:00 | 2016-12-19 14:00 | 2016-09-21 09:00 | 4271392.5 | 3125119.9237 | 1000287.7547 | 2889092.5 | 758203.2861 | 2124910.7825 | 2144797.4352 | 3074744.4362 | 1.5 | 4.735 | 1
TP2 | 2016-02-01 17:00 | 2016-03-01 17:00 | 322050 | 322050 | 226935 | 2016-03-01 17:00 | 0 | 100% | 95115 | 141.9% | 0 | 100% | 100% | 2017-06-09 17:00 | 2017-06-09 17:00 | 2017-01-06 16:00 | 2017-06-09 17:00 | 2017-06-09 17:00 | 2017-01-24 14:00 | 2017-06-09 17:00 | 2017-06-09 17:00 | 2017-01-24 14:00 | 4223835 | 3043381.2087 | 4223835 | 4223835 | 3043381.2087 | 3043381.2087 | 3220188.0814 | 3220188.0814 | 1 | 1 | 1
TP3 | 2016-03-01 17:00 | 2016-04-15 17:00 | 332450 | 355800 | 260220 | 2016-05-12 12:00 | 23350 | 107% | 95580 | 136.7% | 18d 4h | 125.3% | 100% | 2017-06-07 17:00 | 2017-05-08 12:00 | 2016-12-27 16:00 | 2017-06-02 16:00 | 2017-05-08 12:00 | 2017-01-24 12:00 | 2017-05-16 12:00 | 2017-02-24 14:00 | 2016-12-02 10:00 | 4223370 | 3158732.9089 | 3963281.3196 | 3422077.377 | 2968512.9077 | 2572694.7798 | 3290403.9492 | 3207833.0098 | 1.2534 | 1.0702 | 1
TP4 | 2016-04-15 17:00 | 2016-05-01 17:00 | 337450 | 371150 | 276555 | 2016-05-16 17:00 | 33700 | 110% | 94595 | 134.2% | 11d | 113.3% | 100% | 2017-06-07 09:00 | 2017-04-25 09:00 | 2016-12-23 15:00 | 2017-05-30 15:00 | 2017-04-25 09:00 | 2017-01-23 16:00 | 2017-05-25 17:00 | 2017-04-11 11:00 | 2017-01-12 14:00 | 4224355 | 3218179.2193 | 3865899.2274 | 3762378.4043 | 2951083.069 | 2873946.5979 | 3328321.3512 | 3312987.4688 | 1.1325 | 1.0999 | 1
TP5 | 2016-05-01 17:00 | 2016-06-02 17:00 | 373650 | 373650 | 279055 | 2016-06-02 17:00 | 0 | 100% | 94595 | 133.9% | 0 | 100% | 100% | 2017-06-09 17:00 | 2017-06-09 17:00 | 2017-01-30 14:00 | 2017-06-09 17:00 | 2017-06-09 17:00 | 2017-03-08 14:00 | 2017-06-09 17:00 | 2017-06-09 17:00 | 2017-03-08 14:00 | 4224355 | 3225544.2051 | 4224355 | 4224355 | 3225544.2051 | 3225544.2051 | 3382690.4068 | 3382690.4068 | 1 | 1 | 1
TP6 | 2016-06-02 17:00 | 2016-06-30 17:00 | 378450 | 470150 | 386654.385 | 2016-08-11 16:00 | 91700 | 124.2% | 83495.615 | 121.6% | 29d 7h | 123.5% | 78.94% | 2017-05-31 09:00 | 2017-03-01 10:00 | 2016-12-15 16:00 | 2017-04-28 10:00 | 2017-03-01 10:00 | 2017-01-17 12:00 | 2017-05-01 09:00 | 2017-03-02 17:00 | 2017-01-18 16:00 | 4235454.385 | 3551932.2686 | 3484768.5188 | 3502495.6599 | 2934563.3823 | 2949142.2972 | 3538267.5584 | 3541919.8444 | 1.2352 | 1.2423 | 0.78942
TP7 | 2016-06-30 17:00 | 2016-07-15 17:00 | 378450 | 470150 | 386654.385 | 2016-08-11 16:00 | 91700 | 124.2% | 83495.615 | 121.6% | 18d 7h | 113.7% | 78.94% | 2017-05-31 09:00 | 2017-03-01 10:00 | 2016-12-15 16:00 | 2017-04-25 12:00 | 2017-03-01 10:00 | 2017-01-19 11:00 | 2017-05-16 09:00 | 2017-04-10 09:00 | 2017-02-21 11:00 | 4235454.385 | 3551932.2686 | 3484768.5188 | 3772371.6758 | 2934563.3823 | 3171090.0691 | 3538267.5584 | 3593693.4513 | 1.1368 | 1.2423 | 0.78942
TP8 | 2016-07-15 17:00 | 2016-09-07 17:00 | 635977.2727 | 571850 | 497453.77 | 2016-09-05 16:00 | -64127.2727 | 89.92% | 74396.23 | 115% | -2d 1h | 98.79% | 66.6% | 2017-06-19 12:00 | 2017-08-08 16:00 | 2017-05-24 16:00 | 2017-07-05 15:00 | 2017-08-08 16:00 | 2017-06-26 15:00 | 2017-06-14 09:00 | 2017-06-16 12:00 | 2017-05-11 11:00 | 4244553.77 | 3757065.594 | 4664753.6539 | 4290348.6658 | 4122598.5422 | 3796902.6904 | 3905529.5781 | 3851378.3147 | 0.98793 | 0.89917 | 0.66602
TP9 | 2016-09-07 17:00 | 2016-10-06 17:00 | 1037668.1818 | 575450 | 499053.77 | 2016-09-05 17:00 | -462218.1818 | 55.46% | 76396.23 | 115.3% | -23d | 88.32% | 66.51% | 2017-08-04 16:00 | 2018-08-03 14:00 | 2018-04-02 10:00 | 2017-10-11 15:00 | 2018-08-03 14:00 | 2018-05-08 12:00 | 2017-07-12 17:00 | 2017-08-18 10:00 | 2017-07-07 11:00 | 4242553.77 | 3745570.0407 | 7249441.8813 | 4737384.2298 | 6353266.3617 | 4174707.2489 | 4121639.5693 | 3904974.3332 | 0.88325 | 0.55456 | 0.6651
TP10 | 2016-10-06 17:00 | 2016-11-07 17:00 | 1114868.1818 | 575450 | 499053.77 | 2016-09-05 17:00 | -539418.1818 | 51.62% | 76396.23 | 115.3% | -45d | 79.45% | 66.51% | 2017-08-15 14:00 | 2018-10-12 14:00 | 2018-05-31 15:00 | 2017-11-06 17:00 | 2018-10-12 14:00 | 2018-07-11 15:00 | 2017-08-11 17:00 | 2017-10-24 12:00 | 2017-09-07 10:00 | 4242553.77 | 3745570.0407 | 7751654.4106 | 5210700.3217 | 6788805.6025 | 4585186.3177 | 4148764.7214 | 3960866.6158 | 0.79452 | 0.51616 | 0.6651
TP11 | 2016-11-07 17:00 | 2016-12-05 17:00 | 1350288.7097 | 945450 | 905012.64 | 2016-09-21 17:00 | -404838.7097 | 70.02% | 40437.36 | 104.5% | -53d | 77.82% | 84.08% | 2017-07-28 17:00 | 2018-01-19 15:00 | 2017-12-19 16:00 | 2017-09-19 14:00 | 2018-01-19 15:00 | 2018-01-03 09:00 | 2017-08-23 17:00 | 2017-11-07 10:00 | 2017-10-23 17:00 | 4278512.64 | 4134226.3912 | 5723034.7058 | 5239778.769 | 5516965.54 | 5054378.6966 | 4362239.937 | 4307797.7954 | 0.77824 | 0.70018 | 0.84082
TP12 | 2016-12-05 17:00 | 2017-01-01 17:00 | 1991844.6237 | 1671866.6667 | 1632595.0767 | 2016-12-19 12:00 | -319977.957 | 83.94% | 39271.59 | 102.4% | -9d 4h | 96.32% | 100% | 2017-07-19 14:00 | 2017-09-19 11:00 | 2017-09-04 17:00 | 2017-08-08 12:00 | 2017-09-19 11:00 | 2017-09-12 17:00 | 2017-06-23 12:00 | 2017-06-30 10:00 | 2017-06-27 10:00 | 4279678.41 | 4217499.306 | 4786302.7323 | 4380874.7547 | 4712223.192 | 4316318.5824 | 4314231.4133 | 4248601.764 | 0.96318 | 0.83936 | 1
TP13 | 2017-01-01 17:00 | 2017-02-01 17:00 | 2254465.1515 | 1671866.6667 | 1632595.0767 | 2016-12-19 12:00 | -582598.4848 | 74.16% | 39271.59 | 102.4% | -32d 4h | 88.43% | 100% | 2017-08-21 11:00 | 2017-12-08 17:00 | 2017-11-23 09:00 | 2017-09-20 14:00 | 2017-12-08 17:00 | 2017-12-01 15:00 | 2017-07-26 12:00 | 2017-08-17 15:00 | 2017-08-14 12:00 | 4279678.41 | 4217499.306 | 5202112.4593 | 4625876.4315 | 5118265.6874 | 4555565.2515 | 4368429.429 | 4290010.201 | 0.88434 | 0.74158 | 1
TP14 | 2017-02-01 17:00 | 2017-03-01 17:00 | 2676958.7719 | 1671866.6667 | 1632595.0767 | 2016-12-19 12:00 | -1005092.1053 | 62.45% | 39271.59 | 102.4% | -52d 4h | 82.56% | 100% | 2017-10-10 15:00 | 2018-04-20 10:00 | 2018-04-02 10:00 | 2017-11-15 17:00 | 2018-04-20 10:00 | 2018-04-11 10:00 | 2017-08-23 12:00 | 2017-09-28 15:00 | 2017-09-25 10:00 | 4279678.41 | 4217499.306 | 5871050.8641 | 4838921.3677 | 5771490.9523 | 4763605.8333 | 4436258.3036 | 4321736.4695 | 0.82558 | 0.62454 | 1
TP15 | 2017-03-01 17:00 | 2017-04-01 17:00 | 3250020.1754 | 1671866.6667 | 1632595.0767 | 2016-12-19 12:00 | -1578153.5088 | 51.44% | 39271.59 | 102.4% | -74d 4h | 76.93% | 100% | 2017-12-19 10:00 | 2018-10-17 09:00 | 2018-09-21 17:00 | 2018-01-16 16:00 | 2018-10-17 09:00 | 2018-10-03 14:00 | 2017-09-22 12:00 | 2017-11-14 16:00 | 2017-11-08 17:00 | 4279678.41 | 4217499.306 | 6778384.7565 | 5073270.7977 | 6657511.8744 | 4992450.4733 | 4503222.098 | 4352814.9722 | 0.76935 | 0.51442 | 1
TP16 | 2017-04-01 17:00 | 2017-05-01 17:00 | 3797033.3333 | 1671866.6667 | 1632595.0767 | 2016-12-19 12:00 | -2125166.6667 | 44.03% | 39271.59 | 102.4% | -95d 4h | 72.24% | 100% | 2018-02-22 12:00 | 2019-04-05 09:00 | 2019-03-08 10:00 | 2018-03-07 12:00 | 2019-04-05 09:00 | 2019-03-20 11:00 | 2017-10-23 12:00 | 2017-12-28 11:00 | 2017-12-22 10:00 | 4279678.41 | 4217499.306 | 7644476.1992 | 5296967.9808 | 7503259.1182 | 5210893.0843 | 4550116.626 | 4379328.507 | 0.72238 | 0.44031 | 1
TP17 | 2017-05-01 17:00 | 2017-06-01 17:00 | 4317859.0909 | 1671866.6667 | 1632595.0767 | 2016-12-19 12:00 | -2645992.4242 | 38.72% | 39271.59 | 102.4% | -118d 4h | 67.71% | 100% | 2018-04-26 12:00 | 2019-09-16 11:00 | 2019-08-14 15:00 | 2018-04-20 16:00 | 2019-09-16 11:00 | 2019-08-27 11:00 | 2017-11-23 12:00 | 2018-02-14 16:00 | 2018-02-08 12:00 | 4279678.41 | 4217499.306 | 8469104.8673 | 5541969.6575 | 8308517.534 | 5450139.7534 | 4584677.6155 | 4405379.5267 | 0.67711 | 0.3872 | 1
TP18 | 2017-06-01 17:00 | 2017-07-01 17:00 | 4318950 | 1671866.6667 | 1632595.0767 | 2016-12-19 12:00 | -2647083.3333 | 38.71% | 39271.59 | 102.4% | -139d 4h | 64.05% | 100% | 2018-04-26 14:00 | 2019-09-16 14:00 | 2019-08-14 17:00 | 2018-05-30 15:00 | 2019-11-08 11:00 | 2019-10-18 16:00 | 2017-12-22 12:00 | 2018-03-30 11:00 | 2018-03-23 16:00 | 4279678.41 | 4217499.306 | 8470832.1146 | 5765666.8406 | 8310204.2089 | 5668582.3643 | 4584742.0135 | 4426832.6096 | 0.64046 | 0.3871 | 1
TP19 | 2017-07-01 17:00 | 2017-08-01 17:00 | 4318950 | 1671866.6667 | 1632595.0767 | 2016-12-19 12:00 | -2647083.3333 | 38.71% | 39271.59 | 102.4% | -161d 4h | 60.61% | 100% | 2018-04-26 14:00 | 2019-09-16 14:00 | 2019-08-14 17:00 | 2018-07-19 10:00 | 2020-01-28 09:00 | 2020-01-06 16:00 | 2018-01-23 12:00 | 2018-05-16 11:00 | 2018-05-09 14:00 | 4279678.41 | 4217499.306 | 8470832.1146 | 6000016.2705 | 8310204.2089 | 5897427.0043 | 4584742.0135 | 4447253.984 | 0.6061 | 0.3871 | 1
TP20 | 2017-08-01 17:00 | 2017-09-01 17:00 | 4318950 | 1677866.6667 | 1638935.0767 | 2016-12-19 14:00 | -2641083.3333 | 38.85% | 38931.59 | 102.4% | -184d 3h | 57.42% | 99.75% | 2018-04-26 09:00 | 2019-09-11 09:00 | 2019-08-09 16:00 | 2018-09-07 15:00 | 2020-04-14 14:00 | 2020-03-23 15:00 | 2018-02-23 11:00 | 2018-07-03 14:00 | 2018-06-26 14:00 | 4280018.41 | 4218737.2751 | 8437274.3542 | 6238589.5094 | 8279532.2865 | 6131863.5912 | 4584267.5542 | 4467126.775 | 0.57419 | 0.38849 | 0.99749
TP21 | 2017-09-01 17:00 | 2017-10-01 17:00 | 4318950 | 2205283.3333 | 2157658.7433 | 2017-01-23 17:00 | -2113666.6667 | 51.06% | 47624.59 | 102.2% | -179d | 60.49% | 100% | 2018-02-21 12:00 | 2018-10-24 12:00 | 2018-10-02 15:00 | 2018-08-07 15:00 | 2019-05-31 09:00 | 2019-05-17 15:00 | 2018-02-15 17:00 | 2018-05-17 14:00 | 2018-05-14 09:00 | 4271325.41 | 4225679.3441 | 6297181.5484 | 5652151.4441 | 6207785.7445 | 5576685.503 | 4455674.1639 | 4409524.2443 | 0.60486 | 0.51061 | 1
TP22 | 2017-10-01 17:00 | 2017-11-01 17:00 | 4318950 | 3296116.6667 | 3230856.0767 | 2017-04-04 15:00 | -1022833.3333 | 76.32% | 65260.59 | 102% | -151d 2h | 68.22% | 99.82% | 2017-10-12 11:00 | 2017-11-20 15:00 | 2017-11-07 09:00 | 2018-04-09 15:00 | 2018-05-28 15:00 | 2018-05-23 15:00 | 2018-01-09 10:00 | 2018-02-08 15:00 | 2018-02-07 11:00 | 4253689.41 | 4233438.092 | 4571089.5914 | 4730066.7515 | 4544553.9924 | 4700383.5264 | 4286635.6194 | 4304574.0757 | 0.68225 | 0.76318 | 0.99818
TP23 | 2017-11-01 17:00 | 2017-12-01 17:00 | 4318950 | 3302116.6667 | 3236349.5767 | 2017-04-04 17:00 | -1016833.3333 | 76.46% | 65767.09 | 102% | -173d | 65.26% | 100% | 2017-10-11 16:00 | 2017-11-17 16:00 | 2017-11-06 09:00 | 2018-05-16 10:00 | 2018-07-05 11:00 | 2018-07-02 10:00 | 2018-02-07 17:00 | 2018-03-15 12:00 | 2018-03-14 09:00 | 4253182.91 | 4232931.0001 | 4566300.2623 | 4794451.1151 | 4539812.1048 | 4763418.9577 | 4285529.0696 | 4310341.6346 | 0.65261 | 0.76456 | 1
TP24 | 2017-12-01 17:00 | 2018-01-01 17:00 | 4318950 | 4318950 | 4232553.41 | 2017-06-09 17:00 | 0 | 100% | 86396.59 | 102% | -146d | 71.87% | 100% | 2017-06-09 17:00 | 2017-06-09 17:00 | 2017-05-31 12:00 | 2018-01-01 17:00 | 2018-01-01 17:00 | 2018-01-01 17:00 | 2018-01-01 17:00 | 2018-01-01 17:00 | 2018-01-01 17:00 | 4232553.41 | 4232553.41 | 4232553.41 | 4232553.41 | 4232553.41 | 4232553.41 | 4232553.41 | 4232553.41 | 0.71869 | 1 | 1

## Corrective actions Overview
General |  |  | Corrective actions
Name | Start Tracking Period | Status date | Category | Description
TP1 | 2016-01-06 08:00 | 2016-02-01 17:00 | - | -
TP2 | 2016-02-01 17:00 | 2016-03-01 17:00 | - | -
TP3 | 2016-03-01 17:00 | 2016-04-15 17:00 | - | -
TP4 | 2016-04-15 17:00 | 2016-05-01 17:00 | - | -
TP5 | 2016-05-01 17:00 | 2016-06-02 17:00 | - | -
TP6 | 2016-06-02 17:00 | 2016-06-30 17:00 | - | -
TP7 | 2016-06-30 17:00 | 2016-07-15 17:00 | - | -
TP8 | 2016-07-15 17:00 | 2016-09-07 17:00 | - | -
TP9 | 2016-09-07 17:00 | 2016-10-06 17:00 | C1 | Status update call employees
TP10 | 2016-10-06 17:00 | 2016-11-07 17:00 | - | -
TP11 | 2016-11-07 17:00 | 2016-12-05 17:00 | - | -
TP12 | 2016-12-05 17:00 | 2017-01-01 17:00 | - | -
TP13 | 2017-01-01 17:00 | 2017-02-01 17:00 | - | -
TP14 | 2017-02-01 17:00 | 2017-03-01 17:00 | - | -
TP15 | 2017-03-01 17:00 | 2017-04-01 17:00 | - | -
TP16 | 2017-04-01 17:00 | 2017-05-01 17:00 | - | -
TP17 | 2017-05-01 17:00 | 2017-06-01 17:00 | - | -
TP18 | 2017-06-01 17:00 | 2017-07-01 17:00 | - | -
TP19 | 2017-07-01 17:00 | 2017-08-01 17:00 | - | -
TP20 | 2017-08-01 17:00 | 2017-09-01 17:00 | C4 | Use compensation claim in contracts
TP21 | 2017-09-01 17:00 | 2017-10-01 17:00 | - | -
TP22 | 2017-10-01 17:00 | 2017-11-01 17:00 | - | -
TP23 | 2017-11-01 17:00 | 2017-12-01 17:00 | - | -
TP24 | 2017-12-01 17:00 | 2018-01-01 17:00 | - | -