## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | Christmas Market | 1 |  |  | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 | 131.2917
1 | START | 1.1 |  | FS2 | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | -0.625
2 | Creation of the activities plan and location | 1.2 | 1FS | FS3 | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 4.375
3 | Asking City Hall Permission / License - email | 1.3 | 2FS | FS4 | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 29.375
4 | Receiving acceptance | 1.4 | 3FS | FS5;FS6;FS7;FS8;FS21 | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 1.0833
5 | Creation of a safety plan | 1.5 | 4FS | FS9 | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2
6 | Contacting vegan restaurants and sponsors | 1.6 | 4FS | SS10;FS27;FS13 | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 30
7 | Contacting the truck/stand company | 1.7 | 4FS | FS14 | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 14
8 | Contacting / contract Music band/ DJ | 1.8 | 4FS | FS14 | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 14
9 | Approval of the security plan and coordination with the police | 1.9 | 5FS | FS14;FS24 | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 20
10 | Design the Marketing Campaign | 1.10 | 6SS | FS11;FS12 | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 7
11 | Ordering posters and flyers | 1.11 | 10FS | FS13 | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 1.0833
12 | Preparing online campaign | 1.12 | 10FS | FS13 | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 4.375
13 | Start Marketing campaign | 1.13 | 11FS;12FS;6FS | FS27 | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 30
14 | Cut the Circulation | 1.14 | 7FS;8FS;9FS | FS15 | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 1.0833
15 | Installing the tent | 1.15 | 14FS;24FS | FS16;FS18;FS17;FS19;FS20 | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2
16 | Installation of electricity/cabling | 1.16 | 15FS | FS22 | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 3
17 | Stands Construction | 1.17 | 15FS | FS22 | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2
18 | Backstage Construction | 1.18 | 15FS | FS22 | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2
19 | Bathrooms construction/installation | 1.19 | 15FS | FS22 | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 1
20 | Tables installation | 1.20 | 15FS | FS22 | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 1
21 | Designing and Budgeting Christmas decoration | 1.21 | 4FS | FS22 | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 6
22 | Installation of the decoration | 1.22 | 21FS;20FS;19FS;18FS;17FS;16FS | FS23 | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2
23 | Open circulation | 1.23 | 22FS | FS25 | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 1
24 | Hiring security guards | 1.24 | 9FS | FS15 | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 7
25 | Technical Control | 1.25 | 23FS | FS26 | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 1
26 | Placement of people and food | 1.26 | 25FS | FS27 | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 1.9583
27 | Market opening | 1.27 | 13FS;26FS;6FS | FS28 | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 30
28 | Market closing | 1.28 | 27FS | FS29 | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 | 1.0833
29 | Cut circulation | 1.29 | 28FS | FS30;FS31 | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 1.0833
30 | Cleaning | 1.30 | 29FS | FS32 | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 | 1.0833
31 | Uninstallation | 1.31 | 29FS | FS32 | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 | 2
32 | Opening circulation | 1.32 | 30FS;31FS | FS33 | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 1
33 | END | 1.33 | 32FS |  | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost
1 | Team | Renewable | 5 People | 0 | 20 | 2[5.00 Team];4[0.00 Team];5[2.00 Team];6;7;8;10[3.00 Team];11;12;15;21[5.00 Team];22[2.00 Team];24;26[2.00 Team];27[5.00 Team];28;30[5.00 Team]; | 51000
2 | Volunteers | Renewable | 10 People | 0 | 0 | 14[5.00 Volunteers];15[10.00 Volunteers];17[4.00 Volunteers];18[5.00 Volunteers];20[6.00 Volunteers];22[6.00 Volunteers];23[5.00 Volunteers];26[4.00 Volunteers];27[10.00 Volunteers];28[10.00 Volunteers];29[5.00 Volunteers];30[10.00 Volunteers];31[4.00 Volunteers];32[5.00 Volunteers]; | 0

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic | Optimistic (%) | Most probable (%) | Pessimistic (%)
0 | Christmas Market | 1054h |  |  |  |  | 99 | 100 | 101
1 | START | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
2 | Creation of the activities plan and location | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
3 | Asking City Hall Permission / License - email | 240h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
4 | Receiving acceptance | 10h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
5 | Creation of a safety plan | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
6 | Contacting vegan restaurants and sponsors | 240h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
7 | Contacting the truck/stand company | 112h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
8 | Contacting / contract Music band/ DJ | 112h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
9 | Approval of the security plan and coordination with the police | 160h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
10 | Design the Marketing Campaign | 56h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
11 | Ordering posters and flyers | 10h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
12 | Preparing online campaign | 40h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
13 | Start Marketing campaign | 240h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
14 | Cut the Circulation | 10h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
15 | Installing the tent | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
16 | Installation of electricity/cabling | 24h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
17 | Stands Construction | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
18 | Backstage Construction | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
19 | Bathrooms construction/installation | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
20 | Tables installation | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
21 | Designing and Budgeting Christmas decoration | 48h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
22 | Installation of the decoration | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
23 | Open circulation | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
24 | Hiring security guards | 56h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
25 | Technical Control | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
26 | Placement of people and food | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
27 | Market opening | 240h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
28 | Market closing | 10h | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101
29 | Cut circulation | 10h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
30 | Cleaning | 10h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
31 | Uninstallation | 16h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
32 | Opening circulation | 8h | standard - skewed left | 80 | 110 | 120 | 80 | 110 | 120
33 | END | 0 | standard - no risk | 99 | 100 | 101 | 99 | 100 | 101

## TP1
| TP Status Date | 2018-08-30 17:00 |  | TP Name | 30/08/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 5d | [5 empty] | 4000 |  | 4.604% |  | 2711.8645 | 4000
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 5d | 4000 | 1900 | 2d 3h | 0 | 0 | 4000 | 1900 | 67.8% | Started | 2711.8645 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 30d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 0
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2018-09-04 17:00 |  | TP Name | 04/09/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 10d | [5 empty] | 6100 |  | 7.131% |  | 4200 | 4200
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 2d 5h | 200 | 0 | 39d 6h | 0 | 0 | 200 | 0 | 6.195% | Started | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 0
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2018-09-09 17:00 |  | TP Name | 09/09/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 15d | [5 empty] | 6100 |  | 7.131% |  | 4200 | 4200
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 7d 5h | 200 | 0 | 34d 6h | 0 | 0 | 200 | 0 | 17.99% | Started | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 0
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2018-09-14 17:00 |  | TP Name | 14/09/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 20d | [5 empty] | 6100 |  | 7.131% |  | 4200 | 4200
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 12d 5h | 200 | 0 | 29d 6h | 0 | 0 | 200 | 0 | 29.79% | Started | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 0
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2018-09-19 17:00 |  | TP Name | 19/09/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 25d | [5 empty] | 6100 |  | 7.131% |  | 4200 | 4200
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 17d 5h | 200 | 0 | 24d 6h | 0 | 0 | 200 | 0 | 41.59% | Started | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 0
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP6
| TP Status Date | 2018-09-24 17:00 |  | TP Name | 24/09/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 30d | [5 empty] | 6100 |  | 7.131% |  | 4200 | 4200
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 22d 5h | 200 | 0 | 19d 6h | 0 | 0 | 200 | 0 | 53.39% | Started | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 0
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP7
| TP Status Date | 2018-09-29 17:00 |  | TP Name | 29/09/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 35d | [5 empty] | 6100 |  | 7.131% |  | 4200 | 4200
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 27d 5h | 200 | 0 | 14d 6h | 0 | 0 | 200 | 0 | 65.19% | Started | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 0
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 0
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 0
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP8
| TP Status Date | 2018-10-04 17:00 |  | TP Name | 04/10/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 40d | [5 empty] | 6100 |  | 7.131% |  | 4200 | 11840
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 32d 5h | 200 | 0 | 9d 6h | 0 | 0 | 200 | 0 | 76.99% | Started | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 600
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 600
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 600
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 1800
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 3000
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP9
| TP Status Date | 2018-10-09 17:00 |  | TP Name | 09/10/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 45d | [5 empty] | 6100 |  | 7.131% |  | 4200 | 17600
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 37d 5h | 200 | 0 | 4d 6h | 0 | 0 | 200 | 0 | 88.79% | Started | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 1400
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 1400
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 1400
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP10
| TP Status Date | 2018-10-14 17:00 |  | TP Name | 14/10/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 50d | [5 empty] | 6300 |  | 7.47% |  | 4400 | 20000
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 2h | 200 | 0 | 1d 2h | 0 | 0 | 200 | 0 | 16.67% | Started | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 30d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 2200
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 2200
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 |  | 0 | 0 | 2240 | 14d | 0 | 0 | 0 | 2240 | 0% | Not Started | 0 | 2200
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 20d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 |  | 0 | 0 | 3360 | 7d | 0 | 0 | 0 | 3360 | 0% | Not Started | 0 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 |  | 0 | 0 | 4800 | 6d | 0 | 0 | 0 | 4800 | 0% | Not Started | 0 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP11
| TP Status Date | 2018-10-19 17:00 |  | TP Name | 19/10/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 55d | [5 empty] | 13980 |  | 15.87% |  | 9344.6458 | 20880
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 3d 6h | 600 | 4240 | 26d 4h | 0 | 0 | 600 | 4240 | 12.4% | Started | 595.0413 | 3000
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 3d 6h | 600 | 3580 | 22d 3h | 0 | 0 | 600 | 3580 | 14.35% | Started | 321.5311 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 3d 6h | 600 | 3200 | 20d | 0 | 0 | 600 | 3200 | 15.79% | Started | 353.6842 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 1d | 200 | 0 | 30d 1h | 0 | 0 | 200 | 0 | 3.213% | Started | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 3d 6h | 1800 | 4320 | 9d | 0 | 0 | 1800 | 4320 | 29.41% | Started | 988.2353 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 0
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 0
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 3d 6h | 3000 | 4800 | 6d | 0 | 0 | 3000 | 4800 | 38.46% | Started | 1846.1539 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 0
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP12
| TP Status Date | 2018-10-24 17:00 |  | TP Name | 24/10/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 60d | [5 empty] | 22780 |  | 25.16% |  | 14817.5069 | 24160
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 8d 6h | 1400 | 3440 | 21d 4h | 0 | 0 | 1400 | 3440 | 28.93% | Started | 1388.4297 | 3800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 8d 6h | 1400 | 2780 | 17d 3h | 0 | 0 | 1400 | 2780 | 33.49% | Started | 750.2393 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 8d 6h | 1400 | 2400 | 15d | 0 | 0 | 1400 | 2400 | 36.84% | Started | 825.2631 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 6d | 200 | 0 | 25d 1h | 0 | 0 | 200 | 0 | 19.28% | Started | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 8d 6h | 4200 | 1920 | 4d | 0 | 0 | 4200 | 1920 | 68.63% | Started | 2305.8824 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 |  | 0 | 0 | 1200 | 1d 2h | 0 | 0 | 0 | 1200 | 0% | Not Started | 0 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 |  | 0 | 0 | 800 | 5d | 0 | 0 | 0 | 800 | 0% | Not Started | 0 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 8d 6h | 7000 | 800 | 1d | 0 | 0 | 7000 | 800 | 89.74% | Started | 4307.6923 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 280
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP13
| TP Status Date | 2018-10-29 17:00 |  | TP Name | 29/10/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 65d | [5 empty] | 29220 |  | 32.65% |  | 19232.9831 | 25760
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 13d 6h | 2200 | 2640 | 16d 4h | 0 | 0 | 2200 | 2640 | 45.45% | Started | 2181.8182 | 4600
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 13d 6h | 2200 | 1980 | 12d 3h | 0 | 0 | 2200 | 1980 | 52.63% | Started | 1178.9474 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 13d 6h | 2200 | 1600 | 10d | 0 | 0 | 2200 | 1600 | 57.89% | Started | 1296.8421 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 11d | 200 | 0 | 20d 1h | 0 | 0 | 200 | 0 | 35.34% | Started | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 1d | 1160 | 200 | 1d 2h | 0 | 0 | 1160 | 200 | 44.44% | Started | 1088.8889 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 1d | 160 | 1320 | 8d 2h | 0 | 0 | 160 | 1320 | 10.81% | Started | 86.4865 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 0
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 0
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 1080
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP14
| TP Status Date | 2018-11-03 17:00 |  | TP Name | 03/11/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 70d | [5 empty] | 32620 |  | 36.45% |  | 21470.2022 | 30820
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 18d 6h | 3000 | 1840 | 11d 4h | 0 | 0 | 3000 | 1840 | 61.98% | Started | 2975.2067 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 18d 6h | 3000 | 1180 | 7d 3h | 0 | 0 | 3000 | 1180 | 71.77% | Started | 1607.6555 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 18d 6h | 3000 | 800 | 5d | 0 | 0 | 3000 | 800 | 78.95% | Started | 1768.4211 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 16d | 200 | 0 | 15d 1h | 0 | 0 | 200 | 0 | 51.41% | Started | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 6d | 960 | 520 | 3d 2h | 0 | 0 | 960 | 520 | 64.86% | Started | 518.9189 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 0
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP15
| TP Status Date | 2018-11-08 17:00 |  | TP Name | 08/11/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 75d | [5 empty] | 35540 |  | 39.8% |  | 23444.9586 | 32820
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 23d 6h | 3800 | 1040 | 6d 4h | 0 | 0 | 3800 | 1040 | 78.51% | Started | 3768.5949 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 380 | 2d 3h | 0 | 0 | 3800 | 380 | 90.91% | Started | 2036.3637 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 21d | 200 | 0 | 10d 1h | 0 | 0 | 200 | 0 | 67.47% | Started | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 160
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP16
| TP Status Date | 2018-11-13 17:00 |  | TP Name | 13/11/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 80d | [5 empty] | 36720 |  | 41.5% |  | 24441.9835 | 33300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 28d 6h | 4600 | 240 | 1d 4h | 0 | 0 | 4600 | 240 | 95.04% | Started | 4561.9835 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 26d | 200 | 0 | 5d 1h | 0 | 0 | 200 | 0 | 83.53% | Started | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 30d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP17
| TP Status Date | 2018-11-18 17:00 |  | TP Name | 18/11/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 85d | [5 empty] | 37460 |  | 42.75% |  | 25180 | 33300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d | 200 | 0 | 1h | 0 | 0 | 200 | 0 | 99.6% | Started | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 3d 4h | 500 | 0 | 49d 6h | 0 | 0 | 500 | 0 | 6.573% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 |  | 0 | 0 | 1120 | 7d | 0 | 0 | 0 | 1120 | 0% | Not Started | 0 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP18
| TP Status Date | 2018-11-23 17:00 |  | TP Name | 23/11/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 90d | [5 empty] | 38440 |  | 43.94% |  | 25882.069 | 33300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 8d 4h | 500 | 0 | 44d 6h | 0 | 0 | 500 | 0 | 15.96% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 4d 7h | 780 | 960 | 6d | 0 | 0 | 780 | 960 | 44.83% | Started | 502.069 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP19
| TP Status Date | 2018-11-28 17:00 |  | TP Name | 28/11/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 95d | [5 empty] | 39240 |  | 44.82% |  | 26397.0115 | 33300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 13d 4h | 500 | 0 | 39d 6h | 0 | 0 | 500 | 0 | 25.35% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 |  | 0 | 0 | 320 | 2d | 0 | 0 | 0 | 320 | 0% | Not Started | 0 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 3d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 2d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 |  | 0 | 0 | 500 | 1d | 0 | 0 | 0 | 500 | 0% | Not Started | 0 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 9d 7h | 1580 | 160 | 1d | 0 | 0 | 1580 | 160 | 90.8% | Started | 1017.0115 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 0
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP20
| TP Status Date | 2018-12-03 17:00 |  | TP Name | 03/12/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 100d | [5 empty] | 43840 |  | 52.33% |  | 30820 | 36300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 18d 4h | 500 | 0 | 34d 6h | 0 | 0 | 500 | 0 | 34.74% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 1d 2h | 1000 | 0 | 2d 2h | 0 | 0 | 1000 | 0 | 35.71% | Started | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 1d 2h | 1000 | 0 | 2d 2h | 0 | 0 | 1000 | 0 | 35.71% | Started | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 1d 2h | 1000 | 0 | 1d 3h | 0 | 0 | 1000 | 0 | 47.62% | Started | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 2h | 500 | 0 | 5h | 0 | 0 | 500 | 0 | 66.67% | Started | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 2h | 500 | 0 | 1h | 0 | 0 | 500 | 0 | 90.91% | Started | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 3000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP21
| TP Status Date | 2018-12-08 17:00 |  | TP Name | 08/12/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 105d | [5 empty] | 44720 |  | 53.15% |  | 31305.5172 | 40300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 23d 4h | 500 | 0 | 29d 6h | 0 | 0 | 500 | 0 | 44.13% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 2d 6h | 880 | 280 | 7h | 0 | 0 | 880 | 280 | 75.86% | Started | 485.5172 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 |  | 0 | 0 | 640 | 2d | 0 | 0 | 0 | 640 | 0% | Not Started | 0 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 7000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP22
| TP Status Date | 2018-12-13 17:00 |  | TP Name | 13/12/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 110d | [5 empty] | 46560 |  | 55.92% |  | 32934.2857 | 44300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 28d 4h | 500 | 0 | 24d 6h | 0 | 0 | 500 | 0 | 53.52% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 1d 1h | 360 | 480 | 1d 4h | 0 | 0 | 360 | 480 | 42.86% | Started | 274.2857 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 11000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP23
| TP Status Date | 2018-12-18 17:00 |  | TP Name | 18/12/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 115d | [5 empty] | 47040 |  | 56.54% |  | 33300 | 48300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 33d 4h | 500 | 0 | 19d 6h | 0 | 0 | 500 | 0 | 62.91% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 15000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP24
| TP Status Date | 2018-12-23 17:00 |  | TP Name | 23/12/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 120d | [5 empty] | 47040 |  | 56.54% |  | 33300 | 52300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 38d 4h | 500 | 0 | 14d 6h | 0 | 0 | 500 | 0 | 72.3% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 19000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP25
| TP Status Date | 2018-12-28 17:00 |  | TP Name | 28/12/2018 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 125d | [5 empty] | 47040 |  | 56.54% |  | 33300 | 56300
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 43d 4h | 500 | 0 | 9d 6h | 0 | 0 | 500 | 0 | 81.69% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 23000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 0
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP26
| TP Status Date | 2019-01-02 17:00 |  | TP Name | 02/01/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 130d | [5 empty] | 47040 |  | 56.54% |  | 33300 | 58700
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 48d 4h | 500 | 0 | 4d 6h | 0 | 0 | 500 | 0 | 91.08% | Started | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 |  | 0 | 0 | 24000 | 30d | 0 | 0 | 0 | 24000 | 0% | Not Started | 0 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 0
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP27
| TP Status Date | 2019-01-07 17:00 |  | TP Name | 07/01/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 135d | [5 empty] | 47240 |  | 56.77% |  | 33439.5349 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 2h | 200 | 34200 | 42d 6h | 0 | 0 | 200 | 34200 | 0.5814% | Started | 139.5349 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP28
| TP Status Date | 2019-01-12 17:00 |  | TP Name | 12/01/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 140d | [5 empty] | 51240 |  | 61.51% |  | 36230.2325 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 5d 2h | 4200 | 30200 | 37d 6h | 0 | 0 | 4200 | 30200 | 12.21% | Started | 2930.2325 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP29
| TP Status Date | 2019-01-17 17:00 |  | TP Name | 17/01/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 145d | [5 empty] | 55240 |  | 66.25% |  | 39020.9301 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 10d 2h | 8200 | 26200 | 32d 6h | 0 | 0 | 8200 | 26200 | 23.84% | Started | 5720.9301 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP30
| TP Status Date | 2019-01-22 17:00 |  | TP Name | 22/01/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 150d | [5 empty] | 59240 |  | 70.99% |  | 41811.6277 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 15d 2h | 12200 | 22200 | 27d 6h | 0 | 0 | 12200 | 22200 | 35.47% | Started | 8511.6277 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP31
| TP Status Date | 2019-01-27 17:00 |  | TP Name | 27/01/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 155d | [5 empty] | 63240 |  | 75.73% |  | 44602.3252 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 20d 2h | 16200 | 18200 | 22d 6h | 0 | 0 | 16200 | 18200 | 47.09% | Started | 11302.3252 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP32
| TP Status Date | 2019-02-01 17:00 |  | TP Name | 01/02/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 160d | [5 empty] | 67240 |  | 80.46% |  | 47393.0228 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 25d 2h | 20200 | 14200 | 17d 6h | 0 | 0 | 20200 | 14200 | 58.72% | Started | 14093.0228 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP33
| TP Status Date | 2019-02-06 17:00 |  | TP Name | 06/02/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 165d | [5 empty] | 71240 |  | 85.2% |  | 50183.7204 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 30d 2h | 24200 | 10200 | 12d 6h | 0 | 0 | 24200 | 10200 | 70.35% | Started | 16883.7204 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP34
| TP Status Date | 2019-02-11 17:00 |  | TP Name | 11/02/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 170d | [5 empty] | 75240 |  | 89.94% |  | 52974.418 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 35d 2h | 28200 | 6200 | 7d 6h | 0 | 0 | 28200 | 6200 | 81.98% | Started | 19674.418 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP35
| TP Status Date | 2019-02-16 17:00 |  | TP Name | 16/02/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 175d | [5 empty] | 79240 |  | 94.68% |  | 55765.117 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 40d 2h | 32200 | 2200 | 2d 6h | 0 | 0 | 32200 | 2200 | 93.6% | Started | 22465.117 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP36
| TP Status Date | 2019-02-21 17:00 |  | TP Name | 21/02/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 180d | [5 empty] | 81800 |  | 97.61% |  | 57489.4737 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 43d | 34400 | 0 | 0 | 0 | 0 | 34400 | 0 | 100% | Finished | 24000 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 | 2019-02-19 15:00 | 2d 2h | 360 | 20 | 1h | 0 | 0 | 360 | 20 | 94.74% | Started | 189.4737 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d 2h | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 |  | 0 | 0 | 1000 | 1d 2h | 0 | 0 | 0 | 1000 | 0% | Not Started | 0 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 2d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 |  | 0 | 0 | 200 | 1d | 0 | 0 | 0 | 200 | 0% | Not Started | 0 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP37
| TP Status Date | 2019-02-26 17:00 |  | TP Name | 26/02/2019 17:00
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | Christmas Market | 2018-08-26 08:00 | 2019-01-04 15:00 | 131d 6h |  |  | 7900 |  |  | 58900 |  | 184d 5h | [5 empty] | 83920 |  | 100% |  | 58900 | 58900
1 | START | 2018-08-26 08:00 | 2018-08-25 17:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2018-08-26 08:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
2 | Creation of the activities plan and location | 2018-08-26 08:00 | 2018-08-30 17:00 | 5d | Team[5.00 #5] | 4000 | 0 | 0 | 0 | 4000 | 2018-08-26 08:00 | 7d 3h | 5900 | 0 | 0 | 0 | 0 | 5900 | 0 | 100% | Finished | 4000 | 4000
3 | Asking City Hall Permission / License - email | 2018-08-31 08:00 | 2018-09-29 17:00 | 30d |  | 0 | 200 | 0 | 0 | 200 | 2018-09-02 11:00 | 42d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
4 | Receiving acceptance | 2018-09-30 08:00 | 2018-10-01 10:00 | 1d 2h | Team[0.00 #5] | 0 | 200 | 0 | 0 | 200 | 2018-10-14 15:00 | 1d 4h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
5 | Creation of a safety plan | 2018-10-01 10:00 | 2018-10-03 10:00 | 2d | Team[2.00 #5] | 640 | 0 | 0 | 0 | 640 | 2018-10-16 10:00 | 2d 6h | 880 | 0 | 0 | 0 | 0 | 880 | 0 | 100% | Finished | 640 | 640
6 | Contacting vegan restaurants and sponsors | 2018-10-01 10:00 | 2018-10-31 10:00 | 30d | Team | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 30d 2h | 4840 | 0 | 0 | 0 | 0 | 4840 | 0 | 100% | Finished | 4800 | 4800
7 | Contacting the truck/stand company | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 26d 1h | 4180 | 0 | 0 | 0 | 0 | 4180 | 0 | 100% | Finished | 2240 | 2240
8 | Contacting / contract Music band/ DJ | 2018-10-01 10:00 | 2018-10-15 10:00 | 14d | Team | 2240 | 0 | 0 | 0 | 2240 | 2018-10-16 10:00 | 23d 6h | 3800 | 0 | 0 | 0 | 0 | 3800 | 0 | 100% | Finished | 2240 | 2240
9 | Approval of the security plan and coordination with the police | 2018-10-03 10:00 | 2018-10-23 10:00 | 20d |  | 0 | 200 | 0 | 0 | 200 | 2018-10-19 08:00 | 31d 1h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
10 | Design the Marketing Campaign | 2018-10-01 10:00 | 2018-10-08 10:00 | 7d | Team[3.00 #5] | 3360 | 0 | 0 | 0 | 3360 | 2018-10-16 10:00 | 12d 6h | 6120 | 0 | 0 | 0 | 0 | 6120 | 0 | 100% | Finished | 3360 | 3360
11 | Ordering posters and flyers | 2018-10-20 08:00 | 2018-10-21 10:00 | 1d 2h | Team | 200 | 1000 | 0 | 0 | 1200 | 2018-10-29 08:00 | 2d 2h | 1360 | 0 | 0 | 0 | 0 | 1360 | 0 | 100% | Finished | 1200 | 1200
12 | Preparing online campaign | 2018-10-20 08:00 | 2018-10-24 17:00 | 5d | Team | 800 | 0 | 0 | 0 | 800 | 2018-10-29 08:00 | 9d 2h | 1480 | 0 | 0 | 0 | 0 | 1480 | 0 | 100% | Finished | 800 | 800
13 | Start Marketing campaign | 2018-10-31 10:00 | 2018-11-30 10:00 | 30d |  | 0 | 500 | 0 | 0 | 500 | 2018-11-15 13:00 | 53d 2h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
14 | Cut the Circulation | 2018-10-23 10:00 | 2018-10-24 12:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-11-19 09:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
15 | Installing the tent | 2018-10-30 10:00 | 2018-11-01 10:00 | 2d | Team;Volunteers[10.00 #10] | 320 | 0 | 0 | 0 | 320 | 2018-11-30 08:00 | 2d 6h | 440 | 0 | 0 | 0 | 0 | 440 | 0 | 100% | Finished | 320 | 320
16 | Installation of electricity/cabling | 2018-11-01 10:00 | 2018-11-04 10:00 | 3d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
17 | Stands Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[4.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 3d 4h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
18 | Backstage Construction | 2018-11-01 10:00 | 2018-11-03 10:00 | 2d | Volunteers[5.00 #10] | 0 | 1000 | 0 | 0 | 1000 | 2018-12-02 15:00 | 2d 5h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
19 | Bathrooms construction/installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d |  | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 7h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
20 | Tables installation | 2018-11-01 10:00 | 2018-11-02 10:00 | 1d | Volunteers[6.00 #10] | 0 | 500 | 0 | 0 | 500 | 2018-12-02 15:00 | 1d 3h | 500 | 0 | 0 | 0 | 0 | 500 | 0 | 100% | Finished | 500 | 500
21 | Designing and Budgeting Christmas decoration | 2018-10-01 10:00 | 2018-10-07 10:00 | 6d | Team[5.00 #5] | 4800 | 0 | 0 | 0 | 4800 | 2018-10-16 10:00 | 9d 6h | 7800 | 0 | 0 | 0 | 0 | 7800 | 0 | 100% | Finished | 4800 | 4800
22 | Installation of the decoration | 2018-11-04 10:00 | 2018-11-06 10:00 | 2d | Team[2.00 #5];Volunteers[6.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-06 10:00 | 3d 5h | 1160 | 0 | 0 | 0 | 0 | 1160 | 0 | 100% | Finished | 640 | 640
23 | Open circulation | 2018-11-06 10:00 | 2018-11-07 10:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2018-12-09 16:00 | 1d 5h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
24 | Hiring security guards | 2018-10-23 10:00 | 2018-10-30 10:00 | 7d | Team | 1120 | 0 | 0 | 0 | 1120 | 2018-11-19 09:00 | 10d 7h | 1740 | 0 | 0 | 0 | 0 | 1740 | 0 | 100% | Finished | 1120 | 1120
25 | Technical Control | 2018-11-07 10:00 | 2018-11-08 10:00 | 1d |  | 0 | 1000 | 0 | 0 | 1000 | 2018-12-11 13:00 | 1d 3h | 1000 | 0 | 0 | 0 | 0 | 1000 | 0 | 100% | Finished | 1000 | 1000
26 | Placement of people and food | 2018-11-08 13:00 | 2018-11-10 12:00 | 2d | Team[2.00 #5];Volunteers[4.00 #10] | 640 | 0 | 0 | 0 | 640 | 2018-12-12 16:00 | 2d 5h | 840 | 0 | 0 | 0 | 0 | 840 | 0 | 100% | Finished | 640 | 640
27 | Market opening | 2018-11-30 10:00 | 2018-12-30 10:00 | 30d | Team[5.00 #5];Volunteers[10.00 #10] | 24000 | 0 | 0 | 0 | 24000 | 2019-01-07 15:00 | 43d | 34400 | 0 | 0 | 0 | 0 | 34400 | 0 | 100% | Finished | 24000 | 24000
28 | Market closing | 2018-12-30 10:00 | 2018-12-31 12:00 | 1d 2h | Team;Volunteers[10.00 #10] | 200 | 0 | 0 | 0 | 200 | 2019-02-19 15:00 | 2d 3h | 380 | 0 | 0 | 0 | 0 | 380 | 0 | 100% | Finished | 200 | 200
29 | Cut circulation | 2018-12-31 13:00 | 2019-01-01 15:00 | 1d 2h | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2019-02-22 09:00 | 1d 3h | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
30 | Cleaning | 2019-01-01 15:00 | 2019-01-02 17:00 | 1d 2h | Team[5.00 #5];Volunteers[10.00 #10] | 1000 | 0 | 0 | 0 | 1000 | 2019-02-23 13:00 | 2d 1h | 1700 | 0 | 0 | 0 | 0 | 1700 | 0 | 100% | Finished | 1000 | 1000
31 | Uninstallation | 2019-01-01 15:00 | 2019-01-03 15:00 | 2d | Volunteers[4.00 #10] | 0 | 0 | 0 | 0 | 0 | 2019-02-23 13:00 | 2d | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
32 | Opening circulation | 2019-01-03 15:00 | 2019-01-04 15:00 | 1d | Volunteers[5.00 #10] | 0 | 200 | 0 | 0 | 200 | 2019-02-25 14:00 | 1d | 200 | 0 | 0 | 0 | 0 | 200 | 0 | 100% | Finished | 200 | 200
33 | END | 2019-01-04 15:00 | 2019-01-04 15:00 | 0 |  | 0 | 0 | 0 | 0 | 0 | 2019-02-26 14:00 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | Yes
6:00 - 7:00 | No | Sunday | Yes
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | CPI | SPI | p-factor | SV(t) | CPI | CPI threshold | SPI(t) | SPI(t) threshold
30/08/2018 17:00 | 2018-08-26 08:00 | 2018-08-30 17:00 | 4000 | 2711.8645 | 4000 | 2018-08-29 11:00 | -1288.1355 | 67.8% | -1288.1355 | 67.8% | -1d 5h | 67.5% | 100% | 2019-01-07 14:00 | 2019-03-08 11:00 | 2019-06-08 14:00 | 2019-01-06 11:00 | 2019-03-08 11:00 | 2019-06-06 10:00 | 2019-01-06 11:00 | 2019-03-09 09:00 | 2019-06-07 12:00 | 60188.1355 | 86877.4979 | 86877.4979 | 87241.6823 | 126244.3065 | 126781.4784 | 86877.4979 | 86950.0796 | 0.675 | 0.67797 | 0.67797 | 1 | -1.625 | 0.67797 | 1 | 0.675 | 1
04/09/2018 17:00 | 2018-08-30 17:00 | 2018-09-04 17:00 | 4200 | 4200 | 6100 | 2018-09-04 17:00 | 0 | 100% | -1900 | 68.85% | 0 | 100% | 100% | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-03-05 11:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-28 16:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-28 16:00 | 60800 | 85545.2381 | 60800 | 60800 | 85545.2381 | 85545.2381 | 78953.7118 | 78953.7118 | 1 | 0.68852 | 1 | 1 | 0 | 0.68852 | 1 | 1 | 1
09/09/2018 17:00 | 2018-09-04 17:00 | 2018-09-09 17:00 | 4200 | 4200 | 6100 | 2018-09-09 17:00 | 0 | 100% | -1900 | 68.85% | 0 | 100% | 100% | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-03-05 11:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-26 14:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-26 14:00 | 60800 | 85545.2381 | 60800 | 60800 | 85545.2381 | 85545.2381 | 78953.7118 | 78953.7118 | 1 | 0.68852 | 1 | 1 | 0 | 0.68852 | 1 | 1 | 1
14/09/2018 17:00 | 2018-09-09 17:00 | 2018-09-14 17:00 | 4200 | 4200 | 6100 | 2018-09-14 17:00 | 0 | 100% | -1900 | 68.85% | 0 | 100% | 100% | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-03-05 11:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-24 10:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-24 10:00 | 60800 | 85545.2381 | 60800 | 60800 | 85545.2381 | 85545.2381 | 78953.7118 | 78953.7118 | 1 | 0.68852 | 1 | 1 | 0 | 0.68852 | 1 | 1 | 1
19/09/2018 17:00 | 2018-09-14 17:00 | 2018-09-19 17:00 | 4200 | 4200 | 6100 | 2018-09-19 17:00 | 0 | 100% | -1900 | 68.85% | 0 | 100% | 100% | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-03-05 11:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-21 17:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-21 17:00 | 60800 | 85545.2381 | 60800 | 60800 | 85545.2381 | 85545.2381 | 78953.7118 | 78953.7118 | 1 | 0.68852 | 1 | 1 | 0 | 0.68852 | 1 | 1 | 1
24/09/2018 17:00 | 2018-09-19 17:00 | 2018-09-24 17:00 | 4200 | 4200 | 6100 | 2018-09-24 17:00 | 0 | 100% | -1900 | 68.85% | 0 | 100% | 100% | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-03-05 11:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-19 15:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-19 15:00 | 60800 | 85545.2381 | 60800 | 60800 | 85545.2381 | 85545.2381 | 78953.7118 | 78953.7118 | 1 | 0.68852 | 1 | 1 | 0 | 0.68852 | 1 | 1 | 1
29/09/2018 17:00 | 2018-09-24 17:00 | 2018-09-29 17:00 | 4200 | 4200 | 6100 | 2018-09-29 17:00 | 0 | 100% | -1900 | 68.85% | 0 | 100% | 100% | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-03-05 11:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-17 12:00 | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-02-17 12:00 | 60800 | 85545.2381 | 60800 | 60800 | 85545.2381 | 85545.2381 | 78953.7118 | 78953.7118 | 1 | 0.68852 | 1 | 1 | 0 | 0.68852 | 1 | 1 | 1
04/10/2018 17:00 | 2018-09-29 17:00 | 2018-10-04 17:00 | 11840 | 4200 | 6100 | 2018-09-29 17:00 | -7640 | 35.47% | -1900 | 68.85% | -5d | 87.5% | 100% | 2019-01-21 16:00 | 2019-09-01 11:00 | 2020-02-16 11:00 | 2019-01-30 12:00 | 2019-09-01 11:00 | 2020-01-29 11:00 | 2019-01-09 15:00 | 2019-01-23 14:00 | 2019-03-14 14:00 | 60800 | 85545.2381 | 160301.9048 | 68614.2857 | 230059.9093 | 96894.5578 | 94075.273 | 81463.0717 | 0.875 | 0.68852 | 0.35473 | 1 | -5 | 0.68852 | 1 | 0.875 | 1
09/10/2018 17:00 | 2018-10-04 17:00 | 2018-10-09 17:00 | 17600 | 4200 | 6100 | 2018-09-29 17:00 | -13400 | 23.86% | -1900 | 68.85% | -10d | 77.78% | 100% | 2019-02-03 15:00 | 2020-02-29 09:00 | 2020-11-04 16:00 | 2019-02-07 17:00 | 2020-02-29 09:00 | 2020-10-15 12:00 | 2019-01-14 15:00 | 2019-02-11 11:00 | 2019-04-08 14:00 | 60800 | 85545.2381 | 235319.0476 | 76428.5714 | 339013.3787 | 108243.8776 | 97487.9863 | 83537.5967 | 0.77778 | 0.68852 | 0.23864 | 1 | -10 | 0.68852 | 1 | 0.77778 | 1
14/10/2018 17:00 | 2018-10-09 17:00 | 2018-10-14 17:00 | 20000 | 4400 | 6300 | 2018-10-01 10:00 | -15600 | 22% | -1900 | 69.84% | -13d 6h | 72.5% | 100% | 2019-02-08 14:00 | 2020-04-15 16:00 | 2020-12-30 12:00 | 2019-02-12 15:00 | 2020-04-15 16:00 | 2020-12-08 16:00 | 2019-01-18 12:00 | 2019-02-23 15:00 | 2019-04-21 14:00 | 60800 | 84334.0909 | 254027.2727 | 81472.4138 | 361000.4132 | 113933.2288 | 96721.8898 | 83744.457 | 0.725 | 0.69841 | 0.22 | 1 | -13.75 | 0.69841 | 1 | 0.725 | 1
19/10/2018 17:00 | 2018-10-14 17:00 | 2018-10-19 17:00 | 20880 | 9344.6458 | 13980 | 2018-10-03 12:00 | -11535.3542 | 44.75% | -4635.3542 | 66.84% | -16d 4h | 70% | 98.52% | 2019-01-30 12:00 | 2019-06-16 11:00 | 2019-11-09 11:00 | 2019-02-04 09:00 | 2019-06-16 11:00 | 2019-10-13 09:00 | 2019-01-21 10:00 | 2019-03-02 10:00 | 2019-05-07 10:00 | 63535.3542 | 88116.9834 | 124708.1984 | 84773.3631 | 179634.2414 | 119889.9763 | 93363.6007 | 87423.2284 | 0.7 | 0.66843 | 0.44754 | 0.98516 | -16.5 | 0.66843 | 1 | 0.7 | 1
24/10/2018 17:00 | 2018-10-19 17:00 | 2018-10-24 17:00 | 24160 | 14817.5069 | 22780 | 2018-10-06 14:00 | -9342.4931 | 61.33% | -7962.4931 | 65.05% | -18d 3h | 69.38% | 97.15% | 2019-01-25 14:00 | 2019-03-28 16:00 | 2019-07-22 10:00 | 2019-01-27 17:00 | 2019-03-28 16:00 | 2019-06-19 17:00 | 2019-01-23 09:00 | 2019-03-03 16:00 | 2019-05-12 15:00 | 66862.4931 | 90551.1307 | 94656.6689 | 86322.3325 | 133281.0805 | 120468.1163 | 91334.2839 | 89660.9337 | 0.69375 | 0.65046 | 0.61331 | 0.97152 | -18.375 | 0.65046 | 1 | 0.69375 | 1
29/10/2018 17:00 | 2018-10-24 17:00 | 2018-10-29 17:00 | 25760 | 19232.9831 | 29220 | 2018-10-13 11:00 | -6527.0169 | 74.66% | -9987.0169 | 65.82% | -16d 5h | 74.42% | 92.69% | 2019-01-19 11:00 | 2019-02-18 12:00 | 2019-05-21 09:00 | 2019-01-21 10:00 | 2019-02-18 12:00 | 2019-04-17 11:00 | 2019-01-21 11:00 | 2019-02-18 17:00 | 2019-04-18 10:00 | 68887.0169 | 89484.7143 | 82348.6461 | 82519.3508 | 109936.4977 | 110195.8434 | 87908.1536 | 87949.7096 | 0.74423 | 0.65821 | 0.74662 | 0.92694 | -16.625 | 0.65821 | 1 | 0.74423 | 1
03/11/2018 17:00 | 2018-10-29 17:00 | 2018-11-03 17:00 | 30820 | 21470.2022 | 32620 | 2018-10-19 17:00 | -9349.7978 | 69.66% | -11149.7978 | 65.82% | -15d | 78.57% | 94.59% | 2019-01-25 14:00 | 2019-03-03 09:00 | 2019-06-09 11:00 | 2019-01-25 17:00 | 2019-03-03 09:00 | 2019-05-03 17:00 | 2019-01-19 15:00 | 2019-02-09 14:00 | 2019-04-01 11:00 | 70049.7978 | 89487.653 | 86349.6464 | 80257.9245 | 114252.2572 | 104997.0129 | 88831.0669 | 87366.2627 | 0.78571 | 0.65819 | 0.69663 | 0.94594 | -15 | 0.65819 | 1 | 0.78571 | 1
08/11/2018 17:00 | 2018-11-03 17:00 | 2018-11-08 17:00 | 32820 | 23444.9586 | 35540 | 2018-10-23 12:00 | -9375.0414 | 71.43% | -12095.0414 | 65.97% | -16d 4h | 78% | 98.11% | 2019-01-25 15:00 | 2019-02-26 11:00 | 2019-06-01 14:00 | 2019-01-26 09:00 | 2019-02-26 11:00 | 2019-04-23 16:00 | 2019-01-21 10:00 | 2019-02-10 16:00 | 2019-03-31 11:00 | 70995.0414 | 89285.9754 | 85172.6087 | 80995.1812 | 110777.6211 | 104445.0967 | 88409.6473 | 87394.3803 | 0.78 | 0.65968 | 0.71435 | 0.98107 | -16.5 | 0.65968 | 1 | 0.78 | 1
13/11/2018 17:00 | 2018-11-08 17:00 | 2018-11-13 17:00 | 33300 | 24441.9835 | 36720 | 2018-10-25 16:00 | -8858.0165 | 73.4% | -12278.0165 | 66.56% | -19d 1h | 76.09% | 97.46% | 2019-01-24 14:00 | 2019-02-21 12:00 | 2019-05-22 14:00 | 2019-01-25 17:00 | 2019-02-21 12:00 | 2019-04-12 12:00 | 2019-01-23 16:00 | 2019-02-15 09:00 | 2019-04-02 16:00 | 71178.0165 | 88487.4176 | 83665.9424 | 82003.6357 | 107248.4416 | 104751.1032 | 87445.4886 | 87046.2591 | 0.76094 | 0.66563 | 0.73399 | 0.97463 | -19.125 | 0.66563 | 1 | 0.76094 | 1
18/11/2018 17:00 | 2018-11-13 17:00 | 2018-11-18 17:00 | 33300 | 25180 | 37460 | 2018-10-28 09:00 | -8120 | 75.62% | -12280 | 67.22% | -21d 7h | 74.26% | 96.1% | 2019-01-22 16:00 | 2019-02-16 10:00 | 2019-05-12 10:00 | 2019-01-25 12:00 | 2019-02-16 10:00 | 2019-03-31 15:00 | 2019-01-26 14:00 | 2019-02-19 11:00 | 2019-04-05 12:00 | 71180 | 87624.861 | 82053.9635 | 82865.1485 | 103801.9329 | 105008.7237 | 86402.0447 | 86594.726 | 0.74265 | 0.67218 | 0.75616 | 0.96105 | -21.875 | 0.67218 | 1 | 0.74265 | 1
23/11/2018 17:00 | 2018-11-18 17:00 | 2018-11-23 17:00 | 33300 | 25882.069 | 38440 | 2018-10-30 11:00 | -7417.931 | 77.72% | -12557.931 | 67.33% | -24d 5h | 72.64% | 97.54% | 2019-01-21 11:00 | 2019-02-11 12:00 | 2019-05-04 15:00 | 2019-01-24 15:00 | 2019-02-11 12:00 | 2019-03-22 09:00 | 2019-01-29 11:00 | 2019-02-23 11:00 | 2019-04-08 15:00 | 71457.931 | 87478.1689 | 80921.036 | 83894.8955 | 101532.7545 | 105949.525 | 86009.6523 | 86717.0198 | 0.72639 | 0.67331 | 0.77724 | 0.97535 | -24.625 | 0.67331 | 1 | 0.72639 | 1
28/11/2018 17:00 | 2018-11-23 17:00 | 2018-11-28 17:00 | 33300 | 26397.0115 | 39240 | 2018-10-31 10:00 | -6902.9885 | 79.27% | -12842.9885 | 67.27% | -28d 6h | 69.74% | 98.99% | 2019-01-20 10:00 | 2019-02-08 10:00 | 2019-04-30 09:00 | 2019-01-24 12:00 | 2019-02-08 10:00 | 2019-03-14 16:00 | 2019-02-02 12:00 | 2019-03-02 16:00 | 2019-04-17 14:00 | 71742.9885 | 87556.7298 | 80242.7294 | 85848.059 | 100191.8659 | 108524.3673 | 85892.3748 | 87205.0461 | 0.69737 | 0.67271 | 0.7927 | 0.98995 | -28.75 | 0.67271 | 1 | 0.69737 | 1
03/12/2018 17:00 | 2018-11-28 17:00 | 2018-12-03 17:00 | 36300 | 30820 | 43840 | 2018-11-04 10:00 | -5480 | 84.9% | -13020 | 70.3% | -29d 6h | 70.25% | 100% | 2019-01-16 17:00 | 2019-01-28 09:00 | 2019-04-03 15:00 | 2019-01-19 16:00 | 2019-01-28 09:00 | 2019-02-20 12:00 | 2019-02-03 12:00 | 2019-03-01 12:00 | 2019-04-07 12:00 | 71920 | 83782.4789 | 76912.8099 | 83811.5302 | 90884.516 | 100697.6212 | 82189.3436 | 83788.2858 | 0.7025 | 0.70301 | 0.84904 | 1 | -29.75 | 0.70301 | 1 | 0.7025 | 1
08/12/2018 17:00 | 2018-12-03 17:00 | 2018-12-08 17:00 | 40300 | 31305.5172 | 44720 | 2018-11-05 15:00 | -8994.4828 | 77.68% | -13414.4828 | 70% | -33d 2h | 68.33% | 100% | 2019-01-24 16:00 | 2019-02-11 14:00 | 2019-04-25 10:00 | 2019-01-28 09:00 | 2019-02-11 14:00 | 2019-03-11 10:00 | 2019-02-06 17:00 | 2019-03-06 15:00 | 2019-04-13 11:00 | 72314.4828 | 84138.7791 | 80242.737 | 85102.1699 | 95464.3077 | 102406.0182 | 83292.669 | 84327.7623 | 0.68333 | 0.70003 | 0.77681 | 1 | -33.25 | 0.70003 | 1 | 0.68333 | 1
13/12/2018 17:00 | 2018-12-08 17:00 | 2018-12-13 17:00 | 44300 | 32934.2857 | 46560 | 2018-11-09 10:00 | -11365.7143 | 74.34% | -13625.7143 | 70.74% | -34d 6h | 68.41% | 100% | 2019-01-30 09:00 | 2019-02-19 10:00 | 2019-05-03 12:00 | 2019-02-01 17:00 | 2019-02-19 10:00 | 2019-03-18 17:00 | 2019-02-08 12:00 | 2019-03-06 14:00 | 2019-04-09 15:00 | 72525.7143 | 83268.3612 | 81486.555 | 84516.5259 | 95936.5196 | 100220.0629 | 82897.6028 | 83511.3835 | 0.68409 | 0.70735 | 0.74344 | 1 | -34.75 | 0.70735 | 1 | 0.68409 | 1
18/12/2018 17:00 | 2018-12-13 17:00 | 2018-12-18 17:00 | 48300 | 33300 | 47040 | 2018-11-30 10:00 | -15000 | 68.94% | -13740 | 70.79% | -18d 6h | 83.7% | 100% | 2019-02-07 10:00 | 2019-03-05 09:00 | 2019-05-22 17:00 | 2019-02-09 12:00 | 2019-03-05 09:00 | 2019-04-05 12:00 | 2019-01-23 12:00 | 2019-01-30 11:00 | 2019-02-16 16:00 | 72640 | 83202.8829 | 84171.5315 | 77627.013 | 99492.4698 | 90247.6003 | 83392.5484 | 81930.797 | 0.83696 | 0.70791 | 0.68944 | 1 | -18.75 | 0.70791 | 1 | 0.83696 | 1
23/12/2018 17:00 | 2018-12-18 17:00 | 2018-12-23 17:00 | 52300 | 33300 | 47040 | 2018-11-30 10:00 | -19000 | 63.67% | -13740 | 70.79% | -23d 6h | 80.21% | 100% | 2019-02-16 10:00 | 2019-03-20 16:00 | 2019-06-14 10:00 | 2019-02-17 11:00 | 2019-03-20 16:00 | 2019-04-25 15:00 | 2019-01-28 12:00 | 2019-02-06 10:00 | 2019-02-24 12:00 | 72640 | 83202.8829 | 87246.6066 | 78956.8831 | 103836.3596 | 92126.1916 | 83945.2212 | 82265.6479 | 0.80208 | 0.70791 | 0.63671 | 1 | -23.75 | 0.70791 | 1 | 0.80208 | 1
28/12/2018 17:00 | 2018-12-23 17:00 | 2018-12-28 17:00 | 56300 | 33300 | 47040 | 2018-11-30 10:00 | -23000 | 59.15% | -13740 | 70.79% | -28d 6h | 77% | 100% | 2019-02-25 10:00 | 2019-04-05 15:00 | 2019-07-06 14:00 | 2019-02-24 16:00 | 2019-04-05 15:00 | 2019-05-16 09:00 | 2019-02-02 12:00 | 2019-02-13 09:00 | 2019-03-04 09:00 | 72640 | 83202.8829 | 90321.6817 | 80286.7532 | 108180.2494 | 94004.783 | 84432.931 | 82579.4379 | 0.77 | 0.70791 | 0.59147 | 1 | -28.75 | 0.70791 | 1 | 0.77 | 1
02/01/2019 17:00 | 2018-12-28 17:00 | 2019-01-02 17:00 | 58700 | 33300 | 47040 | 2018-11-30 10:00 | -25400 | 56.73% | -13740 | 70.79% | -33d 6h | 74.04% | 100% | 2019-03-02 14:00 | 2019-04-15 10:00 | 2019-07-20 09:00 | 2019-03-01 17:00 | 2019-04-15 10:00 | 2019-05-27 11:00 | 2019-02-07 12:00 | 2019-02-19 17:00 | 2019-03-11 15:00 | 72640 | 83202.8829 | 92166.7267 | 81616.6234 | 110786.5833 | 95883.3743 | 84698.9772 | 82874.0933 | 0.74038 | 0.70791 | 0.56729 | 1 | -33.75 | 0.70791 | 1 | 0.74038 | 1
07/01/2019 17:00 | 2019-01-02 17:00 | 2019-01-07 17:00 | 58900 | 33439.5349 | 47240 | 2018-11-30 11:00 | -25460.4651 | 56.77% | -13800.4651 | 70.79% | -38d 5h | 71.39% | 100% | 2019-03-02 15:00 | 2019-04-15 09:00 | 2019-07-19 16:00 | 2019-03-07 11:00 | 2019-04-20 15:00 | 2019-06-02 10:00 | 2019-02-12 11:00 | 2019-02-26 12:00 | 2019-03-18 17:00 | 72700.4651 | 83207.9755 | 92085.7612 | 82904.4648 | 110593.5653 | 97623.1564 | 84690.7453 | 83146.8608 | 0.71389 | 0.70786 | 0.56773 | 1 | -38.625 | 0.70786 | 1 | 0.71389 | 1
12/01/2019 17:00 | 2019-01-07 17:00 | 2019-01-12 17:00 | 58900 | 36230.2325 | 51240 | 2018-12-03 16:00 | -22669.7675 | 61.51% | -15009.7675 | 70.71% | -40d 1h | 71.34% | 100% | 2019-02-24 12:00 | 2019-03-28 10:00 | 2019-06-24 16:00 | 2019-03-07 16:00 | 2019-04-10 14:00 | 2019-05-16 16:00 | 2019-02-13 16:00 | 2019-02-26 14:00 | 2019-03-17 10:00 | 73909.7675 | 83301.5907 | 88094.5607 | 83017.3962 | 103362.9802 | 96182.405 | 84157.7885 | 83244.3459 | 0.71339 | 0.70707 | 0.61511 | 1 | -40.125 | 0.70707 | 1 | 0.71339 | 1
17/01/2019 17:00 | 2019-01-12 17:00 | 2019-01-17 17:00 | 58900 | 39020.9301 | 55240 | 2018-12-07 11:00 | -19879.0699 | 66.25% | -16219.0699 | 70.64% | -41d 5h | 71.29% | 100% | 2019-02-18 10:00 | 2019-03-12 16:00 | 2019-06-03 12:00 | 2019-03-07 17:00 | 2019-04-01 16:00 | 2019-05-02 14:00 | 2019-02-15 11:00 | 2019-02-26 15:00 | 2019-03-15 11:00 | 75119.0699 | 83381.8156 | 85246.3892 | 83123.5805 | 97718.5605 | 94713.4053 | 83735.959 | 83329.7867 | 0.71293 | 0.70639 | 0.66249 | 1 | -41.625 | 0.70639 | 1 | 0.71293 | 1
22/01/2019 17:00 | 2019-01-17 17:00 | 2019-01-22 17:00 | 58900 | 41811.6277 | 59240 | 2018-12-10 16:00 | -17088.3723 | 70.99% | -17428.3723 | 70.58% | -43d 1h | 71.25% | 100% | 2019-02-11 17:00 | 2019-02-27 14:00 | 2019-05-15 17:00 | 2019-03-07 12:00 | 2019-03-25 10:00 | 2019-04-19 16:00 | 2019-02-16 16:00 | 2019-02-26 16:00 | 2019-03-13 12:00 | 76328.3723 | 83451.3315 | 83312.3738 | 83223.6805 | 93346.4795 | 93220.8161 | 83423.4117 | 83405.4562 | 0.7125 | 0.7058 | 0.70987 | 1 | -43.125 | 0.7058 | 1 | 0.7125 | 1
27/01/2019 17:00 | 2019-01-22 17:00 | 2019-01-27 17:00 | 58900 | 44602.3252 | 63240 | 2018-12-14 11:00 | -14297.6748 | 75.73% | -18637.6748 | 70.53% | -44d 5h | 71.21% | 100% | 2019-02-05 15:00 | 2019-02-15 17:00 | 2019-04-29 14:00 | 2019-03-06 14:00 | 2019-03-18 14:00 | 2019-04-08 12:00 | 2019-02-18 11:00 | 2019-02-26 17:00 | 2019-03-11 12:00 | 77537.6748 | 83512.1483 | 82120.9224 | 83318.2748 | 90010.5669 | 91708.249 | 83217.7395 | 83473.0747 | 0.7121 | 0.70529 | 0.75726 | 1 | -44.625 | 0.70529 | 1 | 0.7121 | 1
01/02/2019 17:00 | 2019-01-27 17:00 | 2019-02-01 17:00 | 58900 | 47393.0228 | 67240 | 2018-12-17 15:00 | -11506.9772 | 80.46% | -19846.9772 | 70.48% | -46d 2h | 71.09% | 100% | 2019-01-30 12:00 | 2019-02-05 15:00 | 2019-04-15 10:00 | 2019-03-05 10:00 | 2019-03-12 16:00 | 2019-03-29 09:00 | 2019-02-19 17:00 | 2019-02-27 11:00 | 2019-03-09 16:00 | 78746.9772 | 83565.8028 | 81540.8594 | 83425.6382 | 87529.6909 | 90203.7666 | 83116.2017 | 83537.576 | 0.71094 | 0.70483 | 0.80464 | 1 | -46.25 | 0.70483 | 1 | 0.71094 | 1
06/02/2019 17:00 | 2019-02-01 17:00 | 2019-02-06 17:00 | 58900 | 50183.7204 | 71240 | 2018-12-21 10:00 | -8716.2796 | 85.2% | -21056.2796 | 70.44% | -47d 6h | 71.06% | 100% | 2019-01-24 10:00 | 2019-01-27 14:00 | 2019-04-02 12:00 | 2019-03-03 11:00 | 2019-03-07 14:00 | 2019-03-19 14:00 | 2019-02-21 12:00 | 2019-02-27 11:00 | 2019-03-07 17:00 | 79956.2796 | 83613.4899 | 81470.1875 | 83505.9798 | 85762.6091 | 88652.5871 | 83115.8727 | 83591.8374 | 0.71061 | 0.70443 | 0.85202 | 1 | -47.75 | 0.70443 | 1 | 0.71061 | 1
11/02/2019 17:00 | 2019-02-06 17:00 | 2019-02-11 17:00 | 58900 | 52974.418 | 75240 | 2018-12-24 15:00 | -5925.582 | 89.94% | -22265.582 | 70.41% | -49d 2h | 71.03% | 100% | 2019-01-17 17:00 | 2019-01-19 12:00 | 2019-03-21 17:00 | 2019-03-01 09:00 | 2019-03-02 17:00 | 2019-03-10 17:00 | 2019-02-22 17:00 | 2019-02-27 12:00 | 2019-03-05 17:00 | 81165.582 | 83656.1527 | 81828.4024 | 83582.4343 | 84597.5619 | 87088.8278 | 83213.7388 | 83641.305 | 0.71029 | 0.70407 | 0.8994 | 1 | -49.25 | 0.70407 | 1 | 0.71029 | 1
16/02/2019 17:00 | 2019-02-11 17:00 | 2019-02-16 17:00 | 58900 | 55765.117 | 79240 | 2018-12-28 10:00 | -3134.883 | 94.68% | -23474.883 | 70.37% | -50d 6h | 71% | 100% | 2019-01-11 15:00 | 2019-01-12 09:00 | 2019-03-11 15:00 | 2019-02-26 11:00 | 2019-02-26 16:00 | 2019-03-02 17:00 | 2019-02-24 12:00 | 2019-02-27 14:00 | 2019-03-03 17:00 | 82374.883 | 83694.5433 | 82551.1131 | 83655.3282 | 83944.9593 | 85514.0047 | 83406.7609 | 83686.6447 | 0.71 | 0.70375 | 0.94678 | 1 | -50.75 | 0.70375 | 1 | 0.71 | 1
21/02/2019 17:00 | 2019-02-16 17:00 | 2019-02-21 17:00 | 58900 | 57489.4737 | 81800 | 2018-12-31 11:00 | -1410.5263 | 97.61% | -24310.5263 | 70.28% | -52d 5h | 70.76% | 100% | 2019-01-07 16:00 | 2019-01-07 17:00 | 2019-03-05 17:00 | 2019-02-26 10:00 | 2019-02-26 11:00 | 2019-02-28 10:00 | 2019-02-26 11:00 | 2019-02-28 09:00 | 2019-03-02 15:00 | 83210.5263 | 83806.9944 | 83245.1341 | 83793.2855 | 83856.2368 | 84636.1844 | 83662.1924 | 83804.2376 | 0.70764 | 0.70281 | 0.97605 | 1 | -52.625 | 0.70281 | 1 | 0.70764 | 1
26/02/2019 17:00 | 2019-02-21 17:00 | 2019-02-26 17:00 | 58900 | 58900 | 83920 | 2019-01-04 15:00 | 0 | 100% | -25020 | 70.19% | -53d 2h | 71.22% | 100% | 2019-01-04 15:00 | 2019-01-04 15:00 | 2019-03-01 15:00 | 2019-02-26 17:00 | 2019-02-26 17:00 | 2019-02-26 17:00 | 2019-02-26 17:00 | 2019-02-26 17:00 | 2019-02-26 17:00 | 83920 | 83920 | 83920 | 83920 | 83920 | 83920 | 83920 | 83920 | 0.71216 | 0.70186 | 1 | 1 | -53.25 | 0.70186 | 1 | 0.71216 | 1