## Baseline Schedule
General |  |  | Relations |  | Baseline |  |  | Resource Demand |  | Baseline Costs
ID | Name | WBS | Predecessors | Successors | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Baseline duration (in calendar days)
0 | PROJECT FUEL TANK FILTER | 1 |  |  | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 | 711.375
1 | Research &amp; pre-design study P87 | 1.1 |  | FS10;FS11 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 311.375
2 | Research &amp; pre-design study P84 /P1UO | 1.2 |  | FS10;FS11 | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 290.375
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 1.3 |  | FS10;FS11 | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 39.375
18 | P84/P1UO | 1.4 |  |  | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 | 407.375
4 | Instal blow mold tool diesel | 1.4.1 |  | FS12;FS14 | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 372.375
5 | Instal welding line P84 | 1.4.2 |  | FS12;FS14 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 309.375
6 | Assembly line Sochaux | 1.4.3 |  | FS12;FS14 | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 337.375
19 | P87 | 1.5 |  |  | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 | 414.375
7 | Blow mold tool diesel | 1.5.1 |  | FS12;FS14 | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 349.375
8 | Instal welding line P87 | 1.5.2 |  | FS12;FS14 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 281.375
9 | Assembly line Rennes | 1.5.3 |  | FS12;FS14 | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 | 344.375
10 | Visual Design &amp; Engineer P84/P1UO | 1.6 | 1FS;2FS;3FS | FS12 | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 376.375
11 | Visual Design &amp; Engineer P87 | 1.7 | 1FS;2FS;3FS | FS14 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 359.375
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 1.8 | 4FS;5FS;6FS;7FS;8FS;9FS;10FS | FS13 | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 | 21.375
13 | PRSEL validation P84/P1UO | 1.9 | 12FS | FS15 | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375
14 | Blow mold &amp; Welding line equipment for P87 | 1.10 | 4FS;5FS;6FS;7FS;8FS;9FS;11FS | FS15 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 | 36.375
15 | PRSEL validation P87 | 1.11 | 13FS;14FS |  | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 0.375

## Resources
General |  |  |  | Resource Cost |  | Resource Demand
ID | Name | Type | Availability | Cost/Use | Cost/Unit | Assigned To | Total Cost

## Risk Analysis
General |  | Baseline | Activity Duration Distribution Profiles
ID | Name | Duration | Description | Optimistic | Most Probable | Pessimistic
0 | PROJECT FUEL TANK FILTER | 4080h
1 | Research &amp; pre-design study P87 | 1792h | standard - no risk | 99 | 100 | 101
2 | Research &amp; pre-design study P84 /P1UO | 1672h | standard - no risk | 99 | 100 | 101
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 240h | standard - no risk | 99 | 100 | 101
18 | P84/P1UO | 2336h
4 | Instal blow mold tool diesel | 2136h | standard - no risk | 99 | 100 | 101
5 | Instal welding line P84 | 1776h | standard - no risk | 99 | 100 | 101
6 | Assembly line Sochaux | 1936h | standard - no risk | 99 | 100 | 101
19 | P87 | 2376h
7 | Blow mold tool diesel | 2000h | standard - no risk | 99 | 100 | 101
8 | Instal welding line P87 | 1616h | standard - no risk | 99 | 100 | 101
9 | Assembly line Rennes | 1976h | standard - no risk | 99 | 100 | 101
10 | Visual Design &amp; Engineer P84/P1UO | 2152h | standard - no risk | 99 | 100 | 101
11 | Visual Design &amp; Engineer P87 | 2064h | standard - no risk | 99 | 100 | 101
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 128h | standard - no risk | 99 | 100 | 101
13 | PRSEL validation P84/P1UO | 8h | standard - no risk | 99 | 100 | 101
14 | Blow mold &amp; Welding line equipment for P87 | 216h | standard - no risk | 99 | 100 | 101
15 | PRSEL validation P87 | 8h | standard - no risk | 99 | 100 | 101

## TP1
| TP Status Date | 2016-10-20 17:00 |  | TP Name | TP1
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 119d | [5 empty] | 268491.5716 |  | 18.12% |  | 263831.5789 | 249628.1638
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 119d | 116875 | 76975.4464 | 78d 3h | 19211.0287 | 0 | 136086.0287 | 76975.4464 | 60.29% | Started | 132631.5789 | 116875
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 104d | 125894.7368 | 188842.1053 | 156d | -21294.7368 | 0 | 104600 | 188842.1053 | 40% | Started | 101200 | 125894.7368
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 |  | 0 | 0 | 70000 | 30d | 0 | 0 | 0 | 70000 | 0% | Not Started | 0 | 0
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 3258.427
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 |  | 0 | 0 | 145000 | 267d | 0 | 0 | 0 | 145000 | 0% | Not Started | 0 | 3258.427
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 |  | 0 | 0 | 5000 | 222d | 0 | 0 | 0 | 5000 | 0% | Not Started | 0 | 0
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 |  | 0 | 0 | 95000 | 242d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 0
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 6d | [5 empty] | 27805.5429 |  | 12.82% |  | 30000 | 3600
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 6d | 3600 | 14400 | 24d | 24205.5429 | 0 | 27805.5429 | 14400 | 20% | Started | 30000 | 3600
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 |  | 0 | 0 | 10000 | 202d | 0 | 0 | 0 | 10000 | 0% | Not Started | 0 | 0
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 |  | 0 | 0 | 74000 | 247d | 0 | 0 | 0 | 74000 | 0% | Not Started | 0 | 0
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 |  | 0 | 0 | 17000 | 269d | 0 | 0 | 0 | 17000 | 0% | Not Started | 0 | 0
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 |  | 0 | 0 | 19000 | 258d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 |  | 0 | 0 | 199000 | 16d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 |  | 0 | 0 | 199000 | 27d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP2
| TP Status Date | 2017-01-10 17:00 |  | TP Name | TP2
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 177d | [5 empty] | 424560.2399 |  | 28.73% |  | 418322.173 | 523799.6876
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 177d | 173839.2857 | 61261.1607 | 62d 3h | -6971.8934 | 0 | 166867.3923 | 61261.1607 | 73.92% | Started | 162631.5789 | 173839.2857
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 162d | 196105.2632 | 65368.4211 | 54d | 19.7368 | 0 | 196125 | 65368.4211 | 75% | Started | 189750 | 196105.2632
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 42d | 98000 | 98000 | 42d | -64930 | 0 | 33070 | 98000 | 50% | Started | 35000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 0 | [5 empty] | 0 |  | 0% |  | 0 | 40567.7374
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 |  | 0 | 0 | 145000 | 267d | 0 | 0 | 0 | 145000 | 0% | Not Started | 0 | 34756.5543
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 |  | 0 | 0 | 5000 | 222d | 0 | 0 | 0 | 5000 | 0.4505% | Started | 0 | 315.3153
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 |  | 0 | 0 | 95000 | 242d | 0 | 0 | 0 | 95000 | 0% | Not Started | 0 | 5495.8678
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 64d | [5 empty] | 28497.8475 |  | 13.22% |  | 30940.5941 | 43287.4013
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 64d | 38400 | 153600 | 256d | -10594.4571 | 0 | 27805.5429 | 153600 | 20% | Started | 30000 | 38400
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 14d | 693.0693 | 6676.9802 | 134d 7h | -0.76473 | 0 | 692.3046 | 6676.9802 | 9.406% | Started | 940.5941 | 693.0693
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 |  | 0 | 0 | 74000 | 247d | 0 | 0 | 0 | 74000 | 0% | Not Started | 0 | 4194.332
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 |  | 0 | 0 | 17000 | 269d | 0 | 0 | 0 | 17000 | 0% | Not Started | 0 | 0
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 |  | 0 | 0 | 19000 | 258d | 0 | 0 | 0 | 19000 | 0% | Not Started | 0 | 0
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 |  | 0 | 0 | 199000 | 16d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 |  | 0 | 0 | 199000 | 27d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP3
| TP Status Date | 2017-04-19 17:00 |  | TP Name | TP3
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 248d | [5 empty] | 535564.2092 |  | 36.14% |  | 526138.5674 | 765480.8247
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 248d | 243571.4286 | 49843.75 | 50d 6h | -56183.1271 | 0 | 187388.3014 | 49843.75 | 83.01% | Started | 182631.5789 | 220000
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 233d | 282052.6316 | 70513.1579 | 58d 2h | -72852.6316 | 0 | 209200 | 70513.1579 | 80% | Started | 202400 | 253000
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 113d | 263666.6667 | 263666.6667 | 113d | -230596.6667 | 0 | 33070 | 263666.6667 | 50% | Started | 35000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 72d | [5 empty] | 40746.2142 |  | 14.61% |  | 35782.3298 | 108596.7898
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 72d | 39101.1236 | 183014.9813 | 337d | -9489.023 | 0 | 29612.1006 | 183014.9813 | 17.6% | Started | 25524.3446 | 73314.6067
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 72d | 1621.6216 | 3378.3784 | 150d | -169.3459 | 0 | 1452.2757 | 3378.3784 | 32.43% | Started | 1621.6216 | 1914.4144
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 72d | 28264.4628 | 282644.6281 | 720d | -18582.6249 | 0 | 9681.8379 | 282644.6281 | 9.091% | Started | 8636.3636 | 33367.7686
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 135d | [5 empty] | 58890.4233 |  | 27.55% |  | 64455.4455 | 110673.5078
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 135d | 81000 | 121500 | 202d 4h | -25388.9141 | 0 | 55611.0859 | 121500 | 40% | Started | 60000 | 81000
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 85d | 4207.9208 | 5235.1485 | 105d 6h | -928.5833 | 0 | 3279.3375 | 5235.1485 | 44.55% | Started | 4455.4455 | 4207.9208
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 |  | 0 | 0 | 74000 | 247d | 0 | 0 | 0 | 74000 | 0% | Not Started | 0 | 25465.587
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 24d | 1516.7286 | 6880.5762 | 108d 7h | 2348.8207 | 0 | 3865.5493 | 6880.5762 | 18.06% | Started | 3070.7635 | 1516.7286
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 23d | 1693.7984 | 9803.7791 | 133d 1h | 709.9225 | 0 | 2403.7209 | 9803.7791 | 14.73% | Started | 2798.4496 | 1693.7984
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 |  | 0 | 0 | 199000 | 16d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 |  | 0 | 0 | 199000 | 27d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP4
| TP Status Date | 2017-07-04 17:00 |  | TP Name | TP4
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 302d | [5 empty] | 724799.3526 |  | 48.65% |  | 708316.4004 | 875862.0193
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 302d | 296607.1429 | 0 | 0 | -70877.1429 | 0 | 225730 | 0 | 100% | Finished | 220000 | 220000
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 287d | 347421.0526 | 0 | 0 | -85921.0526 | 0 | 261500 | 0 | 100% | Finished | 253000 | 253000
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 167d | 389666.6667 | 389666.6667 | 167d | -356596.6667 | 0 | 33070 | 389666.6667 | 50% | Started | 35000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 126d | [5 empty] | 99622.3456 |  | 35.72% |  | 87522.7358 | 160337.1958
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 126d | 68426.9663 | 112483.6142 | 207d 1h | -4792.4522 | 0 | 63634.5141 | 112483.6142 | 37.83% | Started | 54850.1873 | 102640.4494
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 126d | 2837.8378 | 2162.1622 | 96d | -296.3554 | 0 | 2541.4824 | 2162.1622 | 56.76% | Started | 2837.8378 | 3130.6306
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 126d | 49462.8099 | 108052.686 | 275d 2h | -16016.4609 | 0 | 33446.3491 | 108052.686 | 31.4% | Started | 29834.7107 | 54566.1157
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 189d | [5 empty] | 90888.0122 |  | 42.53% |  | 99528.7129 | 161924.9128
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 189d | 113400 | 70725 | 117d 7h | -27758.9278 | 0 | 85641.0722 | 70725 | 61.6% | Started | 92400 | 113400
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 139d | 6881.1881 | 2772.2772 | 56d | -1634.2482 | 0 | 5246.94 | 2772.2772 | 71.29% | Started | 7128.7129 | 6881.1881
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 |  | 0 | 0 | 74000 | 247d | 0 | 0 | 0 | 74000 | 0% | Not Started | 0 | 41643.7247
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 78d | 4929.368 | 7986.5242 | 126d 3h | 3240.0919 | 0 | 8169.46 | 7986.5242 | 38.18% | Started | 6489.7579 | 4929.368
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 77d | 5670.5426 | 10227.2287 | 138d 7h | 148.9922 | 0 | 5819.5349 | 10227.2287 | 35.66% | Started | 6775.1938 | 5670.5426
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 |  | 0 | 0 | 199000 | 16d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 |  | 0 | 0 | 199000 | 27d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP5
| TP Status Date | 2017-09-21 17:00 |  | TP Name | TP5
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 359d | [5 empty] | 932866.585 |  | 62.03% |  | 903141.5647 | 992375.5024
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 302d | 296607.1429 | 0 | 0 | -70877.1429 | 0 | 225730 | 0 | 100% | Finished | 220000 | 220000
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 287d | 347421.0526 | 0 | 0 | -85921.0526 | 0 | 261500 | 0 | 100% | Finished | 253000 | 253000
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 224d | 522666.6667 | 522666.6667 | 224d | -489596.6667 | 0 | 33070 | 522666.6667 | 50% | Started | 35000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 183d | [5 empty] | 223660.137 |  | 79.86% |  | 195650 | 214952.0688
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 183d | 99382.0225 | 5227.0599 | 9d 5h | 60428.8141 | 0 | 159810.8366 | 5227.0599 | 95% | Started | 137750 | 133595.5056
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 183d | 4121.6216 | 261.8243 | 11d 5h | 87.5574 | 0 | 4209.179 | 261.8243 | 94% | Started | 4700 | 4414.4144
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 183d | 71838.843 | 56430.7851 | 143d 6h | -12198.7216 | 0 | 59640.1214 | 56430.7851 | 56% | Started | 53200 | 76942.1488
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 246d | [5 empty] | 166768.8551 |  | 76.25% |  | 178420 | 216023.6181
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 246d | 147600 | 6150 | 10d 2h | -14133.3939 | 0 | 133466.6061 | 6150 | 96% | Started | 144000 | 147600
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 196d | 9702.9703 | 0 | 0 | -2342.6795 | 0 | 7360.2908 | 0 | 100% | Finished | 10000 | 9702.9703
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 | 2017-07-04 08:00 | 58d | 17376.5182 | 35277.3279 | 117d 6h | 8565.44 | 0 | 25941.9582 | 35277.3279 | 33% | Started | 24420 | 58720.6478
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 135d | 8531.5985 | 5829.9257 | 92d 2h | 4180.8782 | 0 | 12712.4767 | 5829.9257 | 59.4% | Started | 10098.6965 | 8531.5985
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 134d | 9868.2171 | 7217.0543 | 98d | -443.1008 | 0 | 9425.1163 | 7217.0543 | 57.75% | Started | 10972.8682 | 9868.2171
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 |  | 0 | 0 | 199000 | 16d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 |  | 0 | 0 | 199000 | 27d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP6
| TP Status Date | 2017-11-14 17:00 |  | TP Name | TP6
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 397d | [5 empty] | 969034.1487 |  | 64.51% |  | 939204.7183 | 1038564.5195
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 302d | 296607.1429 | 0 | 0 | -70877.1429 | 0 | 225730 | 0 | 100% | Finished | 220000 | 220000
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 287d | 347421.0526 | 0 | 0 | -85921.0526 | 0 | 261500 | 0 | 100% | Finished | 253000 | 253000
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 262d | 611333.3333 | 611333.3333 | 262d | -578263.3333 | 0 | 33070 | 611333.3333 | 50% | Started | 35000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 221d | [5 empty] | 218761.127 |  | 78.45% |  | 192200 | 241859.5041
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 221d | 120018.7266 | 33874.0637 | 62d 3h | 11194.3813 | 0 | 131213.1079 | 33874.0637 | 78% | Started | 113100 | 145000
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 221d | 4977.4775 | 0 | 0 | -499.6275 | 0 | 4477.85 | 0 | 100% | Finished | 5000 | 5000
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 221d | 86756.1983 | 24486.0537 | 62d 3h | -3686.0293 | 0 | 83070.1691 | 24486.0537 | 78% | Started | 74100 | 91859.5041
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 284d | [5 empty] | 202403.0299 |  | 90.91% |  | 212728.7449 | 230105.2632
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 284d | 170400 | 0 | 0 | -31372.2853 | 0 | 139027.7147 | 0 | 100% | Finished | 150000 | 150000
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 234d | 11584.1584 | 0 | 0 | -4223.8676 | 0 | 7360.2908 | 0 | 100% | Finished | 10000 | 10000
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 | 2017-07-04 08:00 | 96d | 28761.1336 | 11609.3117 | 38d 6h | 27253.8909 | 0 | 56015.0245 | 11609.3117 | 71.26% | Started | 52728.7449 | 70105.2632
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 173d | 10933.0855 | 3934.0149 | 62d 2h | 4808.0691 | 0 | 15741.1546 | 3934.0149 | 73.56% | Started | 12504.6555 | 10933.0855
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 172d | 12666.6667 | 4805.2326 | 65d 2h | -837.8295 | 0 | 11828.8372 | 4805.2326 | 72.48% | Started | 13771.3178 | 12666.6667
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 |  | 0 | 0 | 199000 | 16d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 |  | 0 | 0 | 199000 | 27d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP7
| TP Status Date | 2018-02-20 17:00 |  | TP Name | TP7
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 467d | [5 empty] | 1085156.4 |  | 72% |  | 1048260 | 1055178.5827
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 302d | 296607.1429 | 0 | 0 | -70877.1429 | 0 | 225730 | 0 | 100% | Finished | 220000 | 220000
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 287d | 347421.0526 | 0 | 0 | -85921.0526 | 0 | 261500 | 0 | 100% | Finished | 253000 | 253000
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 332d | 774666.6667 | 0 | 0 | -708526.6667 | 0 | 66140 | 0 | 100% | Finished | 70000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 291d | [5 empty] | 279200 |  | 100% |  | 245000 | 245000
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 291d | 158033.7079 | 0 | 0 | 10188.2254 | 0 | 168221.9332 | 0 | 100% | Finished | 145000 | 145000
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 221d | 4977.4775 | 0 | 0 | -499.6275 | 0 | 4477.85 | 0 | 100% | Finished | 5000 | 5000
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 291d | 114235.5372 | 0 | 0 | -7735.3205 | 0 | 106500.2167 | 0 | 100% | Finished | 95000 | 95000
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 354d | [5 empty] | 225000 |  | 100% |  | 234000 | 234000
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 284d | 170400 | 0 | 0 | -31372.2853 | 0 | 139027.7147 | 0 | 100% | Finished | 150000 | 150000
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 234d | 11584.1584 | 0 | 0 | -4223.8676 | 0 | 7360.2908 | 0 | 100% | Finished | 10000 | 10000
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 | 2017-07-04 08:00 | 166d | 49732.7935 | 0 | 0 | 28879.201 | 0 | 78611.9945 | 0 | 100% | Finished | 74000 | 74000
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 0 | 0 | 17000 | 269d | 15836 | 0 | 15836 | 17000 | 74% | Started | 12580 | 15356.8773
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 0 | 0 | 19000 | 258d | 11750.4 | 0 | 11750.4 | 19000 | 72% | Started | 13680 | 17821.7054
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 |  | 0 | 0 | 199000 | 16d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 |  | 0 | 0 | 199000 | 27d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP8
| TP Status Date | 2018-03-15 17:00 |  | TP Name | TP8
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 484d | [5 empty] | 1085156.4 |  | 72% |  | 1048260 | 1064801.5971
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 302d | 296607.1429 | 0 | 0 | -70877.1429 | 0 | 225730 | 0 | 100% | Finished | 220000 | 220000
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 287d | 347421.0526 | 0 | 0 | -85921.0526 | 0 | 261500 | 0 | 100% | Finished | 253000 | 253000
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 332d | 774666.6667 | 0 | 0 | -708526.6667 | 0 | 66140 | 0 | 100% | Finished | 70000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 291d | [5 empty] | 279200 |  | 100% |  | 245000 | 245000
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 291d | 158033.7079 | 0 | 0 | 10188.2254 | 0 | 168221.9332 | 0 | 100% | Finished | 145000 | 145000
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 221d | 4977.4775 | 0 | 0 | -499.6275 | 0 | 4477.85 | 0 | 100% | Finished | 5000 | 5000
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 291d | 114235.5372 | 0 | 0 | -7735.3205 | 0 | 106500.2167 | 0 | 100% | Finished | 95000 | 95000
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 354d | [5 empty] | 225000 |  | 100% |  | 234000 | 234000
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 284d | 170400 | 0 | 0 | -31372.2853 | 0 | 139027.7147 | 0 | 100% | Finished | 150000 | 150000
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 234d | 11584.1584 | 0 | 0 | -4223.8676 | 0 | 7360.2908 | 0 | 100% | Finished | 10000 | 10000
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 | 2017-07-04 08:00 | 166d | 49732.7935 | 0 | 0 | 28879.201 | 0 | 78611.9945 | 0 | 100% | Finished | 74000 | 74000
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 260d | 16431.2268 | 5774.6283 | 91d 3h | -595.2268 | 0 | 15836 | 5774.6283 | 74% | Started | 12580 | 16431.2268
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 259d | 19073.6434 | 7419.5736 | 100d 6h | -7323.2434 | 0 | 11750.4 | 7419.5736 | 72% | Started | 13680 | 19000
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 |  | 0 | 0 | 199000 | 16d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 0
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 |  | 0 | 0 | 199000 | 27d | 0 | 0 | 0 | 199000 | 0% | Not Started | 0 | 7370.3704
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP9
| TP Status Date | 2018-04-05 17:00 |  | TP Name | TP9
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 499d | [5 empty] | 1209390 |  | 80.87% |  | 1177400 | 1250550.9259
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 302d | 296607.1429 | 0 | 0 | -70877.1429 | 0 | 225730 | 0 | 100% | Finished | 220000 | 220000
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 287d | 347421.0526 | 0 | 0 | -85921.0526 | 0 | 261500 | 0 | 100% | Finished | 253000 | 253000
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 332d | 774666.6667 | 0 | 0 | -708526.6667 | 0 | 66140 | 0 | 100% | Finished | 70000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 291d | [5 empty] | 279200 |  | 100% |  | 245000 | 245000
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 291d | 158033.7079 | 0 | 0 | 10188.2254 | 0 | 168221.9332 | 0 | 100% | Finished | 145000 | 145000
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 221d | 4977.4775 | 0 | 0 | -499.6275 | 0 | 4477.85 | 0 | 100% | Finished | 5000 | 5000
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 291d | 114235.5372 | 0 | 0 | -7735.3205 | 0 | 106500.2167 | 0 | 100% | Finished | 95000 | 95000
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 354d | [5 empty] | 225000 |  | 100% |  | 234000 | 234000
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 284d | 170400 | 0 | 0 | -31372.2853 | 0 | 139027.7147 | 0 | 100% | Finished | 150000 | 150000
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 234d | 11584.1584 | 0 | 0 | -4223.8676 | 0 | 7360.2908 | 0 | 100% | Finished | 10000 | 10000
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 | 2017-07-04 08:00 | 166d | 49732.7935 | 0 | 0 | 28879.201 | 0 | 78611.9945 | 0 | 100% | Finished | 74000 | 74000
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 275d | 17379.1822 | 0 | 0 | 4020.8178 | 0 | 21400 | 0 | 100% | Finished | 17000 | 17000
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 274d | 20178.2946 | 0 | 0 | -3858.2946 | 0 | 16320 | 0 | 100% | Finished | 19000 | 19000
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 | 2018-03-29 08:00 | 6d | 74625 | 671625 | 54d | -55525 | 0 | 19100 | 671625 | 10% | Started | 19900 | 74625
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 | 2018-03-15 08:00 | 16d | 117925.9259 | 117925.9259 | 16d | -22925.9259 | 0 | 95000 | 117925.9259 | 50% | Started | 99500 | 117925.9259
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 0% | Not Started | 0 | 0

## TP10
| TP Status Date | 2018-04-28 17:00 |  | TP Name | TP10
General |  | Baseline |  |  | Resource Demand |  | Baseline Costs |  |  |  | Tracking
ID | Name | Baseline Start | Baseline End | Duration | Resource Demand | Resource Cost | Fixed Cost | Cost/Hour | Variable Cost | Total Cost | Actual Start | Actual Duration | PAC | PRC | Remaining Duration | PAC Dev | PRC Dev | Actual Cost | Remaining Cost | Percentage Completed | Tracking | Earned Value (EV) | Planned Value (PV)
0 | PROJECT FUEL TANK FILTER | 2016-05-09 08:00 | 2018-04-20 17:00 | 510d |  |  | 0 |  |  | 1456000 |  | 515d | [5 empty] | 1476290 |  | 100% |  | 1456000 | 1456000
1 | Research &amp; pre-design study P87 | 2016-05-09 08:00 | 2017-03-16 17:00 | 224d |  | 0 | 0 | 122.7679 | 220000 | 220000 | 2016-05-09 08:00 | 302d | 296607.1429 | 0 | 0 | -70877.1429 | 0 | 225730 | 0 | 100% | Finished | 220000 | 220000
2 | Research &amp; pre-design study P84 /P1UO | 2016-05-30 08:00 | 2017-03-16 17:00 | 209d |  | 0 | 0 | 151.3158 | 253000 | 253000 | 2016-05-30 08:00 | 287d | 347421.0526 | 0 | 0 | -85921.0526 | 0 | 261500 | 0 | 100% | Finished | 253000 | 253000
3 | Echange documentaire PSA (Responsibility matrix, CD price, Fete 43, 45 and 46) | 2016-11-14 08:00 | 2016-12-23 17:00 | 30d |  | 0 | 0 | 291.6667 | 70000 | 70000 | 2016-11-14 08:00 | 332d | 774666.6667 | 0 | 0 | -708526.6667 | 0 | 66140 | 0 | 100% | Finished | 70000 | 70000
18 | P84/P1UO | 2016-10-13 08:00 | 2017-11-24 17:00 | 292d |  |  | 0 |  |  | 245000 |  | 291d | [5 empty] | 279200 |  | 100% |  | 245000 | 245000
4 | Instal blow mold tool diesel | 2016-10-13 08:00 | 2017-10-20 17:00 | 267d |  | 0 | 0 | 67.8839 | 145000 | 145000 | 2017-01-10 08:00 | 291d | 158033.7079 | 0 | 0 | 10188.2254 | 0 | 168221.9332 | 0 | 100% | Finished | 145000 | 145000
5 | Instal welding line P84 | 2016-12-22 08:00 | 2017-10-27 17:00 | 222d |  | 0 | 0 | 2.8153 | 5000 | 5000 | 2017-01-10 08:00 | 221d | 4977.4775 | 0 | 0 | -499.6275 | 0 | 4477.85 | 0 | 100% | Finished | 5000 | 5000
6 | Assembly line Sochaux | 2016-12-22 08:00 | 2017-11-24 17:00 | 242d |  | 0 | 0 | 49.0702 | 95000 | 95000 | 2017-01-10 08:00 | 291d | 114235.5372 | 0 | 0 | -7735.3205 | 0 | 106500.2167 | 0 | 100% | Finished | 95000 | 95000
19 | P87 | 2016-10-13 08:00 | 2017-12-01 17:00 | 297d |  |  | 0 |  |  | 234000 |  | 354d | [5 empty] | 225000 |  | 100% |  | 234000 | 234000
7 | Blow mold tool diesel | 2016-10-13 08:00 | 2017-09-27 17:00 | 250d |  | 0 | 0 | 75 | 150000 | 150000 | 2016-10-13 08:00 | 284d | 170400 | 0 | 0 | -31372.2853 | 0 | 139027.7147 | 0 | 100% | Finished | 150000 | 150000
8 | Instal welding line P87 | 2016-12-22 08:00 | 2017-09-29 17:00 | 202d |  | 0 | 0 | 6.1881 | 10000 | 10000 | 2016-12-22 08:00 | 234d | 11584.1584 | 0 | 0 | -4223.8676 | 0 | 7360.2908 | 0 | 100% | Finished | 10000 | 10000
9 | Assembly line Rennes | 2016-12-22 08:00 | 2017-12-01 17:00 | 247d |  | 0 | 0 | 37.4494 | 74000 | 74000 | 2017-07-04 08:00 | 166d | 49732.7935 | 0 | 0 | 28879.201 | 0 | 78611.9945 | 0 | 100% | Finished | 74000 | 74000
10 | Visual Design &amp; Engineer P84/P1UO | 2017-03-17 08:00 | 2018-03-28 17:00 | 269d |  | 0 | 0 | 7.8996 | 17000 | 17000 | 2017-03-17 08:00 | 275d | 17379.1822 | 0 | 0 | 4020.8178 | 0 | 21400 | 0 | 100% | Finished | 17000 | 17000
11 | Visual Design &amp; Engineer P87 | 2017-03-20 08:00 | 2018-03-14 17:00 | 258d |  | 0 | 0 | 9.2054 | 19000 | 19000 | 2017-03-20 08:00 | 274d | 20178.2946 | 0 | 0 | -3858.2946 | 0 | 16320 | 0 | 100% | Finished | 19000 | 19000
12 | Blow mold &amp; Welding line equipment for P84/P1UO | 2018-03-29 08:00 | 2018-04-19 17:00 | 16d |  | 0 | 0 | 1554.6875 | 199000 | 199000 | 2018-03-29 08:00 | 6d | 74625 | 0 | 0 | 116375 | 0 | 191000 | 0 | 100% | Finished | 199000 | 199000
13 | PRSEL validation P84/P1UO | 2018-04-19 08:00 | 2018-04-19 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-04-28 | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0
14 | Blow mold &amp; Welding line equipment for P87 | 2018-03-15 08:00 | 2018-04-20 17:00 | 27d |  | 0 | 0 | 921.2963 | 199000 | 199000 | 2018-03-15 08:00 | 16d | 117925.9259 | 0 | 0 | 72074.0741 | 0 | 190000 | 0 | 100% | Finished | 199000 | 199000
15 | PRSEL validation P87 | 2018-04-20 08:00 | 2018-04-20 17:00 | 1d |  | 0 | 0 | 0 | 0 | 0 | 2018-04-28 | 0 | 0 | 0 | 1d | 0 | 0 | 0 | 0 | 100% | Finished | 0 | 0

## Agenda
Working Hours |  | Working Days |  | Holidays (Optional)
0:00 - 1:00 | No | Monday | Yes
1:00 - 2:00 | No | Tuesday | Yes
2:00 - 3:00 | No | Wednesday | Yes
3:00 - 4:00 | No | Thursday | Yes
4:00 - 5:00 | No | Friday | Yes
5:00 - 6:00 | No | Saturday | No
6:00 - 7:00 | No | Sunday | No
7:00 - 8:00 | No
8:00 - 9:00 | Yes
9:00 - 10:00 | Yes
10:00 - 11:00 | Yes
11:00 - 12:00 | Yes
12:00 - 13:00 | No
13:00 - 14:00 | Yes
14:00 - 15:00 | Yes
15:00 - 16:00 | Yes
16:00 - 17:00 | Yes
17:00 - 18:00 | No
18:00 - 19:00 | No
19:00 - 20:00 | No
20:00 - 21:00 | No
21:00 - 22:00 | No
22:00 - 23:00 | No
23:00 - 0:00 | No
Generated by PMConverter v1.1.3

## Tracking Overview
General |  |  | EVM Performance Measures |  |  |  | EVM Forecasting
Name | Start Tracking Period | Status date | Planned Value (PV) | Earned Value (EV) | Actual Cost (AC) | Earned Schedule (ES) | Schedule Variance (SV) | Schedule Performance Index (SPI) | Cost Variance (CV) | Cost Performance Index (CPI) | Schedule Variance (SV(t)) | Schedule Performance Index (SPI(t)) | p-factor | EAC(t)-PV (PF=1) | EAC(t)-PV (PF=SPI) | EAC(t)-PV (PF=SCI) | EAC(t)-ED (PF=1) | EAC(t)-ED (PF=SPI) | EAC(t)-ED (PF=SPI) | EAC(t)-ES (PF=1) | EAC(t)-ES (PF=SPI(t)) | EAC(t)-ES (PF=SCI(t)) | EAC (PF=1) | EAC (PF=CPI) | EAC (PF=SPI) | EAC (PF=SPI(t)) | EAC (PF=SCI) | EAC (PF=SCI(t)) | EAC (PF=0.8*CPI+0.2*SPI) | EAC (PF=0.8*CPI+0.2*SPI(t)) | SPI(t) | SPI | p-factor
TP1 | 2016-05-09 08:00 | 2016-10-20 17:00 | 249628.1638 | 263831.5789 | 268491.5716 | 2016-10-27 11:00 | 14203.4151 | 105.7% | -4659.9927 | 98.26% | 4d 3h | 103.7% | 86.52% | 2018-04-13 17:00 | 2018-03-14 12:00 | 2018-03-27 09:00 | 2018-04-12 10:00 | 2018-03-14 12:00 | 2018-03-22 17:00 | 2018-04-16 14:00 | 2018-03-27 16:00 | 2018-04-05 12:00 | 1460659.9927 | 1481716.9721 | 1396479.4156 | 1418384.5168 | 1416402.7892 | 1438694.7948 | 1463654.234 | 1468498.4577 | 1.0368 | 1.0569 | 0.86517
TP2 | 2016-10-20 17:00 | 2017-01-10 17:00 | 523799.6876 | 418322.173 | 424560.2399 | 2016-12-12 10:00 | -105477.5145 | 79.86% | -6238.0669 | 98.53% | -21d 6h | 87.71% | 91.58% | 2018-06-12 17:00 | 2018-10-18 14:00 | 2018-11-01 09:00 | 2018-06-11 14:00 | 2018-10-18 14:00 | 2018-10-29 12:00 | 2018-05-22 15:00 | 2018-07-31 12:00 | 2018-08-08 12:00 | 1462238.0669 | 1477712.0342 | 1723882.5245 | 1607613.2214 | 1743258.1632 | 1625255.0392 | 1519189.891 | 1501358.8912 | 0.87712 | 0.79863 | 0.91576
TP3 | 2017-01-10 17:00 | 2017-04-19 17:00 | 765480.8247 | 526138.5674 | 535564.2092 | 2017-01-11 12:00 | -239342.2572 | 68.73% | -9425.6418 | 98.24% | -70d 4h | 71.57% | 90.71% | 2018-08-16 16:00 | 2019-03-12 17:00 | 2019-04-01 10:00 | 2018-08-08 12:00 | 2019-03-12 17:00 | 2019-03-25 16:00 | 2018-07-30 12:00 | 2019-01-30 14:00 | 2019-02-11 16:00 | 1465425.6418 | 1482083.8785 | 1888422.8292 | 1834750.8869 | 1912658.9554 | 1858025.4936 | 1542576.2633 | 1536420.8125 | 0.71573 | 0.68733 | 0.90711
TP4 | 2017-04-19 17:00 | 2017-07-04 17:00 | 875862.0193 | 708316.4004 | 724799.3526 | 2017-03-14 17:00 | -167545.6188 | 80.87% | -16482.9522 | 97.73% | -80d | 73.51% | 91.95% | 2018-07-12 14:00 | 2018-10-08 14:00 | 2018-10-29 10:00 | 2018-07-11 15:00 | 2018-10-08 14:00 | 2018-10-18 10:00 | 2018-08-10 17:00 | 2019-01-03 15:00 | 2019-01-16 16:00 | 1472482.9522 | 1489882.003 | 1649340.5137 | 1741918.4836 | 1670855.1472 | 1765587.4626 | 1517216.1236 | 1529775.74 | 0.7351 | 0.80871 | 0.9195
TP5 | 2017-07-04 17:00 | 2017-09-21 17:00 | 992375.5024 | 903141.5647 | 932866.585 | 2017-07-24 10:00 | -89233.9378 | 91.01% | -29725.0204 | 96.81% | -43d 6h | 87.81% | 93.05% | 2018-06-05 10:00 | 2018-07-02 11:00 | 2018-07-26 16:00 | 2018-06-06 10:00 | 2018-07-02 11:00 | 2018-07-10 17:00 | 2018-06-21 15:00 | 2018-07-30 15:00 | 2018-08-09 09:00 | 1485725.0204 | 1503921.2023 | 1540349.6076 | 1562450.0213 | 1560343.6439 | 1583171.4466 | 1510853.1254 | 1514739.8979 | 0.87813 | 0.91008 | 0.93049
TP6 | 2017-09-21 17:00 | 2017-11-14 17:00 | 1038564.5195 | 939204.7183 | 969034.1487 | 2017-08-16 16:00 | -99359.8012 | 90.43% | -29829.4304 | 96.92% | -64d 1h | 83.85% | 95.6% | 2018-06-08 15:00 | 2018-07-05 17:00 | 2018-07-31 16:00 | 2018-06-13 17:00 | 2018-07-05 17:00 | 2018-07-13 10:00 | 2018-07-20 09:00 | 2018-09-06 10:00 | 2018-09-14 17:00 | 1485829.4304 | 1502243.0074 | 1540501.9373 | 1585384.8114 | 1558651.9299 | 1604960.2978 | 1509479.4108 | 1517027.1654 | 0.83848 | 0.90433 | 0.95601
TP7 | 2017-11-14 17:00 | 2018-02-20 17:00 | 1055178.5827 | 1048260 | 1085156.4 | 2017-12-12 11:00 | -6918.5827 | 99.34% | -36896.4 | 96.6% | -50d 5h | 89.16% | 99.96% | 2018-04-25 11:00 | 2018-04-26 11:00 | 2018-05-22 11:00 | 2018-04-25 17:00 | 2018-04-26 11:00 | 2018-04-27 17:00 | 2018-07-02 14:00 | 2018-07-17 17:00 | 2018-07-23 15:00 | 1492896.4 | 1507247.9331 | 1495587.51 | 1542471.5126 | 1510033.7641 | 1558567.9785 | 1504863.144 | 1513851.776 | 0.8916 | 0.99344 | 0.99961
TP8 | 2018-02-20 17:00 | 2018-03-15 17:00 | 1064801.5971 | 1048260 | 1085156.4 | 2017-12-12 11:00 | -16541.5971 | 98.45% | -36896.4 | 96.6% | -67d 5h | 86.03% | 99.96% | 2018-04-30 15:00 | 2018-05-02 17:00 | 2018-05-29 10:00 | 2018-05-02 12:00 | 2018-05-02 17:00 | 2018-05-04 10:00 | 2018-07-25 14:00 | 2018-08-15 16:00 | 2018-08-21 14:00 | 1492896.4 | 1507247.9331 | 1499330.5583 | 1559118.9578 | 1513908.5594 | 1575801.3764 | 1505640.3346 | 1516693.52 | 0.86028 | 0.98447 | 0.99961
TP9 | 2018-03-15 17:00 | 2018-04-05 17:00 | 1250550.9259 | 1177400 | 1209390 | 2018-04-02 10:00 | -73150.9259 | 94.15% | -31990 | 97.35% | -3d 6h | 99.25% | 99.31% | 2018-05-28 14:00 | 2018-06-05 14:00 | 2018-06-26 11:00 | 2018-06-01 10:00 | 2018-06-05 14:00 | 2018-06-06 16:00 | 2018-04-26 15:00 | 2018-04-26 16:00 | 2018-04-27 10:00 | 1487990 | 1495559.5719 | 1505299.1965 | 1490099.5406 | 1513339.0599 | 1497726.4289 | 1497455.8654 | 1494450.6392 | 0.99248 | 0.94151 | 0.99313
TP10 | 2018-04-05 17:00 | 2018-04-28 17:00 | 1456000 | 1456000 | 1476290 | 2018-04-20 17:00 | 0 | 100% | -20290 | 98.63% | -5d | 99.03% | 100% | 2018-04-20 17:00 | 2018-04-20 17:00 | 2018-05-02 09:00 | 2018-04-27 17:00 | 2018-04-27 17:00 | 2018-04-27 17:00 | 2018-04-27 17:00 | 2018-04-27 17:00 | 2018-04-27 17:00 | 1476290 | 1476290 | 1476290 | 1476290 | 1476290 | 1476290 | 1476290 | 1476290 | 0.99029 | 1 | 1

## Corrective actions Overview
General |  |  | Corrective actions
Name | Start Tracking Period | Status date | Category | Description
TP1 | 2016-05-09 08:00 | 2016-10-20 17:00 | - | -
TP2 | 2016-10-20 17:00 | 2017-01-10 17:00 | - | -
TP3 | 2017-01-10 17:00 | 2017-04-19 17:00 | C3 | Use new resource/supplier
TP4 | 2017-04-19 17:00 | 2017-07-04 17:00 | - | -
TP5 | 2017-07-04 17:00 | 2017-09-21 17:00 | - | -
TP6 | 2017-09-21 17:00 | 2017-11-14 17:00 | - | -
TP7 | 2017-11-14 17:00 | 2018-02-20 17:00 | - | -
TP8 | 2018-02-20 17:00 | 2018-03-15 17:00 | C1 | Status update call employees
TP9 | 2018-03-15 17:00 | 2018-04-05 17:00 | - | -
TP10 | 2018-04-05 17:00 | 2018-04-28 17:00 | - | -